## Program List
Tower | Supplier | Facility name | Facility Location | Commodity | Performing GCM | SAQ Date (SAQ=Self Assesement Questonnaire) | SAQ Score | SAQ Target date | SAQ Remarks | Last Audit | Audit Category | CAP got or not | CAP Target date | Remaining Open items | Remaining Open Item Details | E12 Finding(next tier management) | Open Priority Finding | Audit Target Date | Audit/CAP Remark | WH Report Request Date | WH Report Due Date | 60 Hours/week Compliance | ODM/TCO | VAP Recognition | Number of Workers
NB ODM | Wistron | WISTRON INFOCOMM (KUNSHAN) CO., LTD | Kunshan | NB ODM | Tavia Yu | 2020-06-17 | 91.8% | 2021-06-17 |  | 2019-07-20 | Non-VAP | no need | N/A | 0 |  | 0 | 0 | 2021-07-20 |  |  |  | Yes | yes
NB ODM | Compal | Compal Information Technology(KUNSHAN) CO., LTD | Kunshan | NB ODM | Jessie Yue4 Li | 2020-04-08 | 91.7% | 2021-04-08 |  | 2018-04-27 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2020-08-31 | Originally committed the audit will be done in July 2020. And then to Oct, and now to Jan 2021. The latest concern is Covid-19. |  |  | Yes | yes
NB ODM | QUANTA | Tech-Com (Shanghai) Computer CO., Ltd | Shanghai | NB ODM | Vivian Ruan/Ge Jing | 2020-03-31 | 94.5% | 2021-03-31 |  | 2020-09-09 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2022-09-09 |  |  |  | Yes | yes
NB ODM | Huaqin | Nanchang Huaqin Electronic Technology Co., Ltd | Nanchang | ODM | Sandy Chen | 2020-05-13 | 93% | 2021-05-13 |  | 2018-01-04 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-06-30 | 20200409:Huaqin 笔电项目都在新建好的南昌工厂(Nanchang Qinsheng)，南昌华勤是新工厂，后续认证审核在南昌园区ready后进行，已经在做审计计划。东莞厂只生产手机手表，目前不生产联想产品。Lenovo phones were made in Moto Wuhan factory. |  |  | No | yes
Power | LGC | LG Chem: LG Chem(Nanjing)I & E Materials Co., Ltd | Nanjing | NB Battery | Hunter Gao | 2020-05-06 | 91.3% | 2021-05-06 |  | 2020-01-16 | VAP | yes | N/A | 1 | A4.4b | 0 | 0 | 2022-01-16 | by 202009-A3.1&A3.2 Major | 2020-10-19 | 2021-01-19 | No
Power | Simplo | Simplo Technology (ChongQing) INC. | Chongqing | NB Battery | Hunter Gao | 2020-03-17 | 93.6% | 2021-03-17 |  | 2020-04-17 | VAP | yes | N/A | 2 | A3.1, A3.3 | 0 | 0 | 2022-04-17 |  |  |  | No
Power | LITEON | LITE-ON Technology (ChangZhou) CO.,Ltd.,the Power Plant | Changzhou | NB Adapter | Jukka Song | 2020-03-20 | 94.7% | 2021-03-20 |  | 2019-10-21 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-10-21 | WH is under good control since 2017 |  |  | Yes |  | Silver
Power | Delta | Delta Electronics (Jiangsu) Ltd | Suzhou | NB Adapter | Jukka Song | 2020-03-29 | 98% | 2021-03-29 |  | 2019-12-12 | VAP | yes | N/A | 2 | A3.2, A3.3 | 0 | 0 | 2021-12-12 | Next RBA audit is a VAP audit: Dec, 2021 |  |  | Yes
Power | ATL | Amperex Technology Limited | Ningde | Battery | Frank Wang | 2020-08-03 | 95.1% | 2021-08-03 | Suggest supplier grant Lenovo access to audit too | 2018-12-19 | Non-VAP | yes | N/A | 1 | A3.1 (keep on priority level since June, Oct to major 2020) | 0 | 0 | 2020-12-31 | Next RBA audit is a VAP audit: June 2021 / 根据供应商要求改过一次 | 2020-11-12 | 2021-02-12 | No
Power | Sunwoda | Sunwoda Electronic Co., Ltd. | Shenzhen | NB Battery | Hunter Gao | 2020-07-06 | 95.8% | 2021-07-06 |  | 2020-09-15 | Non-VAP | yes | N/A | 2 | A4.4b, C1.1 | 0 | 0 | 2022-09-15 | Next RBA audit is a VAP audit:2022 |  |  | Yes
Power | Salom | Salom Electric (Xiamen) Co., Ltd. | Xiamen | Charger | William Cheng | 2020-10-15 | 94.2% | 2021-10-15 |  | 2019-09-27 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-09-27 | Plan to apply the VAP audit in Oct 2021. |  |  | No
Power | Celxpert | Celxpert (Kunshan)Energy Co.,LTD. 加百裕工業股份有限公司 | Kunshan | NB Battery | Hunter Gao, Jack Cui | 2020-09-14 | 92.3% | 2021-09-14 |  |  |  |  | N/A | 0 |  | 0 | 0 | 2020-12-31
Power | SCUD | SCUD（FUJIAN）ELECTRONICS CO., LTD | Fuzhou | Battery | Frank Wang <frankwang@motorola.com> | 2020-03-05 | 94.7% | 2021-03-05 |  | 2020-08-12 | VAP | yes | N/A | 0 |  | 0 | 0 | 2022-08-12 |  |  |  | Yes |  | Silver
Power | ChenYang | 江苏辰阳电子有限公司 | Danyang | Charger | William Cheng | 2020-08-28 | 92.9% | 2021-08-28 |  | 2020-08-20 | VAP | yes | N/A | 0 |  | 0 | 0 | 2022-08-20 | A3.1, A3.2, A3.3 are closed based on data from Oct. | 2020-11-28 | 2021-02-28 | Yes
Power | Chicony | Chicony Power Technology(SuZhou) Co. Ltd | Suzhou | NB Adapter | Jukka Song | 2020-03-26 | 93.9% | 2021-03-26 |  | 2020-08-18 | VAP | no need | N/A | 0 |  | 0 | 0 | 2022-08-18 |  |  |  | Yes |  | Platinum
DT/WS | Wistron | Wistron InfoComm (Zhongshan) Corporation | Zhongshan | AIO ODM | Jie Jie25 Li <lijie25@lenovo.com> | 2020-03-24 | 91.1% | 2021-03-24 |  | 2019-07-11 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-07-11 | A3.1 is a major finding, but it is about local law |  |  | Yes | yes | Silver
DT/WS | ECS | Golden Elite Technology (Shenzhen) Ltd. | Shenzhen | DT ECAT | Thomas Yang | 2020-03-16 | 94.1% | 2021-03-16 |  | 2020-07-27 | VAP | yes | N/A | 1 | A4.4b | 0 | 0 | 2022-07-27 |  |  |  | Yes | yes | Silver | 2860
DT/WS | MSI | MSI Computer (Shenzhen) Co., Ltd. (Micro-Star Int'l Co., Ltd.) | Shenzhen | DT ECAT / VGA | Thomas Yang | 2020-03-18 | 96.3% | 2021-03-18 |  | 2019-10-17 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-10-17 |  |  |  | Yes |  | Silver
DT/WS | AVC | Asia Vital Component (Shenzhen) Co., Ltd. | Shenzhen | DT Thermal | Jessica Liu | 2020-03-23 | 92.7% | 2021-03-23 |  | 2019-09-20 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-09-20 | by 202006: A3.1 &A3.2 on major//by 202003 data: A3.1 &A3.2 reached minor level by Jan 2020 (all facility) & A3.1 major, A3.2 major (Lenovo line dedicated)//A3.1 & A3.2 keep on priority level | 2020-07-28 | 2021-01-28 | No
DT/WS | AVC | Asia Vital Components (Dongguan) Co., Ltd. | Dongguan | DT AIO | Kevin Wang | 2020-09-24 | 96.1% | 2021-09-24 |  | 2020-08-14 | Non-VAP | yes | N/A | 1 | C1.2b | 0 | 0 | 2022-08-14 | C1.2b还在等待政府部门的批复,预计12月底可完成/ A3.1, A3.3 are minor findings based on RBA deciplines. |  |  | Yes | yes
DT/WS | Huntkey | Shenzhen Huntkey Electric Co., Ltd | Shenzhen | DT PSU | Yang Xuan | 2020-03-04 | 97.3% | 2021-03-04 |  | 2020-11-27 | Non-VAP | no | 2021-02-21 | 0 |  | 0 | 0 | 2022-11-27 | 20200511-针对“C1.1b”问题点，我们工厂已经在施工，预计8月份完成并获得《环保设施竣工验收报告》; closed on Dec 8-A3.1 exceed legal requirement// Will have VAP on 2021/12/31(CPO) |  |  | Yes |  |  | 420
DT/WS | Jiatian | DONGGUAN JIATIAN ELECTRONICS TECHNOLOGY CO.,LTD | Dongguan | DT ME | Elain Liu | 2020-07-02 | 90.9% | 2021-07-02 | Jiatian company level and facility are the same one. | 2019-08-03 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-08-03 |  |  |  | Yes
DT/WS | Acbel | Acbel Electronic (Dong Guan) Co., Ltd | Dongguan | DT PSU | Yang Xuan | 2020-03-17 | 95.2% | 2021-03-17 |  | 2020-07-13 | VAP | yes | N/A | 2 | A3.1, A3.3 | 0 | 1(A3.1) | 2022-07-13 | 2020 July data reached minor, Nov. reach priority according to the WH report. //20200511: 目前我司工廠端預計7月改善完成，並預計在7月底8月初進行缺失項的closure audit | 2020-12-17 | 2021-03-17 | No |  | Silver
DT/WS | Taisol | Dong Guan TaiSol Electronics Co,;Ltd | Dongguan | DT Thermal | Jessica Liu | 2020-04-08 | 92.1% | 2021-04-08 |  | 2020-08-27 | VAP | yes | N/A | 2 | A4.4b, B2.1b | 0 | 0 | 2022-08-27 |  |  |  | Yes
DT/WS | FSP | FSP TECHNOLOGY INC.: Shenzhen Huili-Fuyong Electronics Co.,Ltd//深圳輝力電子有限公司 | Shenzhen | DT PSU | Yang Xuan | 2020-03-19 | 93.5% | 2021-03-19 |  | 2019-08-29 | Non-VAP | yes | N/A | 1 | C2.1 | 0 | 0 | 2021-08-29 | A3.1&A3.2 Keep on priority levels in the past years// Will have VAP 2022.8.31 (CPO) |  |  | No
DT/WS | Bitland | Shenzhen Bitland Information Technology Co., Ltd | Shenzhen | DT VGA | Meng Xiaojie | 2020-03-10 | 86.6% | 2021-03-10 |  | 2020-06-09 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2022-06-09 | Will have VAP on 2022/6/1(CPO) |  |  | No
DT/WS | Honhai (Foxconn) | Foxconn - NEW PCEBG (DT1&EMD, New PCEBG, Foxconn Wuhan） | WuHan | DT ME | Elain Liu | 2020-03-23 | 97.2% | 2021-03-23 | Under Foxconn New PCEBG-AP3, New PCEBG, Foxconn Wuhan | 2019-11-18 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-11-18 | Will have VAP on 2022/3(CPO) |  |  | Yes | yes
DT/WS | Flex | Flextronics International Kft | Hungary PCG | DT/WS ODM | Monika Mosna | 2020-06-08 | 90.3% | 2021-06-08 |  | 2018-11-22 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021/6/31 | RBA VAP audit dates with RBA team to Nov 20, 2020/ postponement due to COVID-19, confirmed by David through email / based on David email, postpone to 2021/6/31 (documentation)(check whether the inter-production shift or still stick the plan) |  |  | Yes | yes
ACC/PPS | Luxshare | Luxshare Precision Industry Co., Ltd.: Dongguan Xuntao Electronic Co.,Ltd. | Dongguan | DT Cables & Power Cords | Mandy Xia | 2020-04-16 | 93.7% | 2021-04-16 |  | 2020-06-04 | VAP | yes | N/A | 2 | A3.1, A3.3 | 0 | 0 | 2022-06-04 | The Dongguan factory plans to apply for an RBA-VAP audit again in Sept 2020 ; A3.1 major (almost 40%)& A3.2 minor; kept on major level for 6 months |  |  | No |  | Silver
ACC/PPS | Sunrex(JME) | JING MOLD ELECTRONICS TECHNOLOGY(SHENZHEN)CO.,LTD | Shenzhen | KB&MS | Grace Jin | 2020-05-27 | 93.2% | 2021-05-27 |  | 2020-11-24 | Non-VAP | no | 2021-02-07 | 0 |  | 0 | 0 | 2022-11-24 | Will have a VAP on 2022/12/31(CPO) |  |  | Yes
ACC/PPS | Goodway | Goodway Electronic (Kunshan) Co., Ltd. | Kunshan | USB Docking | William Guo | 2020-07-02 | 89.2% | 2021-07-02 |  | 2020-04-15 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2022-04-15 |  | N/A |  | No
ACC/PPS | USI | USI Electronics(ShenZhen)CO.,LTD: Universal Scientific Industrial (Shanghai) Co., Ltd. | Shenzhen | Dock | Vonesa Chen | 2020-03-19 | 95.2% | 2021-03-19 |  | 2019-10-16 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-10-16 |  |  |  | Yes |  | Silver
ACC/PPS | PRIMAX | PRIMAX ELECTRONICS (ChongQing) Corp., LTD | Chongqing | DT KB&MS | Grace Jin | 2020-03-23 | 94.1% | 2021-03-23 |  | 2020-04-29 | VAP | yes | N/A | 1 | A4.4b | 0 | 0 | 2022-04-29 |  |  |  | Yes |  | Silver
Memory/SSD | RAMAXEL (Unionmem) | Ramaxel Technology (Huizhou) Ltd. | Huizhou | Memory/SSD | Leon Lin1 Gan/Jeff Luo | 2020-04-17 | 93.5% | 2021-04-17 |  | 2019-04-03 | Non-VAP | yes | N/A | 1 | A3.1 | 0 | 0 | 2021-04-03 | A3.1 A3.2 reached minor in June 2019, but rose to priority from Aug 2019 again// Will have VAP on 2021/9/31(CPO) | 2020-10-28 | 2021-01-28 | No
Memory/SSD | SANDISK(WD) | SanDisk Storage Malaysia Sdn Bhd | Malaysia | SSD | Jeff Luo | 2020-04-16 | 91.3% | 2021-04-16 |  | 2020-08-19 | VAP | yes | N/A | 0 |  | 0 | 0 | 2022-08-19 |  |  |  | Yes
Brazil Proc. | Envision(TPV) | Envision Indústria de Produtos Eletrônicos Ltda. | Manaus | NB ODM | Lucas Geraldo | 2020-05-21 | 94.5% | 2021-05-21 |  | 2019-08-13 | VAP | no need | N/A | 0 |  | 0 | 0 | 2021-08-13 | 20200916: Our company plans to perform this audit between the end of January and the beginning of March, 2021.;The proposed audit start date is between 03/02/2021 and 03/04/2021. | N/A |  | Yes | yes | Platinum
HDD/ODD | Toshiba | AFI Technologies (ChangAn) Ltd. 东莞时力科技电子有限公司 | Dongguan | HDD | Danny Zhao | 2020-09-14 | 95.3% | 2021-09-14 |  | 2018-12-18 | VAP | yes | N/A | 0 |  | 0 | 0 | 2020-12-31 | Closed on Dec 8-A3.1 fail local requirement; the audit is finally fixed on 12/17/2020-12/18/2020, submit the report by week 21 Dec. It is likely to be ready by week 28 Dec. |  |  | Yes
HDD/ODD | Seagate | Seagate Technology (Wuxi)Co. Ltd | Wuxi | HDD | Danny Zhao | 2020-03-26 | 92.7% | 2021-03-26 |  | 2020-08-24 | VAP | no need | N/A | 0 |  | 0 | 0 | 2022-08-24 | The proposed audit start date is between 13/04/2020 and 24/04/2020. |  |  | Yes |  | Platinum
HDD/ODD | WD | WESTERN DIGITAL THAILAND COMPANY LTD. | Thailand | HDD | Danny Zhao | 2020-03-31 | 93.3% | 2021-03-31 |  | 2019-08-15 | VAP | no need | N/A | 0 |  | 0 | 0 | 2021-08-15 |  |  |  | Yes |  | Gold
HDD/ODD | HLDS | Hitachi-LG Data Storage (Hui Zhou), Ltd. | Huizhou | ODD | Carol Zhu | 2020-03-30 | 93.2% | 2021-03-30 |  | 2020-08-26 | VAP | yes | N/A | 3 | A3.1, A3.3, A4.1 | 0 | 0 | 2022-08-26 |  |  |  | Yes |  | should be Silver
HDD/ODD | PLDS | Philips & LITE-ON Digital Solution Corp // LITEON OPTO TECHNOLOGY (BEIHAI) LTD. | Beihai | ODD | Carol Zhu | 2020-08-27 | 95.6% | 2021-08-27 |  | 2020-11-12 | VAP | no | 2021-02-08 | 0 |  | 0 | 0 | 2022-11-12 |  |  |  | Yes
NB Components | Chicony | Chicony Electronics (Dongguan) Co.,Ltd | Dongguan | NB KB & Camera | Bill Ru (rujg1) | 2020-05-05 | 94.8% | 2021-05-05 |  | 2020-06-23 | VAP | yes | N/A | 3 | A3.1, A3.3, A4.3 | 0 | 0 | 2022-06-23 | 10/21(一)已提供 8~9月份之工時資料 |  |  | No |  | should be Silver
NB Components | O-FILM | Ofilm Microelectronics System Co., Ltd 微电子 | Nanchang FPR | Finger Print Reader | Michelle Qiu | 2020-05-28 | 95.1% | 2021-05-28 |  | 2020-07-30 | VAP | yes | N/A | 2 | A4.4b, B2.1b | 0 | 0 | 2022-07-30 |  |  |  | Yes |  | should be Silver
Display | AUO | AU Optronics (Suzhou) Corporation | Suzhou | NB LCD | Bruce Li / Zhu Qing | 2020-04-23 | 92.5% | 2021-04-23 |  | 2019-10-21 | VAP | yes | N/A | 2 | A3.2, A3.3 | 0 | 0 | 2021-10-21 | 20191227 New audit-A3.2 on major level; |  |  | Yes |  | Silver
Display | BOE | Beijing BOE Display Technology Co.,Ltd. | Beijing | NB LCD | Bruce Li / Zhu Qing | 2020-07-15 | 94% | 2021-07-15 |  | 2019-06-20 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-06-20 |  |  |  | Yes |  | Silver
Display | LGD | LGDNJ | Nanjing | NB LCD | Bruce Li / Zhu Qing | 2020-05-07 | 91.9% | 2021-05-07 |  | 2020-09-15 | VAP | no | 2021-01-05 | 5 | A3.1, A3.2, A3.3, B1.1b, B2.1b | 0 | 0 | 2022-09-15 |  |  |  | Yes |  | should be Silver
Display | Infovision (IVO) | InfoVision Electronics (Kunshan) Co., Ltd | Kunshan | NB LCD | Bruce Li / Zhu Qing | 2020-07-17 | 96.1% | 2021-07-17 |  | 2020-06-17 | Non-VAP | yes | N/A | 4 | A3.1, A3.2 A3.3, A4.4b | 0 | 0 | 2022-06-17 | Will have VAP on 2021/9/31 |  |  | No
Display | Innolux | Foxconn-Innolux Corporation: Innolux Corporation-Ningbo | Ningbo | NB LCD | Bruce Li / Zhu Qing | 2020-07-20 | 95.2% | 2021-07-20 |  | 2020-10-23 | VAP | yes | N/A | 4 | A3.1, A3.2, A3.3, A4.4b | 0 | 1(A3.1) | 2022-10-23 |  | 2020-12-01 | 2021-03-01 | No
Display | TPV | TPV Electronics (Fujian) Co.,Ltd | Fuqing | MNT | Iris Zhang / Karen Wang | 2020-03-14 | 95% | 2021-03-14 |  | 2020-05-13 | VAP | yes | N/A | 0 |  | 0 | 0 | 2022-05-13 |  | under good control |  | Yes | yes | should be Silver
Display | TPV | TPV Display Technology (China) Co., Ltd | Beijing | MNT | Iris Zhang / Karen Wang | 2019-11-29 | 94.5% | 2020-11-29 |  | 2019-11-15 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-11-15 | 20191220: 审计分数正在询问//A3.1 major for local requirement | under good control |  | Yes | yes
Display | Foxconn | Foxconn - NEW PCEBG;Hongfujin Precision Electronics (Chongqing) Co., Ltd | Chongqing | MNT | Iris Zhang / Karen Wang | 2020-03-23 | 96.9% | 2021-03-23 |  | 2018-12-18 | VAP | yes | N/A | 1 | A4.4b | 0 | 0 | 2020-12-18 | Supplier said B4.1b closed, but no evidence |  |  | Yes | yes
Display | L&T(TPV) | L&T Display Technology (Fujian)Ltd 捷星显示科技（福建）有限公司 | Fuqing | MNT | Iris Zhang / Karen Wang | 2020-07-16 | 90.6% | 2021-07-16 |  | 2020-09-22 | VAP | no | 2020-12-07 | 0 |  | 0 | 0 | 2022-09-22 |  | under good control |  | Yes | yes | should be Silver
Display | Mutto | Mutto Optronics(Suzhou) Co., LTD | Suzhou | MBG Display | James SJ5 Xu / David Wei14 Xiong | 2019-12-21 | 89.7% | 2020-12-21 |  |  |  |  | N/A | 0 |  | 0 | 0 | 2019-12-31 | 202007-postponed to 2020 Aug. //20190916-Supplier confirm to complete audit by the end of 2019. The plan has been postponed again and again.
Display | DJN | Shenzhen DJN Optronics Technology CO.,LTD | Shenzhen | MBG Display | James SJ5 Xu / David Wei14 Xiong | 2020-06-07 | 92.5% | 2021-06-07 |  | 2020-09-23 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2022-09-23 | 20191020-联想产线目前在江门厂，会先安排深圳厂审计，再安排江门厂审计；20190925-DJN 审计将于2019年年底完成；20190125-DJN 的RBA 审计，供应商已在规划安排中，target date 请协助改成2019/6/30 |  |  | Yes
Display | K-TRONICS(BOE) | K-TRONICS (SUZHOU) TECHNOLOGY CO., LTD. | Suzhou | MNT | Iris Zhang / Karen Wang | 2020-03-23 | 93.7% | 2021-03-23 |  | 2020-07-10 | VAP | yes | N/A | 4 | B1.1b, B7.1b, C1.1b, E12.2b | E12.2b | 0 | 2022-07-10 |  |  |  | Yes | yes
Display | Laibao | Chongqing Laibao Technology Co., Ltd | Chongqing | Touch Panel | Kenny Xiao / Brian Wang | 2020-12-09 | 93.4% | 2021-12-09 |  | 2019-01-10 | VAP | yes | N/A | 2 | B2.2, B3.1b | 0 | 0 | 2021-01-10 |  |  |  | Yes
Display | Tianma | Shanghai AVIC Optoelectronics co.,LTD | Shanghai | MBG Display | James SJ5 Xu / David Xiong | 2020-04-22 | 90.8% | 2021-04-22 |  | 2019-07-12 | VAP | yes | N/A | 11 | A1.1, A1.2, A6.3, B1.4b, B7.1b, B7.2b, C3.2, E4.1, E5.1, E10.1b, E12.2b | E12.2b | 1(A1.1) | 2021-07-12 |  |  |  | No
Display | Huntkey | Hefei Huntkey Display Technology Co.,Ltd. | Hefei | MNT | Iris Zhang / Karen Wang | 2020-09-24 | 90.6% | 2021-09-24 |  | 2019-01-17 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-01-17 |  |  |  | Yes | yes
Display | Wistron | Wistron (Zhongshan) Linhai Branch | Zhongshan Linhai | MNT | Iris Zhang / Karen Wang | 2020-03-24 | 91.9% | 2021-03-24 |  | 2019-07-19 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-07-19 | the RBA VAP initial Audit will take place on 7/14~7/16. | N/A |  | Yes | yes | Silver
Display | BOE | Hefei BOE Vision-electronic Technology Co.,Ltd. | Hefei | MNT | Iris Zhang / Karen Wang | 2020-03-18 | 93.3% | 2021-03-18 | BOE Hefei will still manufacture for Lenovo | 2019-04-30 | VAP | yes | N/A | 2 | A1.2, A4.4b | 0 | 0 | 2021-04-30 |  |  |  | Yes | yes
Logic/Software | NVIDIA | ODM: Taiwan Semiconductor Mfg. Company | Taiwan | GPU | Eric Starkovich | 2020-04-10 | 93.5% | 2021-04-10 | Both NVIDIA and TSMC’s timeline for completion is early June. | 2019-07-15 | VAP | no need | N/A | 0 |  | 0 | 0 | 2021-07-15 |  |  |  | Yes |  | Platinum
Logic/Software | CYBERTAN | Foxconn-CNSBG FCQ | Chongqing | Wireless | Yang Chao | 2020-04-23 | 93.9% | 2021-04-23 |  | 2019-07-09 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-07-09 |  |  |  | Yes
Logic/Software | Fibocom | BYD precision manufacturing co. LTD | Shenzhen | Communication | Yang Chao | 2020-10-27 | 96.1% | 2021-10-27 |  |  |  |  | N/A | 0 |  | 0 | 0 | N/A
Logic/Software | Fibocom | ShenZhen Eternity Technology Co., Ltd. | Shenzhen | Communication | Yang Chao |  |  | 2021-01-31 | 根据供应商提供的日期改过一次 |  |  |  | N/A | 0 |  | 0 | 0 | N/A
Logic/Software | Skyworks | Skyworks - Mexicali | Mexico | RF | Haoling Zhai | 2020-07-22 | 93.2% | 2021-07-22 |  | 2016-09-06 | VAP | yes | N/A | 0 |  | 0 | 0 | Exempted | Skyworks is RBA Full Member |  |  | Yes
Logic/Software | Qualcomm | Qualcomm Incorporated -ODM TSMC/Samsung (covered already) | Taiwan | Chipset | Hui Lv | 2020-04-10 | 93.5% | 2021-04-10 | Qualcomm own SAQ 13/06/2019, 89% | 2019-07-15 | VAP | no need | N/A | 0 |  | 0 | 0 | 2021-07-15 |  |  |  | Yes |  | Platinum
Logic/Software | MTK | 1.MediaTek -ODM TSMC 2.MediaTek Singapore Pte. Ltd-ODM TSMC | Taiwan/ Singapore | Chipset | Hui Lv | 2020-04-10 | 93.5% | 2021-04-10 |  | 2019-07-15 | VAP | no need | N/A | 0 |  | 0 | 0 | 2021-07-15 |  |  |  | Yes |  | Platinum
Mobile ODM EMS | Wingtech | Lenovo Wuhan site | Wuhan | ODM | Roc Zhao | 2020-09-24 | 90.6% | 2021-09-24 |  |  |  |  | N/A | 0 |  | 0 | 0 | N/A | No phone project in WT facility now, Moto phone produced in Wuhan plant. No ACC products produced in Wingtech too. |  |  |  | yes
Mobile ODM EMS | TINNO | Jiangxi Maxon Communication Co.,Ltd | Nanchang | ODM | Roc(dapeng) Zhao, Daniel Li | 2020-08-13 | 95% | 2021-08-13 |  | 2020-10-20 | VAP | yes | N/A | 0 |  | 0 | 0 | 2022-10-20 | Per our EMS strategy, the 1st priority is Maxon Nanchang factory// Current TINNO projects are built in Wuhan for all FY2021, it might keep the possibility to use TINNO Nanchang factory in the future when Wuhan capacity constraint, but so far we cannot predict if any products will be built in there (From Daniel Li) |  |  |  |  | Silver
Mobile ODM EMS | Ontim | Shenzhen Chino-e Communication Co., Ltd / 变更为：Guangdong Enok Communication Co., Ltd. | Dongguan | ODM | Wendy Wen | 2020-11-17 | 92.1% | 2022-11-17 | 根据供应商提供的日期改过一次 / 建议下次做facility level |  |  |  | N/A | 0 |  | 0 | 0 | 2021-06-01 |  |  |  |  | yes
Mobile ODM EMS | Flex | Flextronics Jaguariuna | Jaguariuna | EMS | Lei Jiang | 2020-05-07 | 95.9% | 2021-05-07 |  | 2020-01-24 | Non-VAP | no need | N/A | 0 |  | 0 | 0 | 2022-01-24 |  |  |  | Yes | yes
Mobile ODM EMS | Flex | Manaus | Manaus | EMS | Lei Jiang | 2020-05-15 | 96% | 2021-05-15 |  | 2019-11-06 | Non-VAP | yes | N/A | 1 | CAR-00082206 | 0 | 0 | 2021-09-21 | 20200722-The proposed audit start date is between 11/02/2020 and 11/30/2020.；//In 2019 we will have another audit based on the RBA standard that is equivalent for 3 years. |  |  | yes | yes
Mobile ODM EMS | Flex | Flextronics Technologies India Pvt Ltd | India | EMS | Louis Li | 2020-05-08 | 91.5% | 2021-05-08 |  | 2018-11-30 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021/2/31 | The proposed audit start date is between 01/11/2021 and 02/28/2021 / 受印度疫情影响(接近九百万确诊病例)，RBA team已经通知Flex India， Audit会推迟到2021年2月份展开(20201118邮件). |  |  | Yes | yes | Silver
Mobile ODM EMS | TDF | Grupo Newsan | Argentina | EMS | Lei Jiang | 2020-04-24 | 80.9% | 2021-04-24 |  |  |  |  | N/A | 0 |  | 0 | 0 | 2019-12-05 | 20200804-Supplier is disable to receive any kind of visitors into Tierra del Fuego due to coronavirus that it is still present in Argentina. We should postpone the on-site audit until the borders will reopen. The prevous target date 20200715 is invalid, since it is based on supplier's misunderstanding on RBA audit. |  |  |  | yes
Mobile Components | Q-tech | Kunshan Q Technology Limted | Kunshan | Imager | Jenny Liu | 2020-06-03 | 86% | 2021-06-03 |  | 2019-09-04 | Non-VAP | yes | N/A | 4 | B1.1b B2.1 B7.1b C1.1b | 0 | 0 | 2021-09-04 |  |  |  | Yes
Mobile Components | Sunny | Ningbo Sunny Opotech Co., Ltd. | Ningbo | Imager | Jenny Liu | 2020-08-10 | 94.1% | 2021-08-10 |  | 2020-09-22 | Non-VAP | yes | N/A | 2 | A4.1, B2.4 | 0 | 0 | 2022-09-03 | The audit schedule postponed again and again. Supplier lose their credit. | 2020-11-30 | 2021/2/30 | Yes
Mobile Components | COMPEQ | Compeq Manufacturing Co.,Ltd. | Taiwan | PCB | Guohc1 | 2020-03-17 | 97.8% | 2021-03-17 |  | 2020-06-29 | VAP | yes | N/A | 0 |  | 0 | 0 | 2022-06-29 |  | N/A |  | Yes |  | Silver
Mobile Components | BYD | 惠州比亚迪电子有限公司:惠州市大亚湾区响水河工业区比亚迪工业园 | Huizhou | ME | Bobby Gu | 2020-03-24 | 92.1% | 2021-03-24 |  | 2020-05-28 | VAP | yes | N/A | 7 | A3.1, A3.2, A3.3, A4.1, A4.2, A4.4b, B3.4 | 0 | 0 | 2022-05-28 | 2020 审计报告表明工时没有保持在priority以下//20200114：Plastic业务主体是比亚迪精密，在深圳，现在基本没业务。 | 2020-11-23 | 2021-02-23 | No
Mobile Components | O-FILM | Nanchang O-FILM optical-Electronic Heck Co.,LTD 光电 | Nanchang Imager | Imager | Jenny Liu | 2020-08-12 | 92.3% | 2021-08-12 |  | 2020-09-03 | VAP | yes | N/A | 1 | A4.4b | 0 | 0 | 2022-09-03 |  |  |  | Yes |  | should be Silver
Mobile Components | O-FILM | Ofilm Microelectronics System Co., Ltd | Nanchang FPM | FPM | Shi Qiangyong | 2020-05-28 | 95.1% | 2021-05-28 |  | 2020-07-30 | VAP | yes | N/A | 2 | A4.4b, B2.1b | 0 | 0 | 2022-07-30 | 关于B1.1b和b7.1b涉及的几栋楼，目前Ofilm已向当地政府发函且收到回函，需等政府收回产权再改造报批。目前还无法提供证明（Xinpei1207- email） |  |  | Yes |  | should be Silver
Android&Chrome&Cloud | Genrpro | 安徽精卓光显技术有限责任公司 | Nanchang | Touch Panel | Yuan Yuan |  |  | 2021-02-01 |  |  |  |  | N/A | 0 |  | 0 | 0 | 2021-08-30
Android&Chrome&Cloud | Longcheer | 龙旗电子（惠州）有限公司 | Huizhou | ODM | Haishan Gu | 2020-08-31 | 93% | 2021-08-31 |  | 2020-10-28 | VAP | yes | N/A | 0 | 0 | 0 | 0 | 2022-10-28 |  |  |  | Yes | yes | should be Silver |  | CSR Focal 郭红方
Android&Chrome&Cloud | GTK | GoerTek Inc. | Weifang | Baseunit | Baodong Cheng | 2020-08-07 | 93.6% | 2021-08-07 |  | 2019-08-07 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-08-07 |  |  |  | Yes | yes
Android&Chrome&Cloud | GTK | GOERTEK VINA CO., Ltd | Vietnam | Baseunit | Baodong Cheng | 2020-08-11 | 92.1% | 2021-08-11 |  | 2019-08-06 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-08-06 |  | 2020-10-14 | 2021-01-14 | Yes | yes
Android&Chrome&Cloud | 3NOD | Shenzhen 3NOD Digital Technology Company LTD | Shenzhen | Smart Speaker ODM | Yiqing Liu | 2020-11-02 | 92.1% | 2021-11-02 |  | 2019-12-26 | VAP | yes | N/A | 6 | A3.1 A3.3 A4.2 A4.4b B1.2 C3.1b | 0 | 0 | 2021-12-26 |  |  |  | No | yes | Silver
Android&Chrome&Cloud | Tonly | TCL Technoly Electronics (Huizhou) Co., Ltd. | Huizhou | Smart Device | Yiqing Liu | 2020-03-07 | 93.8% | 2021-03-07 |  | 2019-03-28 | VAP | yes | N/A | 1 | A3.1 | 0 | 0 | 2021-03-28 |  |  |  | No | yes | Silver
LCFC | HANNSTAR | Hannstar Board Technology (JiangYin) Corp. | Jiangyin | PCB | Li Betty | 2020-08-31 | 93.5% | 2021-08-31 |  | 2020-04-24 | Non-VAP | yes | N/A | 4 | A3.1, B1.1b,B2.1b, B4.1b, C7.1 | 0 | 0 | 2022-04-24 | A3.1达到关闭状态，需要等到供应商的target day和具体执行结果 |  |  | Yes
LCFC | Chunqiu | Suzhou Chunqiu Electronic Technology Co.,LTD 苏州春秋电子科技股份有限公司 | Kunshan | Plastic | Hu Cherry | 2020-07-28 | 90.3% | 2021-07-28 |  | 2019-06-19 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-06-19 |  |  |  | No
LCFC | Victory | Victory Technology (HongKong) Limit. Anhui Victory Precision Manufacture Technology Co., Ltd. | Liuan | Plastic | Hu Cherry | 2020-05-19 | 92.3% | 2021-05-19 |  | 2019-11-24 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-11-24 |  |  |  | Yes
LCFC | Toray Kohwa | KOHWA PRECISION MOLDING （SHANGHAI）CO.,LTD. | Shang Hai | A Cover (CFRP) | Yao Chunxiao | 2020-08-14 | 87.9% | 2021-08-14 |  | 2019-01-23 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-01-23 |  |  |  | yes
LCFC | Toray Taiyi | Taiyi Electronic(Kunshan)Co.,LTD | Kunshan | A Cover (CFRP) | Yao Chunxiao | 2020-05-26 | 93% | 2021-05-26 |  | 2019-07-05 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2021-07-05 |  |  |  | yes
DCG | Karrie | KARRIE INTERNATIONAL HOLDINGS LTD: Dongguan Feng Gang Castfast Metal & Plastics Co., Ltd. | Dongguan | ME | Clare Chen | 2020-07-05 | 88.4% | 2021-07-05 |  | 2019-11-15 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-11-15 | The proposed VAP audit start date is between 12/14/2020 and 12/18/2020. | N/A |  | Yes |  | Silver
DCG | Artesyn | Artesyn Technologies Asia-Pacific LTD - Zhong Shan | Zhongshan | Power Supply | Aiwa Zhang | 2020-04-30 | 93.5% | 2021-04-30 |  | 2019-08-13 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-08-13 |  |  |  | Yes |  | Silver
DCG | Seagate Cloud Systems | ODM: Foxconn-CESBG-Tianjin | Tianjin | Storage | Rachel Yeh1(<ryeh1@lenovo.com>) | 2020-05-15 | 92.9% | 2021-05-15 |  | 2020-08-14 | VAP | yes | N/A | 0 |  | 0 | 0 | 2022-08-14 |  |  |  | Yes |  | should be Silver
DCG | Cavium(Marvell) | ODM: Venture Electronics Services (M) Sdn. Bhd. | Malaysia | NIC/RAID | Frank Mah | 2020-08-07 | 90.1% | 2021-08-07 |  | 2019-05-29 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2020-10-21 | 2019/10: Supplier had Microsoft SEA audit in Sep |  |  | Yes
DCG | Mellanox | ODM: Flextronics Israel LTD | Israel | NIC/RAID | Edison Hsiao | 2020-10-08 | 85.2% | 2021-10-08 |  | 2016-08-23 | Non-VAP | yes | N/A | 0 |  | 0 | 0 | 2020-10-06 | on-hold due to COVID-19(20201029);20191128-Flex sent Flex Pledge Certification, which is valid to 2020 Sep 6th. And they confirm they will have a new audit. scheduled for July 2020 and will then have an updated report on Oct 2020 to provide. //Flex Israel has 3 year audit cycle |  |  | Yes
DCG | Samsung | Samsung Electronics (Suzhou) Semiconductor | Suzhou | Memory | Cody Quick <cquick@lenovo.com> | 2020-06-02 | 95.1% | 2021-06-02 |  | 2020-08-14 | VAP | no | 2020-10-25 | 0 |  | 0 | 0 | 2022-08-14 | Full score |  |  | Yes |  | Silver
DCG | Micron | Micron Technology, Inc.: Micron Semiconductor Asia Pte. Ltd. | Singapore | Memory | Cody Quick <cquick@lenovo.com> | 2020-04-27 | 91.6% | 2021-04-27 |  | 2020-02-14 | VAP | no need | N/A | 0 |  | 0 | 0 | 2022-02-14 | Full score |  |  | Yes |  | Platinum
DCG | SK Hynix | SK Hynix Semiconductor INC | Wuxi | Memory | Cody Quick <cquick@lenovo.com> | 2020-07-12 | 95.8% | 2021-07-12 |  | 2020-10-22 | VAP | yes | N/A | 1 | A4.4b | 0 | 0 | 2022-10-22 | 20200826: Will have an audit in Oct / 2019 Audit E12 finding is closed based on acknowledgement. | N/A |  | Yes |  | should be Silver
DCG | Flextronics | Flextronics Technology (Penang) Sdn. Bhd | Malaysia | Networking | Frank Mah | 2020-06-23 | 92.4% | 2021-06-23 |  | 2018-12-19 | VAP | yes | N/A | 0 |  | 0 | 0 | 2020-12-19 | Based on Kari's email, reschedule Feb 8-10. 2021 |  |  | Yes |  | Silver
DCG | Pegatron | Pegatron Taoyuan Plant | Taoyuan | ECAT | Carol Chu (chucarol@lenovo.com) | 2020-05-25 | 91.9% | 2021-05-25 |  | 2019-01-14 | VAP | yes | N/A | 0 |  | 0 | 0 | N/A | 20200826-1. As Rock ODM no longer Pegatron, but LCFC; 2. Lenovo biz with Pegatron is supposed to be EOL in March 2021. |  |  | Yes | yes
DCG | Inventec | Inventec (Pudong) Technology Corporation | Pudong | ECAT | Catherine Ge1 Zhou <zhouge1@lenovo.com> | 2020-03-30 | 94.5% | 2021-03-30 |  | 2019-11-29 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021-11-29 | 20191211: A3.1 comply with 60 hours requirement, while A3.2 major//A3.1 closed in Sep 2019 |  |  | No | yes | Silver
DCG | Flex | Flextronics International Kft | Hungary DCG | DCG ODM | Marion Hynd | 2020-06-08 | 90.3% | 2021-06-08 |  | 2018-11-22 | VAP | yes | N/A | 0 |  | 0 | 0 | 2021/6/31 | Virtual Audit from RBA, waiting for the exact date from Kari and Marion/postponement due to COVID-19, confirmed by David through email / based on David email, postpone to 2021/6 (documentation) |  |  | Yes | yes
DCG | HGST | HGST (Thailand) Ltd. | Thailand | HDD | Nicki Dillinger | 2020-03-31 | 94.5% | 2021-03-31 |  | 2019-10-03 | VAP | no need | N/A | 0 |  | 0 | 0 | 2021-10-03 | Full score | N/A |  | Yes |  | Platinum
DCG | CIS | Asia Pacific CIS (Wuxi)Co. Ltd | Wuxi | Slide rail, CMA | Mina Liu | 2020-05-21 | 92.8% | 2021-05-21 |  | 2020-09-28 | VAP | yes | N/A | 0 |  | 0 | 0 | 2022-09-28 | A3.1&A3.2 closed in 2020 June// Based on RBA decipline, A3.1 in closure Audit reach minor level (2020)// reach priority level at Sep 2020, back to major at Oct. | 2020-12-08 | 2021-03-08 | No |  | should be Silver
Formulas:
Audit Target Date = EDATE([Last Audit],24)
Audit Target Date = EDATE([Last Audit], 24)
WH Report Due Date = EDATE([WH Report Request Date], 3)
WH Report Due Date = EDATE([WH Report Request Date],3)
Note on N1: 作者: CAP:Corrective Action Plan
Note on V2: 作者: track under Global MI
Note on C5: 作者: 交易主体：20190706切换为南昌勤胜电子科技有限公司；
Note on T5: 作者: Revised according to Huaqin'email,20201216.
Note on W5: 作者: offer data to Aug 18, after that day, no Lenovo products production
Note on X5: 作者: 20190626,May data major, but April March A3.1 priority, A3.2 MAJOR 20190325, A3.1 priority, A3.2 major; 20181105, A3.1 on priority level;A3.2 compliance
Note on Y5: 作者: 20200811.Lenovo request to add Huaqin to TCO list
Note on W6: 作者: reached minor in Apirl 2020, but rised to priority in July. Reached in major in Sep 2020
Note on X10: 作者: A3.1 Keep on major level for 7 months since July 2019
Note on H11: 作者: Corp level
Note on X12: 作者: A3.1 major
Note on C13: 作者: Add in 201907
Note on C15: 作者: Add in 201907
Note on W15: 作者: ask for Nov-Jan data.first tracking after compliance.
Note on B17: 作者: Desktop/ workstation
Note on C18: 作者: ECS (Elitegroup Computer Systems)
Note on D19: 作者: 中文名恩斯迈电子（深圳）有限公司
Note on V20: 作者: ask July to Sep data, in no priority then stop tracking
Note on W20: 作者: 10-12月数据
Note on C21: 作者: 14001 OK
Note on V24: 作者: ask for Dec to Feb data
Note on C28: 作者: 18001 ok
Note on C35: 作者: Unionmem is a subsidiary of Ramaxel
Note on B38: 作者: Hard Disk Drive/ Optical Disk Drive
Note on D38: 作者: Previous Name-Toshiba America Electronic Components, SAE Magnetics (H.K.) Ltd.
Note on N39: 作者: full score
Note on D40: 作者: MY factory will be closed in April 2019. Production transfer to TH
Note on E40: 作者: Future track:Western Digital(Thailand) Company Limited
Note on Q42: 作者: Submit E12 rest of evidence 2021/2/5.
Note on W43: 作者: From Feb, we only track ODM and non-ODM but with priority finding
Note on D44: 作者: Previous name: Nanchang O-film Bio-identification Technology Co., Ltd.
Note on Q44: 作者: B2.1b 1）进行中，2021/6/31完成；2）完成
Note on C48: 作者: Added in June, 2018
Note on W49: 作者: ask for data from Nov.to Jan.
Note on C50: Offer products that are TCO certified .. a major Corp. Soc. Resp. standard in European and India.
Note on C51: Offer products that are TCO certified .. a major Corp. Soc. Resp. standard in European and India.
Note on C56: 作者: belong to BOE group
Note on S59: 作者: A3.1 9月达到minor.
Note on V59: 作者: 自2020年起，WH数据转为Global MI监控
Note on C62: 作者: Full name NVIDIA Corporation Singapore Pte. Ltd.
Note on H62: 作者: It's TSMC SAQ.
Note on C63: 作者: Cybertan is a subsidary within the Foxconn group.
Note on E63: 作者: Address: No1, East Zone1st Road, XiYong Town, ShaPingBa District, Chongqing City, China
Note on N66: 作者: CAP is in EICC ON
Note on H67: 作者: It's TSMC SAQ.
Note on H68: 作者: It's TSMC SAQ.
Note on C70: 作者: 交易主体SHENZHEN TINNO Mobile Technology Corp. Ltd.
Note on D70: 作者: Need to check with Daniel whether use this facility at end of Mar.2021.
Note on P70: 作者: Business transition to built-in Wuhan plant. Not review the CAP.
Note on Z70: 作者: VAP recognition received.
Note on I71: 作者: 本次coporate level,下次建议facility level
Note on T71: Zhexian ZX1 Xue:first time conduct VAP.
Note on T74: 作者: Check the remark.
Note on T75: 作者: on hold due to Covid-19!
Note on D77: 作者: 宁波舜宇光电信息有限公司
Note on W77: 作者: first tracking: ask for 11 12 1 WH data. Reach minor level at Aug 2020.
Note on N78: 作者: A3.1 is beneath major level of RBA 60 hours requirements
Note on D79: Rita Yang: Add to program on Dec 21, 2017
Note on O79: 作者: send a CAP, but mismatch with the audit report
Note on S79: 作者: A3.1, A3.2 reach major since Sep.
Note on W79: 作者: asking data from 11 to 1.
Note on F80: 作者: 欧菲光电专门生产Imager
Note on Q80: 作者: A4.4b can be finished no later than end of Dec 2020.
Note on D81: 作者: Previous name: Nanchang O-film Bio-identification Technology Co., Ltd.
Note on X85: 作者: Ask for Oct to Dec. Final.
Note on H90: 作者: Corp level
Note on C91: 作者: Toray International(China)Co. Ltd.
Note on C92: 作者: Toray International(China)Co. Ltd.
Note on C94: 作者: Acquisited by Advanced energy.
Note on C95: 作者: Dothill are acquired by Seagate
Note on C96: 作者: Cavium acquired by Marvell in July 2018
Note on H96: 作者: Venture SAQ
Note on N96: 作者: due date end of Jan 2018
Note on T96: 作者: on hold due to Covid-19!
Note on H97: 作者: Mellanox SAQ
Note on M97: 作者: Audit type: Flex Pledge
Note on T97: 作者: on hold due to Covid-19!
Note on N99: 作者: Full score
Note on T101: 作者: on hold due to Covid-19!
Note on D102: 作者: Suzhou facility closed in March 2019
Note on C103: 作者: IEC
Note on V103: 作者: Monitor by Global MI
Note on C104: 作者: Share the same information with PCG
Note on C105: 作者: WD group
Note on W106: 作者: 2020 Dec to 2021 Feb

## Sheet1
2016 2half | close |  | new | [5 empty] | VAP@eiccoalition.org
priority | 1 | Bitland | 3 | Shimane Sanyo
| 5 | A-max (Arkon) | 2 | Coslight
| 1 | Goodway | 2 | Innolux
| 1 | A-max (Arkon) | 1 | Wistron ZS
| 1 | PLDS | 1 | Toshiba
| 2 | Coslight | 2 | FSP
major | 1 | lighton | 5 | Simplo
| 2 | Bitland | 2 | Flex MY |  | PLDS
| 3 | Luxshare | 1 | Multek
| 1 | Compal | 6 | Compeq
| 24 | A-max (Arkon) | 5 | Chicony
| 8 | Goodway | 5 | Honhai Foxconn
| 3 | Wistron ZS | 2 | Inventec
| 4 | Simplo | 11 | Shimane Sanyo
| 4 | USI | 1 | Skyworks
| 1 | Wistron KS | 15 | Coslight |  |  |  |  | close | currently open
| 7 | A-max (Arkon) | 3 | HLDS |  |  |  | Sunrex/JME | 11 | 0
| 1 | Goodway | 4 | Innolux
| 1 | Simplo | 1 | AUO
| 2 | Lite on | 11 | Cybertan (Foxconn)
| 12 | A-max (Arkon) | 3 | Wistron ZS
| 1 | A-max (Arkon) | 5 | Toshiba | [6 empty] | 2016 first half year data
| 1 | Bitland | 2 | Dothill (Foxconn)
| 3 | Honhai Foxconn | 9 | Accuride
| 6 | PLDS | 2 | SCUD | report sent on 2017
| 5 | Compeq | 6 | FSP
| 1 | Multek
| 2 | Flex MY
| 1 | Skyworks
| 13 | Coslight
| 1 | Goodway
| 3 | Toshiba
| 1 | Lite on Changzhou
| 3 | Innolux
| 2 | Coslight
| 2 | Wistron ZS
| 1 | A-Max (Arkon)
| 2 | Shimane Sanyo
| 2 | Dothill (Foxconn)
| 4 | FSP
2017/18 first half
| close |  | new
priority | 1 | Toshiba | 1 | Ramaxel
| 1 | Shimane Sanyo | 1 | Brother
|  |  | 1 | Lite-on
|  |  | 1 | Eaton
|  |  | 0 | WD
|  |  | 1 | LGC
major | 2 | Shimane Sanyo | 11 | Brocade (Foxconn Nanning) | report sent on 2017
| 1 | Compeq | 10 | Envision | report sent on 2017
| 1 | Chicony | 3 | SK hynix Inc.
| 7 | Cybertan | 2 | Artesyn | report sent on 2017
| 1 | SCUD | 5 | k-tronics | report sent on 2017
| 2 | Brocade (Foxconn Nanning) | 1 | Karrie | report sent on 2017
| 2 | Honhai | 9 | Brother
| 1 | Artesyn | 16 | Ramaxel
| 9 | Envision | 2 | Sandisk
| 3 | K-tronics | 2 | Lite-on
| 1 | Wistron ZS | 4 | Eaton
| 1 | HLDS | 0 | WD
| 5 | Accuride | 2 | LGC | report found on 2017
| 2 | Toshiba | 5 | Sunwoda
| 3 | Huntkey | 4 | Huntkey | report sent on 2017
| 5 | Brocade (Foxconn Nanning) | 7 | Luxshare | report sent on 2017
| 1 | FSP
| 1 | Pegatron
| 1 | Lite-on Changzhou
| 1 | Envision
| 1 | Shimane Sanyo
| 3 | SK hynix Inc.
| 1 | Lite-on Changzhou
| 3 | Shimane Sanyo
| 1 | LGC
2017/18 Second half
| close |  | new
priority | 1 | Shimane Sanyo | 3 | LGDNJ
| 2 | LGDNJ | 2 | Quanta |  |  |  | 2017 first half
| 1 | Wistron ZS | 3 | LGDNJ
| 1 | Ten Pao | 1 | Coslight
| 2 | 3nod | 1 | AVC Shenzhen
| 1 | 3nod | 2 | Innolux
| 1 | Ten Pao | 2 | Ten Pao
| 1 | Sierra Wireless | 3 | Longcheer
|  |  | 2 | Salom
|  |  | 1 | Sierra Wireless
|  |  | 3 | 3nod
|  |  | 3 | LGC
|  |  | 1 | Acbel
|  |  | 2 | AVC Dongguan
|  |  | 3 | Sharetronic
major | 1 | FSP | 11 | LGDNJ
| 3 | Luxshare | 7 | AUO
| 3 | Sunwoda | 8 | Quanta
| 1 | Artesyn | 1 | TPV Fujian
| 10 | LGDNJ | 7 | Delta
| 1 | TPV Fujian | 9 | K-tronics Suzhou
| 2 | Eaton | 1 | WD MY
| 2 | Shimane Sanyo | 8 | O-film
| 3 | Accuride | 1 | Wistron ZS
| 1 | Jiatian | 2 | Jiatian
| 5 | O-film | 1 | Toshiba
| 7 | K-tronics | 2 | Simplo
| 3 | L&T | 6 | LGDNJ
| 8 | AVC Shenzhen | 2 | BOE
| 1 | FSP | 7 | Coslight
| 8 | Ramaxel | 3 | L&T
| 2 | HLDS | 12 | AVC Shenzhen
| 4 | Delta | 4 | Pegatron
| 2 | AVC Shenzhen | 4 | PLDS
| 1 | O-film | 2 | ATL
| 3 | PLDS | 2 | Innolux
| 3 | Pegatron | 36 | Ten Pao
| 1 | O-film | 2 | Multek
| 3 | Quanta | 6 | Longcheer
| 1 | K-tronics | 4 | Salom
| 2 | Shimane Sanyo | 21 | Huaqin
| 1 | K-tronics | 1 | SK hynix Inc.
| 20 | Ten Pao | 11 | Sierra Wireless(Jabil Vietnam)
| 1 | Innolux | 4 | Huntkey SZ
| 1 | Accuride | 10 | 3NOD
| 1 | SK hynix Inc. | 3 | USI
| 4 | 3NOD | 13 | Inventec
| 3 | Longcheer | 8 | ECS
| 1 | Compal | 1 | Dothill
| 4 | 3NOD | 11 | LGC
| 3 | Luxshare | 4 | Molex
| 2 | ECS | 3 | Acbel
| 1 | Wistron ZS | 5 | AVC Dongguan
| 1 | ECS | 50 | Sharetronic
| 1 | Huntkey
| 1 | Jiatian
| 1 | Lite-on Changzhou
| 1 | Delta
| 1 | Toshiba
| 1 | PLDS
| 1 | SCUD
| 1 | AUO
| 1 | Cybertan
| 1 | Multek
| 1 | MSI
| 6 | Inventec
| 4 | Huntkey SZ
| 1 | Chicony
| 1 | Sanyo
| 1 | 3Nod
| 1 | Ten Pao
| 2 | GTK
| 2 | ECS
| 10 | Sierra Wireless(Jabil Vietnam)
2018/19 1st half
CY 2018/19 1st half | close |  | new
Priority | 1 | Sanyo | 1 | Qlogic
| 1 | Salom | 1 | Coslight
| 1 | Acbel
Major | 1 | Luxshare | 5 | MSI
| 3 | Salom | 3 | Sandisk
| 3 | MSI | 2 | Coslight
| 2 | Multek | 4 | Qlogic
| 2 | Acbel | 7 | BOE Hefei
| 2 | ATL | 3 | HGST Thailand
| 4 | BOE Hefei | 7 | HLDS
| 1 | Delta
| 5 | Huntkey SZ
| 1 | Karrie
CY 2018/19 1st half | [8 empty] | 2018 1st half
| close |  | new
Priority | 1 | Salom | 6 | Bitland Hefei
| 1 | Ramaxel | 4 | LGD
| 2 | Quanta | 1 | LGC
| 2 | Longcheer | 3 | Wistron KS
| 2 | Bitland Hefei | 4 | Bitland SZ
| 1 | Sanyo (换工厂,老工厂不再生产联想产品) | 1 | Simplo
| 4 | Bitland Hefei | 3 | AAC
| 1 | Longcheer | 1 | Luxshare
| 2 | Bitland SZ | 2 | Qorvo
| 1 | Bitland Hefei | 3 | Ramaxel
major | 1 | Cybertan | 6 | Laibao
| 3 | Inventec | 4 | Foxconn Wuhan
| 2 | Cybertan | 9 | Bitland Hefei
| 1 | MSI | 3 | Inventec
| 1 | Salom | 20 | LGD
| 2 | Ramaxel | 6 | LGC
| 1 | Ramaxel | 1 | Acbel
| 1 | 3Nod | 10 | Wistron KS
| 4 | Inventec | 9 | Bitland SZ
| 1 | Quanta | 11 | Simplo
| 2 | AVC Dongguan | 12 | Taisol
| 3 | HGST Thailand | 2 | Compeq
| 3 | Ramaxel | 13 | AAC
| 1 | Acbel | 6 | ECS
| 2 | Hefei BOE | 7 | Huaqin
| 1 | Wistron KS | 3 | Luxshare
| 1 | Simplo Chongqing | 4 | AUO
| 1 | Honhai | 2 | K-tronics
| 2 | Bitland Hefei | 1 | Seagate
| 1 | ECS | 5 | Qorvo
| 2 | ECS (no longer finding in 2018 audit report)
| 1 | Longcheer
| 3 | Bitland Shenzhen
| 44 | Sharetronic
| 1 | Wistron ZS Linhai
| 5 | Simplo Chongqing
| 4 | AUO
| 3 | SANDISK(WD)
| 1 | Simplo Chongqing
CY 2018/19 2nd half | [8 empty] | 2018 2nd half
| close |  | new
Priority | 2 | AVC Dongguan | 2 | Innolux
| 2 | Innolux | 1 | Coslight
| 2 | Qorvo | 3 | FSP
| 1 | Bitland SZ | 4 | PLDS
| 1 | Wistron KS | 2 | Panasonic
| 1 | Coslight | 1 | Tianma | 2017 audit
| 1 | FSP
| 1 | Qlogic
| 1 | FSP
| 1 | Bitland Hefei
| 3 | AAC
| 1 | Coslight
| 4 | PLDS
CY 2019/20 1st half
| close |  | new
Priority | 1 | BYD | 2 | Innolux
| 2 | Foxconn Tianjin (ODM of Dothill) | 2 | BYD
| 2 | Innolux | 5 | Sunrex/JME
|  |  | 2 | Foxconn Tianjin (ODM of Dothill)
|  |  | 1 | Laibao |  | a1.1
|  |  | 1 | Lite-On Changzhou |  | a1.1 |  |  | Tower | Supplier | Facility name | Facility Location | Commodity | GCM | SAQ Date (SAQ=Self Assesement Questonnaire) | SAQ Score | SAQ Target Date | SAQ Remarks | Last Audit | Audit Type
|  |  | 1 | AUO |  | A2.3B |  |  | NB ODM | Wistron | WISTRON INFOCOMM (KUNSHAN) CO., LTD | Kunshan | NB ODM | Tavia Yu | 2018-07-06 | 92% | 2019-07-06 |  | 2018-04-09 | Non-VAP
|  |  | 3 | Ramaxel |  | a1.1 |  |  | NB ODM | Compal | Compal Information Technology(KUNSHAN) CO., LTD | Kunshan | NB ODM | Jessie Yue4 Li | 2018-03-31 | 92% | 2019-03-31 |  | 2018-04-27 | Non-VAP
|  |  | 1 | Molex |  |  |  |  | NB ODM | Bitland | Hefei Bitland Information Technology Co., LTD | Hefei | PCG ODM | Ben Li | 2018-12-03 | 93.3% | 2019-12-03 |  | 2018-01-30 | VAP
[9 empty] | Power | LGC | LG Chem: LG Chem(Nanjing)I & E Materials Co., Ltd | Nanjing | NB Battery | Jukka Song | 2018-08-03 | 90% | 2019-08-03 |  | 2018-03-02 | VAP
CY 2019/20 2nd half | [8 empty] | Power | Simplo | Simplo Technology (ChongQing) INC. | Chongqing | NB Battery | Jukka Song | 2018-03-09 | 92.4% | 2019-03-09 |  | 2018-06-26 | VAP
| close |  | new | [5 empty] | DT/WS | FSP | FSP TECHNOLOGY INC.: Shenzhen Huili-Fuyong Electronics Co.,Ltd//深圳輝力電子有限公司 | Shenzhen | DT PSU | Annie Yang | 2018-03-29 | 92.3% | 2019-03-29 |  | 2018-06-14 | Non-VAP
| 5 | Sunrex/JME (A3.1&A3.2) | 3 | AVC Shenzhen |  | A3.1, A3.2, B2.4 |  |  | ACC/PPS | Goodway | Goodway Electronic (Kunshan) Co., Ltd. | Kunshan | USB Docking | William Guo | 2018-05-30 | 93.5% | 2019-05-30 |  | 2018-05-29 | Non-VAP
| 1 | AUO (A2.3b) | 2 | Shanghai AVIC Optoelectronics co.,LTD |  | A1.1, A3.1 |  |  | HDD/ODD | WD | Western Digital (M) sdn.bhd. | Malaysia | HDD | Danny Zhao | 2018-03-20 | 90.1% | 2019-03-20 |  | 2018-05-25 | VAP
| 1 | Laibao (A1.1) | 3 | Q-tech |  | A1.1, A3.1, B2.4 |  |  | Display | Innolux | Foxconn-Innolux Corporation: Innolux Corporation-Ningbo | Ningbo | NB LCD | Bruce Li / Zhu Qing | 2018-03-07 | 95.3% | 2019-03-07 |  | 2018-04-16 | VAP
VAP Closure | 1 | Lite-On Changzhou | 1 | Hannstar |  | a1.1 |  |  | Display | O-FILM | Nanchang O-film Optical Display Technology Co., Ltd. | Nanchang | Touch Panel | Kenny Xiao / Brian Wang | 2018-04-21 | 95.3% | 2019-04-21 |  | 2018-05-28 | VAP
| 1 | Hannstar | 1 | Acbel |  | A3.1
| 1 | AVC Shenzhen B2.4 | 2 | AVC Shenzhen |  | A3.1, A3.2
| 2 | Q-tech
| 1 | Shanghai AVIC Optoelectronics co.,LTD
| 1 | Ramaxel
CY 20/21 1st half
| close |  | new
| 1 | Sandisk MY | 2 | Sandisk MY |  | A1.1, E12.2b
| 1 | Acbel | 4 | Longcheer |  | A1.1, A2.3b, A2.4b, B2.2
| 1 | LGC | 1 | Acbel |  | A3.1
| 1 | HLDS | 1 | LGC |  | B2.4
| 2 | Sandisk MY | 1 | HLDS |  | E12.2b
| 1 | Goodway | 1 | Goodway |  | E12.2b
| 1 | Coslight | 3 | FSP |  | A1.1, A3.1, A3.2
|  |  | 1 | Coslight |  | B2.4
CY 20/21 1st half
| close |  | new
| 4 | Longcheer | 1 | BYD |  | A3.2
| 1 | Delta | 2 | CIS |  | A3.1, A3.2
| 1 | Chenyang | 1 | Delta | 2019 audit | A1.1 | prohibited recruitment and hiring fees that are paid and not reimbursed within 90 days, or as soon as practicable upon discovery.
| 2 | CIS | 1 | Chenyang |  | A3.2
| 3 | DJN | 2 | Quanta |  | A3.1, A3.2
|  |  | 3 | Sunny |  | A3.1, A3.2, B2.2
|  |  | 1 | Sandisk MY |  | A1.1
|  |  | 3 | DJN | 2020 audit | B2.4,E12.1b,E12.2b
|  |  | 1 | Innolux |  | A3.1
Note on P253: 作者: Corp. level

## CAP evidence
Supplier | Full name | Content | Type | Evidence | Request Date | Reply Date
Taisol | Dong Guan TaiSol Electronics Co,;Ltd | evidence of 5 closed items | major | YES | 2016-04-18 | 2016-04-29
Lite-On | LITE-ON Technology (ChangZhou) CO.,Ltd.,the Power Plant | 建立政策程序：禁止安排未成年工加班 | major | NA | 2016-04-20 | NA | Lite on sent a new audit report
Luxshare | Luxshare Precision Industry Co., Ltd.: Dongguan Xuntao Electronic Co.,Ltd. | EHS Engineer check the item every month, and let them to correct it if there have any problem | major | YES | 2016-04-27 | 2016-04-29
Bitland | Shenzhen Bitland Information Technology Co., Ltd | 人力资源部对工厂的加班进行定期抽查，发现有超时情况及时发出预警，及时安排员工休息。 | priority | YES | 2016-08-01 | 2016-08-08
Luxshare | Luxshare Precision Industry Co., Ltd.: Dongguan Xuntao Electronic Co.,Ltd. | HR keep monitoring the worktime,if there have any nonconforming, ask the relevant dept. to feedback the reason and effectively correct it immediately。 | priority | YES | 2016-08-17 | 2016-08-25
Lite-On | LITE-ON Technology (ChangZhou) CO.,Ltd.,the Power Plant | 1. Ensured one day off per seven days period to minor level.2.To buy social insurance for all employees who are working for lenovo. | major | YES | 2016-09-22 | 2016-09-23
Amax | Arkon Electronics (HuiZhou) Co. Limited | 已要求派遣公司提供复印件给到我司 | priority | YES | 2016-09-26 | 2016-09-28
Amax | Arkon Electronics (HuiZhou) Co. Limited | 教育员工，公司为所有员工购买社保 | priority | YES | 2016-09-26 | 2016-09-28
Compeq | Compeq Manufacturing Co.,Ltd. | evidence of midifying SOP | major | YES | 2016-11-02 | 2016-11-03
Coslight | zhu hai coslight battery co.,ltd | 1.对《环境管理手册》进行修订，增加温室气体排放的识别、排放核算、管理流程、管理责任等内容；建立温室气体排放管控清单，对温室气体进行识别并核算其排放量。 | major | YES | 2016-11-21 | 2016-11-21
Coslight | zhu hai coslight battery co.,ltd | Working Hours/Time Off findings | priority | YES | 2016-12-21 | 2016-12-23
SK Hynix | SK Hynix Semiconductor INC | Evidence of all major items | major | YES | 2017-07-04 | 2017-11-13
Sunwoda | Sunwoda Electronic Co., Ltd. | Conduct identification and evaluation of Ergonomics for the related departments timely | major | YES | 2017-07-10 | 2017-07-12
Sanyo | UMC Electronics Dongguan Works | 人事部每10日发送各部门加班明细给部门长，以便部门进行监控。 |  | YES | 2017-07-05 | 2017-08-19
AVC | Asia Vital Component (Shenzhen) Co., Ltd. | B3.1b, C2.1, C4.1b | major | YES | 2017-09-22 | 2017-09-30
Pegatron | MAINTEK Computer (Suzhou) Co., Ltd. | evidence of E12.2 | major | YES | 2017-10-24 | 2017-10-27
SK Hynix |  | evidence of C3.1b | major | YES | 2017-11-27 | 2017-12-06
Inventec |  | evidence of all 6 closed items | major | YES | 2017-12-18 | 2017-12-20
Acbel |  | evidence of B2.4 | priority | YES | 2018-01-22 | 2018-01-22
Sharetronic |  | evidence of B2.4& B6.2b | priority | YES | 2018-03-22 | 2018-08-14
Wistron KS |  | evidence of A1.2& C3.1b | major | YES | 2018-07-16 | 2018-07-19
FSP |  | evidence of A1.1 | priority | No | 2018-08-01
Sharetronic |  | evidence of E2.2 and E4.1 | major | YES | 2018-08-06 | 2018-08-14
USI |  | evidence of B2.1 | major | YES | 2018-10-09 | 2018-10-10
BOE Beijing |  | evidence of A3.1 | major | No | 2018-12-03
SCUD |  | evidence of A4.4 | major | No | 2019-04-03
Toray Shanghai |  | evidence of A2.4 and B3.1 | major | YES | 2019-06-20 | 2019-06-25
K-tronics |  | evidence of B7.3b E3.1 | major | No | 2019-07-31
PLDS |  | evidence of A2.4b | major | No | 2019-09-24
Tianma |  | evidence of B5.1b | major | No | 2019-11-11
Goodway |  | evidence of E12.2 | priority | YES | 2020-06-10 | 2020-06-22
Sandisk |  | evidence of B1.3b and B4.2 | major | YES | 2020-06-21 | 2020-06-22
FSP |  | evidence of A1.1 and A4.1 | priority&major | YES | 2020-06-30 | 2020-07-10
AVC |  | evidence of C3.1b | major | YES | 2020-07-14 | 2020-07-16
IVE |  | evidence of A4.4b and -B7.1b | major | No | 2020-09-03
|  | AAC Supplier | Sinolong Technology (Shanghai) Co., Ltd. | 527931049
Note on G34: 作者: A1.1 not closed

## Change history
Group | Supplier | Delete/Add Reason | Date | Change
PCG | TSST | will move out of our business in new FY |  | delete
| IVO | IVO spending in this FY2016 will be reduced a lot. Without IVE, LCD may reach 95%. Will reassess within 6 months | 2016-06-07 | delete
| Primax | MBG got bigger spend |  | delete
| Flex Hungary | Monika Mosna confirm Flex FY1516 Total Spend (we run Buy/Sell with them) was $379M | 2016-07-07 | add
| TPV BJ | TPV produced products that are TCO certified .. a major Corp. Soc. Resp. standard in European and India. |  | add
| Hon Hai | Foxconn been highlight for labor violation in Apple supply chain, and HH has big spend with Lenovo too | 2016-09-27 | add
| TNI | No business between Lenovo and TNI from Sep. 2016. | 2016-08-18 | delete
| 3Nod/Yifang/AVC Dongguan | We are getting more and more focus from customers on our Lenovo and Supplier sites who build completed product. Most every negative sustainability event has been with suppliers who build boxes (vs. commodities) |  | add
| HLDS MY | no Lenovo ODD was produced at HLDS Malaysia now | 2016-11-23 | delete
| HLDS HuiZhou | HLDS Huizhou is the only MFG for Lenovo ODD production. | 2016-11-23 | add
| L&T | TCO certification |  | add
| K-TRONICS | TCO certification |  | add
| Korrun | We will end the business with them in early 2017. | 2016-12-13 | delete
| A-Max (Arkon) | GCM confirm the annual spending with A-Max is lower than $1M. | 2017-03-01 | delete
| Sharetronic | A-max annual spending is only $0.2M last year, while Sharetronic get big spend in Annie Tower. | 2017-03-07 | add
| Qorvo | RF Micro Devices (Beijing) Co., Ltd removed from quovo.Qorvo is the new company merged by RFMD and Triquint, can delete RFMD. | 2017-03-14 | delete
| Yassy | Lenovo won’t have no new projects planned with Yassy in 2017 | 2017-03-23 | delete
| Brother | Brother removed for Printer BU is a spin-off company after April 2017 | 2017-04-12 | delete
| Yifang | We are closing the business with Yifang. Project is going to EOL phase, no new business. | 2017-06-01 | delete
| Samsung | Samsung HQ refuse to offer Dram facility, but Samsung is EICC member and we are tracking Samsung Suzhou plant | 2017-08-17 | delete
| Lite On | ODM/CM | 2018-02-21 | add
| Lite On | Removed due to Liteon’s project have been EOL, and no new biz in the coming half year | 2018-12-28 | delete
| 3Nod Beihai | All PC projects will be planned to EOL this calendar year end in Beihai factory. Now no new business to 3Nod. | 2019-07-01 | delete
| Celxpert | Spending rank among 95% coverage | 2019-07-19 | add
| Chen Yang | GCM inform to add | 2019-07-19 | add
| Chicony Suzhou | GCM inform to add | 2019-07-19 | add
| Sierra Wireless | will phase out by end of 2020. Spending already very low. | 2019-11-25 | delete
| TINNO |  | 2019-12-05 | add
| Unionmem |  | 2019-12-05 | add
| Huaqin | Move from ACC to NB ODM since Huaqin facility only produce NB for Lenovo | 2020-04-13 | move to NB ODM
| Fibocom | Big spending supplier, rank among 95% spend coverage | 2020-06-16 | add
| Bitland Hefei | Stop produing for Lenovo for Uyghur labor issue | 2020-07-30 | delete
MBG | CCI | CCI is Compal Electronics, Inc., it is tablet supplier.The tablet business has been transferred from MBG to PCG. |  | delete
| TDI | the supplier will phase out in MBG this year |  | delete
| KHV | the supplier will phase out in MBG this year |  | delete
| Foxconn | the supplier will phase out in MBG this year |  | delete
| Sandisk | PCG got bigger spend |  | delete
| O-Film | PCG got bigger spend |  | delete
| LGI | Samsung Electronics Co., Ltd covered by PCG |  | delete
| Hipad | MBG request to remove the supplier since it is out of strategic sourcing scope.No more business when current come to end | 2016-07-13 | delete
| JABIL | MBG request to remove the supplier since it is out of strategic sourcing scope.No more business when current come to end | 2016-07-13 | delete
| Ontim | MBG request to remove the supplier since it is out of strategic sourcing scope.No more business when current come to end |  | delete
| Samsung South Korea | Sharp and Sony are suggested to move out of the candidate list because there will be no cooperation with Sharp and Sony. Spend will focus on PRIMAX, Q-tech, Sunny (on the list) and SEMCO (part of Samsung). |  | add
| S.LSI | It is Samsung, already covered by other commodity | 2017-08-01 | delete
| BYD | BYD shift from MBG EMS to MBG Components | 2017-12-21 | change
| OVT | GCM confirm OVT is Tier 2 supplier | 2018-01-17 | delete
| Fabri Tech | Fabri tech has little share | 2018-01-29 | delete
| Flex | ODM/CM | 2018-02-21 | add
| TDF | ODM/CM | 2018-02-21 | add
| Hipid Shenzhen | Tablet has no business with Hipid | 2018-02-23 | delete
| BYD Shenzhen | Tablet business with BYD Shenzhen will be ended by the 2nd half of CY2018 | 2018-02-23 | delete
| TDK | Lenovo terminated the contract with TDK and there will be no new business | 2018-04-26 | delete |  |  |  | 2017-12-31
| Biel Crystal | Display have no more business with this supplier | 2018-10-29 | delete
| Wind | Wind phased out from current business;There will be no more business with Wind in coming years | 2018-12-28 | delete
| Huaqin | Shift to ACC:No phone project in Huaqin facility now, Moto phone produced in Wuhan plant; | 2019-06-10 | move to ACC
| Longcheer | Shift to ACC: For phone biz, Longcheer facility will phase out in 2019 Q2 | 2019-06-10 | move to ACC
| Multek | MULTEK could be removed from the list as they are phased out. Unnecessary to spend resource to manage that. | 2019-08-21 | delete
| Molex | Molex spending too low, no longer rank 95% coverage | 2019-11-26 | delete
| Ontim | Big spending supplier, ODM too. | 2020-06-16 | add
| Coslight | We have exited the pack business with CosMX some time before. Agree to remove it from the tracking. | 2020-07-29 | delete
| Tinno | TINNO Guang Dong factory were disqualified by our quality team | 2020-12-07 | delete
DCG | Hon Hai | ECAT has exited Hon Hai since last Jun. Meaning we don’t do business w/ Hon Hai now. They only supports product service now. | 2016-06-15 | delete
| EMC | GCM feedback that business will be end in Q2 FY16/17 between Lenovo and EMC | 2016-06-23 | delete
| Broadcom(Avago) | Broadcomo does not support EICC related programs.This position is supported by the executive management. | 2016-08-03 | delete
| Micron/Samsung/Hynix | As DCG was separated from PC, Kelden from Andrew’s team is not the same organization | 2016-10-14 | move from PCG list
| Inventec | Add under DCG, since it is DCG big spend supplier. (TNI removed from PCG list, and TNI not Inventec) | 2016-10-21 | add
| Celestica | GCM confirm Celestica is not getting any new business awards in 2017 | 2017-03-28 | delete
| Eaton | GCM confirm Annual spending of each is about $ 6~7M, and not rank among 95% spending coverage | 2017-07-27 | delete
| Avocent | GCM confirm Annual spending of each is about $ 6~7M, and not rank among 95% spending coverage | 2017-07-27 | delete
| Cavium | Qlogic and Cavium are the same suppliers. We just renamed Qlogic to Cavium. | 2017-08-15 | rename
| Brocade | Acquired by Broadcom, follow Broadcom practice | 2018-01-12 | delete
| Accuride | DCG team confirmed Accuride spending is too low | 2018-08-23 | delete | Mason Mao | 2017-08-16 | 92.6% | 2018-08-16 | 2016-12-05 | VAP | yes | 0 | 2018-12-05 | A3.1 closed on Nov 27. A3.3 closed on 20170816 | 2017-11-24 | Compliance for 2 quarters | Yes
| Artesyn | Lenovo PSU products already moved from Zhongshan factory to Luoding factory | 2019-05-30 | change
| Artesyn | Lenovo PSU products moved from Luoding factory to Zhongshan factory | 2020-04-27 | change
| Bromake | DCG BC focal send request to add the supplier | 2020-05-28 | add
| CIS | DCG BC focal send request to add the supplier | 2020-05-28 | add
| Ingrasys | Spending rank among 95% coverage | 2020-06-15 | add
| Bromake | Spending is small could not rank among 95% coverage | 2020-07-31 | delete
| Ingrasys | AVAC supplier, and under-control by Microsofts | 2020-11-19 | delete
ACC | 3Nod Songgang | Smart Speaker ODM | 2019-07-17 | Add
| Tonly | Smart Device ODM | 2019-03-01 | Add
| Huaqin | Delete from ACC list, move to NB ODM | 2020-04-13 | delete
Note on G73: 作者: Corp. level

## delete list since 2019
2019
Tower | Supplier | Facility name | Facility Location | Commodity | GCM | SAQ Date (SAQ=Self Assesement Questonnaire) | SAQ Score | SAQ Target Date | SAQ Remarks | Last Audit | Audit Type | CAP got or not | Remaining Open item | Audit Target Date | Remaining Open Item Details | Audit/CAP Remark | WH Report Request Date | WH Report Due Date | 60 Hours/week Compliance | ODM/CM/TCO | Send Survey or not
Mobile ODM EMS | Wind | Shanghai Wind Communication Technologies Co.,Ltd. | Shanghai | ODM | Roc Zhao | 2018-07-23 | 85.5% | 2019-07-23 | [5 empty] | 2018-12-31 |  | No Lenovo project in Wind facility now, the audit postponed |  |  |  | yes | no need
DT/WS | Lite On | 光宝网络通讯（东莞）有限公司-旭福厂 | Dongguan | ODM | Kevin Wang | 2018-06-22 | 93.3% | 2019-06-22 | [5 empty] | 2019-06-29 | [5 empty] | yes | no need
NB ODM | 3Nod | GUANGXI SANCHUANG TECHNOLOGY CO.,LTD | Beihai | NB ODM | Wupengb | 2018-06-14 | 91.6% | 2019-06-14 |  | 2017-05-10 | VAP | yes | 0 | 2019-05-10 |  | 继续更新audit report |  |  | Yes | yes | Called
Power | Ten pao | Ten Pao Electronics (Huizhou) Co., Ltd. | Huizhou | Charger | Jack Cui (Cuihl3) | 2019-05-29 | 88.4% | 2020-05-29 |  | 2017-08-09 | VAP | yes | 0 | 2019-08-09 |  |  |  |  | Yes
Mobile Components | MULTEK | MULTEK TECHNOLOGIES LIMITED | Zhuhai | PCB | Guohc1 | 2019-05-17 | 92.2% | 2020-05-17 | when will phase out? | 2017-09-01 | VAP | yes | 0 | 2019/9/31 | The proposed audit start date is between 01/09/2019 and 30/09/2019. | 0 | The proposed audit start date is between 03/09/2018 and 28/09/2018; Closed on Dec 8-Working hours compliant to RBA; |  |  | Yes
Logic/Software | Sierra Wireless | ODM: Jabil Vietnam | Vietnam | Wireless | Yang Chao | 2019-05-31 | 92.3% | 2020-05-31 | will phase out by end of 2020 | 2019-10-15 | VAP | no | 2020-01-08 | 0 |  | 0 | 2021-10-15 |  |  |  | Yes
Mobile Components | Molex | Molex Shanghai | Shanghai | Connector | Johnny Wu (wuyla) | 2019-03-22 | 94.2% | 2020-03-22 |  | 2019-05-17 | VAP | yes | N/A | 0 |  | 0 | 2021-05-17 | If next quarter spending still small, remove this supplier; The proposed audit start date is between 06/01/2020 and 10/01/2020. |  |  | Yes
2020
Mobile Components | AAC | AAC (Vietnam) Technologies Co. Ltd. | Vietnam | Acoustics | Bobby Gu | 2019-10-25 | 95.8% | 2020-10-25 | Next cycle should be SAQ for Vietnam facility | 2018-05-03 | Non-VAP | yes | N/A | 0 |  | 0 | 2020-09-26 | A3.1, A3.2 priority, keep on minor level from April to Oct. |  |  | Yes
Logic/Software | TAIYO | TAIYO YUDEN MOBILE TECHNOLOGY CO.LTD | Japan | RF | Haoling Zhai | 2020-04-23 | 95.5% | 2021-04-23 |  | 2019-03-15 | VAP | no need | N/A | 0 |  | 0 | 2021-03-15 | The proposed audit start date is between 16/03/2020 and 19/03/2020. |  |  | yes |  |  | Gold
Logic/Software | Qorvo | Qorvo Dezhou Co., Ltd. | Dezhou | RF | Haoling Zhai <haoling@motorola.com> | 2020-03-26 | 93.2% | 2021-03-26 |  | 2018-10-18 | VAP | no need | N/A | 0 |  | 0 | 2020-10-18 |  |  |  | Yes |  |  | Gold
ACC/PPS | Sharetronic | sharetronic Date Technology Co.,Ltd.:Dongguan Sharetronic Date Technology Co.,Ltd. | DongGuan | UHD | Annie Liu | 2019-08-09 | 91% | 2020-08-09 |  | 2019-09-25 | VAP | yes | N/A | 0 |  | 0 | 2021-09-25 |  |  |  | Yes
Logic/Software | SPREADTRUM | ODM: Taiwan Semiconductor Mfg. Company | Taiwan | Chipset | Hui Lv | 2020-04-10 | 93.5% | 2021-04-10 |  | 2018-08-16 | Non-VAP | no need | N/A |  |  | 0 | 2020-08-16 |  |  |  | Yes
ACC/PPS | Panasonic | DONGGUAN SHINGI ELECTRONICS CO. LTD 东莞新技电子有限公司 | Dongguan | ME Docking | Vonesa Chen | 2020-04-01 | 90.2% | 2021-04-01 |  | 2018-10-16 | Non-VAP | yes | N/A | 0 |  |  | 0 | 2020-10-16 | A3.1&A3.2 closed in June, 2019 |  |  | Yes
Power | CosMX | zhu hai coslight battery co.,ltd | Zhuhai | Battery | Frank Wang <frankwang@motorola.com> | 2020-03-11 | 94.7% | 2021-03-11 |  | 2020-04-17 | VAP | yes | N/A | 1 | B3.1b |  | 0 | 2022-04-17 | Closure audit in July 2020 |  |  | Yes |  |  | Silver
NB ODM | Bitland | Hefei Bitland Information Technology Co., LTD | Hefei | PCG ODM | Ben Li | 2019-10-11 | 93.7% | 2020-10-11 |  | 2018-12-28 | Non-VAP | yes | N/A | 0 |  |  | 0 | 2020-12-28 | Next cycle audit schedule ——2020.12. RBA Non Vap, 2021.12. RBA Vap ; Next audit target score ——RBA Non Vap 目标160分，至少不低于140分, ——RBA Vap ≥160分 |  |  | Yes | yes
DCG | Bromake | Shenzhen Bromake New Material Co., Ltd., | Shenzhen | Packaging | Clare Chen |  |  | 2020-08-28
DCG（20201119） | Ingrasys | HONG FU JIN PRECISION INDUSTRY (TIANJIN) CO., LTD. | Tianjin | ECAT | Ying Ying7 Song <songying7@lenovo.com> |  |  | 2020-09-17 | 除天津厂以外，还有Ingrasys Technology Inc. Taoyuan 厂，2020年下半年Taoyuan厂spending可能会上升 | [9 empty] | ISO50000/ Cannot provide the SEA with Microsoft(details can be checked with emails 20201117)/Under control of Microsoft(details can be checked with emails 20201119)
Mobile ODM EMS | TINNO | Guangdong Maxon Communication Co., Ltd. | Heyuan | ODM | Roc Zhao, Daniel Li | 2020-05-11 | 91.7% | 2021-05-11 | 广东美晨通讯有限公司目前只有LDA， 江西美晨通讯有限公司目前未生产联想产品 |  |  |  |  | 0 |  |  | 0 | N/A | Audit will be done after Nanchang facility finish the RBA audit |  |  |  | yes
Formulas:
Audit Target Date = EDATE([Last Audit],24)
WH Report Request Date = EDATE([Last Audit],24)
WH Report Due Date = EDATE([Last Audit],24)
Note on M2: 作者: CAP:Corrective Action Plan
Note on B3: 作者: need GCM further confirmation
Note on V3: 作者: covered by Wuhan plant RBA audit
Note on G5: 作者: Corp level
Note on G6: 作者: Corp level SAQ
Note on B8: 作者: Corp SAQ, 20180612, 88.3%
Note on B12: 作者: 工厂不在常州，在越南和深圳. 越南工厂spending更大
Note on G16: 作者: It's TSMC SAQ.
Note on B18: 作者: Old name Coslight
Note on G19: 作者: Corp level
Note on B22: 作者: 交易主体SHENZHEN TINNO Mobile Technology Corp. Ltd.
Note on H22: 作者: 操作不熟悉选了Corp level,