## Mark
Process Notes: | Process completed | Process to be complete | Process delayed | Current week | Holiday
Project Notes: | Update | Delete | Add
Content Notes: | Updates
| Tech Spec released on 1.8 |  |  |  |  | In Process

## Change Log
2014： | http://ecm.lenovo.com/os/ProductGroup/Chief%20Data%20Officer%20Organization/Forms/AllItems.aspx?RootFolder=%2fos%2fProductGroup%2fChief%20Data%20Officer%20Organization%2f2014%20Project%20Timeline%20list&FolderCTID=0x012000F455E9C95A6E6D4892E561863B45A8AC
2016-2017： | http://ecm.lenovo.com/os/ProductGroup/Chief%20Data%20Officer%20Organization/Forms/AllItems.aspx?RootFolder=%2fos%2fProductGroup%2fChief%20Data%20Officer%20Organization%2fPDM%20New%20Projects%20Launch%20Management&FolderCTID=0x012000F455E9C95A6E6D4892E561863B45A8AC#InplviewHash75d2793e-63c1-49ba-8963-dc8966abf2bc=RootFolder%3D%252fos%252fProductGroup%252fChief%2520Data%2520Officer%2520Organization%252fPDM%2520New%2520Projects%2520Launch%2520Management-FolderCTID%3D0x012000F455E9C95A6E6D4892E561863B45A8AC
2018.5之前存档： | http://ecm.lenovo.com/os/ProductGroup/Chief%20Data%20Officer%20Organization/Forms/AllItems.aspx?RootFolder=%2Fos%2FProductGroup%2FChief%20Data%20Officer%20Organization%2FPDM%20Think%20Lenovo%20New%20Projects%20Smart%20Launch%20Dashboard%20%2B%20Timeline&FolderCTID=0x012000F455E9C95A6E6D4892E561863B45A8AC&View=%7B75D2793E%2D63C1%2D49BA%2D8963%2DDC8966ABF2BC%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
2019-05-16 | DT/WS Smart Launch Dashboard release Add CSR Name/BOM Name in PCSD Projects List
2019-05-22 | Add 510-15ICK, 510A-15ICK, T540-15ICK G, A340-24ICK, A340-22ICK
2019-05-28 | Add 510S-07ICB
2019-06-05 | Complete A540-24ICB, A540-24API, 510A-15ARR
2019-06-06 | Add E76x, E76p, E96x, V530S-07ICR, V530-15ICR, M720e
2019-06-12 | Complete A540-27ICB Update new projects workload planning
2019-06-13 | Change project name from 510S-07ICB to 510S-07ICK
2019-06-19 | Update E76x, E76p, E96x workload planning, add some projects details
2019-06-21 | Add annotation and EOW on Workload Planning, complete M90n-1
2019-06-26 | Complete 510-15ICK, 510A-15ICK, T540-15ICK G, EOL E75s, Lenovo V330-15IGM Desktop
2019-07-03 | Complete A340-24ICK, A340-22ICK
2019-07-04 | Add Lenovo V55t-15API PM:houce1 Update V55t-15API workload planning
2019-07-05 | EOL M910z, Lenovo V520-15IKL Desktop Update several products EOL Target
2019-07-08 | Change EOW of M720e to 2019/8/27
2019-07-30 | Update P330 tiny Planner
2019-08-02 | Update F0EACTO1WW, F0EBCTO1WW,90HVCTO1WW,90HXCTO1WW,90HYCTO1WW,M920t,M920s PDM PM
2019-08-05 | EOL P320 tiny
2019-08-08 | Add P330 tiny 30CGCTO1WW(OEM)
2019-08-14 | Update V530S-07ICR & V530-15ICR CTO Status Update M75s-1/V530S-07ICR/M720e CSR Name & BOM Name Update M75q-1 EOW &AD
2019-08-19 | Update M625q, M625q Thin Client, AIO 330-20IGM, T530-28ICB ES, C530-19ICB, V530-15ICB, V530-15ARR, T730-28ICO, V540-24IWL AIO EOL Target
2019-08-27 | Update V530-15ICR CSR Name & BOM Name
2019-08-28 | Add M90a M70a M70t M70s M80t M80s M90t M90s M70q M80q M90q P340 Tiny P340 SFF P340 Tower
2019-09-11 | Add E97, E77, Lenovo V50t-13IMB, Lenovo V50s-07IMB, Lenovo V50a-24IMB, Lenovo V50a-22IMB, Lenovo V30a-24IML, Lenovo V30a-22IML
2019-09-16 | EOL 30C5/30C6/30C9/30C7/30C8/30CA, update P330 SFF & P330 Tower CSR name
2019-10-16 | Update new projects workload planning, add mkt PM, update new products info
2019-10-25 | Add ideacentre AIO 330-20AST from EOL
2019-10-31 | Add new CTO 11AK for M90n-1
2019-11-13 | Add new CTO 10T1 for M920q Add OEM CTO Change V50a AD & EOW
2019-11-18 | Add IdeaCentre AIO 5 27IMB05 and IdeaCentre AIO 5 24IMB05 Change EOW and AD of M90a M70a M70ts M80ts M90ts M70q M80q M90q
2019-11-20 | SML admin change to Runpeng Add P340 Tower & P340 SFF CTO number
2019-11-27 | Add: New Product - M70c Change: Update 510A-15ICB，510A-15ARR，T530-28APR，C530-19ICB，ideacentre 310S-08IGM，ideacentre 720-18ICB，P320 SFF，P330 Tower，P330 SFF，P330 Tower，P340 Tower，P340 SFF，P340 Tiny，P520，P520c，P720，P920， EOL Date Optimized interface Lenovo V520S-08IKL Desktop already EOL
2019-12-04 | Update: Last consumer contact list; 510/510A-15ICK，510S-07ICK，T540-15ICK，Lenovo Legion T530-28APR ES，Lenovo Legion T730-28ICO，Lenovo Legion T530-28ICB ES，Lenovo Legion C730-19ICO，Lenovo Legion C530-19ICB，M920z，M720t，M715q，M715q Thinclient，M720s，M725s，M920q，M820z，M920x，M920t/s，M910t/s，M630e，Lenovo V540-24IWL AIO，M90n-1，M75s-1，M720e，M75q-1，Lenovo V520S-08IKL，Lenovo V130-20IGM，Lenovo V530-22ICB，Lenovo V530-24ICB EOL date. Add: New Product E76a， M90n-1 new CTO: 11J3,11J7; Change member list
2019-12-11 | 1. Update：M710q，Lenovo V530-15ICB Desktop，Lenovo V530s-07ICB Desktop，E76，E96，Lenovo V530-15ARR Desktop，M910q，ideacentre AIO 520-24ARR，ideacentre AIO 520-27ICB，ideacentre AIO 520-24IKU，EOL date；M75n update EOW/AD date； 2. M70s/t Project name； 3. All new project name，Bom name update； 4. Move Lenovo V520S-08IKL Desktop to EOL list； 5. Add：New project Lenovo V35s-07ADA；Lenovo V50t-13IMB new CTO number 11HC，11HD；Lenovo V50s-07IMB new CTO 11HA，11HB；
2019-12-25 | 1. Add new project Durham_M；
1. Update M76a AD/EOW/EOL；
2020-01-15 | 1. Change IdeaCentre AIO 3 Planner Liye16;
2020-01-22 | 1. Change Lenovo Legion T5 28IMB05 EOW and AD；
2020-02-05 | 1. Add comments in M75n-1；
2020-02-12 | 1. Add new project M75q Gen2；
2020-02-17 | 1. Add CTO List；
2020-02-27 | 1. Add new project IdeaCentre G5 14AMR05，IdeaCentre 5 14ARE05，IdeaCentre Mini 5 01IMH05；
2020-03-09 | 1. Update Lenovo V50a-22IMB,V50a-24IMB,Lenovo V30a-22IML EOW/AD； 2. Add P720 P920 refresh 7.0(zejian);
2020-03-18 | 1. Add new products Lenovo Legion R5 28IMB05,Lenovo Legion T7 34IMZ05; 2. Update P320 TWR, P320 SFF, P330 Tiny, P520, P520c, P720, P920, P340 TWR, P340 SFF, P340 Tiny, M910t, M910s, M710t, M710s, M710e, M910q, M710q, M75s-1, M715q, M90n-1 , Lenovo V55t-15API, E76a, EOL; 3. Update Member List；
2020-03-25 | 1. Update project Lenovo V50t-13IMB, Lenovo V50s-07IMB, Lenovo V35s-07ADA, E77, E97, M90a, M70a, M70c, M70t, M70s, M70q, M75n, M80t, M80s, M90t, M90s, M80q, M90q, P340 TWR, P340 SFF, P340 Tiny EOW and AD;
2020-04-01 | 1. Project ideacentre AIO 520-24IKU, ideacentre AIO 520-22IKU, ideacentre AIO 730S-24IKB, ideacentre AIO 520-24ICB, ideacentre AIO 520-22ICB, ideacentre AIO 520-24ARR, ideacentre 510-15ICB, E76s, ideacentre 510S-07ICB, E76, E96z, E96, ideacentre A340-22ICB EOL;
2020-04-08 | 1. Add new CTO M75n 11G4/11G5/11G6/11G7； 2. Update EOL list；
2020-04-15 | 1. Update planner info Xuru XR10 Li instead of Yi Yi2 Tan； 2. Update M75s-2 name to M75t/s Gen 2，EOW/AD; 3. M90q add new CTO 11DK/11DL/11EY/11F0; M920t/s add new CTO 10U0/10U1/10U2/10U3;
2020-04-22 | 1. Add new project IdeaCentre C5 14IMB05；Project P520,P520c,P720,P920 refresh 6.0; Project P520,P520c,P720,P920 refresh 5.0 wave2, Project P520,P520c,P720,P920 refresh 7.0; 2. Project M710t, M710s, M710q, M910t, M910s, M910q EOL;
2020-04-29 | 1. Project ideacentre 720-18ICB，ideacentre AIO 520-27ICB，IdeaCentre T540-15ICB G，Lenovo V530-15ICB Desktop，Lenovo V530s-07ICB Desktop EOL;
2020-05-13 | 1. Add new project Lenovo Legion T5 26AMR5 ES，Lenovo Legion T5 26AMR5 ES；Lenovo V55t-15ARE；
2020-05-27 | 1. Add new project Yoga AIO 7 27ARH6，IdeaCentre AIO 3 22IIL5，IdeaCentre AIO 3 24IIL5；
2020-06-03 | 1. Add new project M60q；
2020-06-10 | 1. Add new project IdeaCentre G5 14IMB05，IdeaCentre G5 14AMR05 for CTO;
2020-06-17 | 1. Add new project P620，Lenovo V30a 22IIL，Lenovo V30a 24IIL；
2020-07-29 | 1. Update CTO 11E7/11E8/11EG for M70q，M80q；
2020-08-05 | 1. Add new project M70a Gen 2，M70t Gen 2，M70s Gen 2，M90t Gen 2，M90s Gen 2, M90a Gen 2，M70a Gen 2，M90q Gen 2； 2. Update ideacentre 510A-15ARR，ideacentre 510A-15ICB，Lenovo Legion T530-28ICB ES， Lenovo Legion T530-28APR，ideacentre 720-18APR，Lenovo Legion T730-28ICO，ideacentre A340-24ICB，Lenovo Legion T530-28ICB，T540-15AMA G，510A-15ARR，IdeaCentre A540-24ICB，IdeaCentre A540-24API，510-15ICK，510A-15ICK，T540-15ICK G，IdeaCentre A540-27ICB，510S-07ICK，P330 Tower，P330 SFF，P330 Tiny，P720，P920，Lenovo V130-20IGM，Lenovo V530-22ICB，Lenovo V530-24ICB，M715q，M720q，M920t，M920s，M920q，M820z，M920z，M920x，M90n-1 EOL date； 3. Update M60e EOW/AD date； 4. Project Lenovo V530-15ARR Desktop，Lenovo V540-24IWL，M710e AIO EOL；
2020-08-26 | 1. Add new projet M90n Gen 2；
2020-09-02 | 1. Add new project IdeaCentre Gaming5 14IOB6，IC Creator 5 14IOB6，IdeaCentre 5 14IOB6；Hub T；Hub Z；
2020-09-16 | 1. Add new project Lenovo Legion T5 26IOB6； 2. Add new CTO 30EN for project P340 Tower；

## PDM DT WS Portfolio Online
Action | Remark | Note | PROJECT | Sub-Series Name | CTO # | Product Category | Brand | Segment | Planner | CSR Name | Bom Name | Mkt PM | EOW | AD | Web CTO AD | IAD | Enable Web CTO | PDM PM | Status | EOL
|  |  | Den | 310S-08ASR | 90G9 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2016-11-28 | 2017-01-23 |  |  | No | guorp2 | Completed | 2020-09-30
|  |  | Malone Stockton | P320 SFF | 30BK 30BJ | DT Workstation_Commercial | ThinkStation | Commercial WS | Yimeng YM23 Zhang | STOCKTON CTO | P320_Malone_Stockton |  | 2017-04-18 | 2017-04-18 | 2017-04-18 |  | Yes | guorp2 | Completed | 2020-12-31
|  |  | Malone Stockton | P320 Twr | 30BG 30BH | DT Workstation_Commercial | ThinkStation | Commercial WS | Yimeng YM23 Zhang | MALONE CTO | P320_Malone_Stockton |  | 2017-04-18 | 2017-04-18 | 2017-04-18 |  | Yes | guorp2 | Completed | 2020-12-31
|  |  | Mofushi E-1.0 | E75 | 10QE | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia |  |  |  | 2017-03-02 | 2017-04-18 |  |  | No | guorp2 | Completed | 2020-12-31
|  |  | Mofushi_E | E95 | 10RJ | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia |  |  |  | 2017-07-17 | 2017-08-21 |  |  | No | lizj22 | Completed | 2020-12-31
| Tech Spec released on 9.6 |  | ideacentre AIO 330-20AST | F0D8CTO1WW | F0D8 | DT_Consumer | IdeaCentre | Consumer | Lynn Ling2 He |  |  |  | 2017-09-25 | 2017-11-20 |  |  | No | guorp2 | Completed | 2020-12-31
|  |  | ideacentre 310S-08IGM | 90HXCTO1WW | 90HX | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2017-12-13 | 2018-02-07 |  |  | No | guorp2 | Completed | 2020-12-31
| Tech Spec released on 1.8. MKT Spec released on 2.9 |  | Dover_M_Tiny | M625q | 10TF 10TG 10TH 10TJ 10TK | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Xuru XR10 Li | Dover Tiny CTO | M625q(Dover_M_Tiny) |  | 2018-03-20 | 2018-04-24 | 2018-04-24 |  | Yes | houce1 | Completed | 2020-09-30
| Tech Spec released on 1.8. MKT Spec released on 2.9 |  | Dover_M_Tiny | M625q Thin Client | 10TL 10UY 10V0 10V1 10V2 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Xuru XR10 Li | Dover TC CTO | M625q(Dover_M_Tiny) |  | 2018-03-20 | 2018-04-24 | 2018-04-24 |  | Yes | houce1 | Completed | 2021-12-31
| MKT Spec released on 11.7. Sys Spec released on 11.30 |  | ideacentre 510A-15ARR | 90J0CTO1WW | 90J0 | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  |  | 2018-03-02 | 2018-04-27 |  |  | No | lizj22 | Completed | 2020-12-31
| Tech Spec released on 9.8. MKT Spec released on 12.26 |  | ideacentre AIO 330-20IGM | F0D7CTO1WW | F0D7 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2018-03-21 | 2018-05-16 |  |  | No | qinn1 | Completed | 2020-12-31
| Tech Spec released on 12.26. MKT Spec released on 1.17 Update EOL Target |  | ideacentre 510A-15ICB | 90HVCTO1WW | 90HV | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2018-03-26 | 2018-05-21 |  |  | No | guorp2 | Completed | 2020-10-25
| Tech Spec released on 10.16. MKT Spec released on 3.15 |  | Singapore_E2 | Lenovo V130-20IGM | 10RX | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu |  |  |  | 2018-04-24 | 2018-05-22 |  | 2018-02-22 | No | qinn1 | Completed | 2023-03-31
| MKT Spec released on 2.23. Tech Spec released on 2.26. PP info updated. |  | Lenovo Legion T530-28ICB ES | 90JLCTO1WW | 90JL | DT_Consumer | Lenovo | Consumer | Ricky RC1 Liu |  |  |  | 2018-04-02 | 2018-05-28 |  | 2018-04-30 | No | qinn1 | Completed | 2020-12-31
| MKT Spec released on 2.23. Tech Spec released on 2.26 |  | Lenovo Legion C530-19ICB | 90JXCTO1WW | 90JX | DT_Consumer | Lenovo | Consumer | Ricky RC1 Liu |  |  |  | 2018-04-02 | 2018-05-28 |  | 2018-04-30 | No | guorp2 | Completed | 2020-09-30
| MKT Spec released on 2.23. Tech Spec released on 2.26 Update EOL Target |  | Lenovo Legion T730-28ICO | 90JFCTO1WW | 90JF | DT_Consumer | Lenovo | Consumer | Rainbow LL9 Liu |  |  |  | 2018-04-02 | 2018-05-28 |  | 2018-05-28 | No | guorp2 | Completed | 2020-09-30
| Tech Spec released on 2.26. MKT Spec released on 3.27 |  | Mansfield_M | M720t | 10SQ 10SR 10U4 10U5 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | Mansfield_M CTO | M720t/s(Mansfield_M) |  | 2018-05-15 | 2018-06-12 | 2018-06-12 | 2018-03-15 | Yes | qinn1 | Completed | 2020-12-31
| Tech Spec released on 2.26. MKT Spec released on 3.27 |  | Mansfield_M | M720s | 10ST 10SU 10U6 10U7 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | Mansfield_M CTO | M720t/s(Mansfield_M) |  | 2018-05-15 | 2018-06-12 | 2018-06-12 | 2018-03-15 | Yes | qinn1 | Completed | 2020-12-31
| MKT Spec released on 2.23. Tech Spec released on 2.26 |  | Lenovo Legion C730-19ICO | 90JHCTO1WW | 90JH | DT_Consumer | Lenovo | Consumer | Rainbow LL9 Liu |  |  |  | 2018-04-20 | 2018-06-15 |  | 2018-06-15 | No | guorp2 | Completed | 2020-09-30
| Tech Spec released on 2.26. MKT Spec released on 4.3 |  | Singapore_E3 | Lenovo V330-20ICB | 10UK 10UL | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu | Singapore_E3 | Singapore_E3 |  | 2018-05-22 | 2018-06-19 | 2018-06-19 | 2018-04-20 | Yes | guorp2 | Completed | 6/31/2021
| Tech Spec released on 2.26. MKT Spec released on 4.3 | MTM Only | Singapore_M4 | Lenovo V530-22ICB | 10US 10UT 10UU 10UV | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu | Singapore_M4 |  |  | 2018-05-22 | 2018-06-19 |  | 2018-03-23 | No | guorp2 | Completed | 2020-12-31
| Tech Spec released on 2.26. MKT Spec released on 4.3 | MTM Only | Singapore_M5 | Lenovo V530-24ICB | 10UW 10UX | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu | Singapore_M5 |  |  | 2018-05-22 | 2018-06-19 |  | 2018-03-23 | No | lizj22 | Completed | 2020-12-31
| Tech Spec released on 3.5. MKT Spec released on 3.13 |  | Dakota_M_RR | M715q | 10VG 10VH 10VJ 10VK | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Xuru XR10 Li | Dakota_M | Dakota |  | 2018-05-15 | 2018-06-19 | 2018-06-19 | 2018-03-23 | Yes | qinn1 | Completed | 2020-12-31
| Tech Spec released on 3.5. MKT Spec released on 3.13 |  | Dakota_M_RR | M715q Thinclient | 10VL 10VM 10VN 10VQ | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao | Dakota_M | Dakota |  | 2018-05-15 | 2018-06-19 | 2018-06-19 | 2018-03-23 | Yes | qinn1 | Completed | 2020-12-31
| Tech Spec released on 3.15.MKT Spec released on 4.10 |  | Mansfield_M_Tiny | M720q | 10T7 10T8 10T9 10TA 10TC | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao | Mansfield Tiny CTO | M720q(Mansfield_M) |  | 2018-05-22 | 2018-06-26 | 2018-06-26 | 2018-03-30 | Yes | qinn1 | Completed | 2020-12-31
| Tech Spec released on 3.6. MKT Spec released on 3.27 |  | Paros_M | M920t | 10SF 10SG 10U0 10U1 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Ian Yuan11 Yao | Paros_M CTO | M920t/s(Paros_M) |  | 2018-05-22 | 2018-06-26 | 2018-06-26 | 2018-03-30 | Yes | guorp2 | Completed | 2020-12-31
| Tech Spec released on 3.6. MKT Spec released on 3.27 |  | Paros_M | M920s | 10SJ 10SK 10U2 10U3 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Ian Yuan11 Yao | Paros_M CTO | M920t/s(Paros_M) |  | 2018-05-22 | 2018-06-26 | 2018-06-26 | 2018-03-30 | Yes | guorp2 | Completed | 2020-12-31
| MKT Spec released on 2.23. Tech Spec released on 2.26 |  | Lenovo Legion T530-28APR ES | 90JYCTO1WW | 90JY | DT_Consumer | Lenovo | Consumer | Rainbow LL9 Liu |  |  |  | 2018-05-03 | 2018-06-28 |  | 2018-05-14 | No | guorp2 | Completed | 2020-12-31
| MKT Spec released on 2.23. Tech Spec released on 2.26 |  | Lenovo Legion T530-28APR Non-ES | 90K0CTO1WW | 90K0 | DT_Consumer | Lenovo | Consumer | Ricky RC1 Liu |  |  |  | 2018-05-03 | 2018-06-28 |  | 2018-05-14 | No | guorp2 | Completed | 2020-12-31
| Tech Spec & MKT Spec released on 4.16 |  | ideacentre 720-18APR | 90HYCTO1WW | 90HY | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  |  | 2018-05-04 | 2018-06-29 |  |  | No | guorp2 | Completed | 2020-12-31
| Tech Spec released on 3.15. MKT Spec released on 4.10 |  | Paros_M_Tiny | M920q | 10RR 10RS 10RT 10RU 10V8 10SY | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao | Paros_M_Tiny M920q | M920q(Paros_M TN_Q) |  | 2018-05-29 | 2018-07-03 | 2018-07-03 | 2018-04-03 | Yes | qinn1 | Completed | 2020-12-31
| Tech Spec released on 4.3. MKT Spec released on 5.8 |  | Montana_M8 | M820z | 10SC 10SD | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Hua Hua7 Chen | MONTANA_M8 | M820z(Montana_M8) |  | 2018-06-19 | 2018-07-24 | 2018-07-24 | 2018-04-26 | Yes | lizj22 | Completed | 2020-10-31
| Tech Spec released on 4.3. MKT Spec released on 5.8 |  | Montana_P9 | M920z | 10S6 10S7 10Y6 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Hua Hua7 Chen | MONTANA_M9 | M920z(Montana_P9) |  | 2018-06-19 | 2018-07-24 | 2018-07-24 | 2018-05-01 | Yes | qinn1 | Completed | 2020-10-31
| Tech Spec released on 3.12. MKT Spec released on 5.21 |  | Viper | P330 Tower | 30CY 30D0 | DT Workstation_Commercial | ThinkStation | Commercial WS | Yimeng YM23 Zhang | VIPER REF 2.0 CTO | P330(Viper_Mustang) |  | 2018-07-10 | 2018-07-24 | 2018-08-14 | 2018-06-12 | Yes | guorp2 | Completed | 2021-03-31
| Tech Spec released on 3.12. MKT Spec released on 5.21 |  | Mustang | P330 SFF | 30D1 30D2 | DT Workstation_Commercial | ThinkStation | Commercial WS | Yimeng YM23 Zhang | MUSTANG REF 2.0 CTO | P330(Viper_Mustang) |  | 2018-07-10 | 2018-07-24 | 2018-08-14 | 2018-06-12 | Yes | guorp2 | Completed | 2021-03-31
| Tech Spec released on 3.15. MKT Spec released on 4.10 |  | Paros_M_Tiny | M920x | 10S0 10S1 10S2 10S3 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao | Paros_M_Tiny M920x | M920x(Paros_M TN_X) |  | 2018-06-26 | 2018-07-31 | 2018-07-31 | 2018-05-01 | Yes | houce1 | Completed | 2020-12-31
|  |  | Magic & Jordan | P720 | 30BA 30BB | DT Workstation_Commercial | ThinkStation | Commercial WS | Maura Xu12 Wang | MAGIC CTO | P720_Magic |  | 2018-07-24 | 2018-07-31 | 2018-07-31 |  | Yes | lizj22 | Completed | 2023-03-30
|  |  | Magic & Jordan | P920 | 30BC 30BD | DT Workstation_Commercial | ThinkStation | Commercial WS | Maura Xu12 Wang | JORDAN CTO | P920_Jordan |  | 2018-07-24 | 2018-07-31 | 2018-07-31 |  | Yes | lizj22 | Completed | 2022-12-31
| Tech Spec released on 5.29 |  | Barkley & Bird | P520c | 30BX 30BY | DT Workstation_Commercial | ThinkStation | Commercial WS | Keke KK1 Shi | BARKLEY CTO | P520c_Barkley |  | 2018-07-31 | 2018-07-31 | 2018-08-07 |  | Yes | houce1 | Completed | 2023-06-30
| Tech Spec released on 5.29 |  | Barkley & Bird | P520 | 30BE 30BF | DT Workstation_Commercial | ThinkStation | Commercial WS | Keke KK1 Shi | BIRD CTO | P520_Bird |  | 2018-07-31 | 2018-07-31 | 2018-08-07 |  | Yes | houce1 | Completed | 2023-06-30
| Tech Spec released on 4.2. MKT Spec released on 5.15 |  | Dubai_M | M725s | 10VT 10VU | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | Dubai_M CTO | M725s(Dubai_M) |  | 2018-06-26 | 2018-07-31 | 2018-07-31 | 2018-05-01 | Yes | lizj22 | Completed | 2020-09-30
| Similar as M920x. P330 Tiny MKT Spec released on 6.12. P330 Tiny Tech Spec released on 6.20 |  | Camaro | P330 Tiny | 30CF 30CE | DT Workstation_Commercial | ThinkStation | Commercial WS | Qianyu QY18 Wang | P330 Tiny | M920x(Paros_M TN_X) |  | 2018-07-16 | 2018-07-31 | 2018-07-31 |  | Yes | houce1 | Completed | 2021-03-31
|  |  | Lenovo Legion T730-28ICO | 90JGCTO1WW | 90JG | DT_Consumer | Lenovo | Consumer | Ricky RC1 Liu |  |  |  |  | 2018-11-16 |  |  | No | lizj22 | Completed | 2020-09-30
| Tech Spec released on 9.18. MKT Spec released on 10.22 |  | Yoga A940-27ICB | F0E4 F0E5 | F0E4 F0E5 | DT_Consumer | Lenovo | Consumer | Rainbow LL9 Liu |  |  |  | 2018-11-19 | 2019-01-14 |  |  | No | qinn1 | Completed | 2021-09-01
| Tech Spec updated on 9.21. MKT Spec released on 10.22 |  | ideacentre A340-24ICB | F0E6CTO1WW | F0E6 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2018-11-21 | 2019-01-16 |  |  | No | lizj22 | Completed | 2020-12-31
| Tech Spec released on 9.21. MKT Spec released on 10.22 |  | ideacentre A340-24IGM | F0E7CTO1WW | F0E7 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2018-11-21 | 2019-01-16 |  |  | No | guorp2 | Completed | 2020-12-31
| Tech Spec released on 9.21. MKT Spec released on 10.22 |  | ideacentre A340-22IGM | F0EACTO1WW | F0EA | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2018-11-21 | 2019-01-16 |  |  | No | guorp2 | Completed | 2020-12-31
| Tech Spec released on 9.21. MKT Spec released on 10.22 |  | ideacentre A340-24IWL | F0E8CTO1WW | F0E8 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2018-11-28 | 2019-01-31 |  |  | No | lizj22 | Completed | 2020-12-31
| Tech Spec released on 9.21. MKT Spec released on 10.22 |  | ideacentre A340-22IWL | F0EBCTO1WW | F0EB | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2018-11-28 | 2019-01-31 |  |  | No | guorp2 | Completed | 2020-12-31
| MKT Spec updated on 1.3 |  | Lenovo Legion C530-19ICB | 90L2CTO1WW | 90L2 | DT_Consumer | Lenovo | Consumer | Ricky RC1 Liu |  |  |  | 2018-11-28 | 2019-01-31 |  |  | No | qinn1 | Completed | 2020-09-30
| MKT Spec updated on 1.3 |  | Lenovo Legion T530-28ICB | 90L3CTO1WW 90L4CTO1WW | 90L3 90L4 | DT_Consumer | Lenovo | Consumer | Ricky RC1 Liu |  |  |  | 2018-11-28 | 2019-01-31 |  |  | No | qinn1 | Completed | 2020-12-31
| Tech Spec released on 12.25. MKT Spec released on 1.8 |  | Eton_M_Tiny | M630e | 10YM | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia |  |  |  | 2019-02-05 | 2019-03-12 |  |  | No | qinn1 | Completed | 2021-03-31
| Tech Spec released on 12.25. MKT Spec released on 1.8 |  | Eton_M_Tiny | M630e TIO | 10YN | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia |  |  |  | 2019-02-05 | 2019-03-12 |  |  | No | qinn1 | Completed | 2021-03-31
| Tech Spec released on 1.7. IMG released on 3.22 |  | A340-22AST | F0EQCTO1WW | F0EQ | DT_Consumer | IdeaCentre | Consumer | Lynn Ling2 He |  |  |  | 2019-03-04 | 2019-04-29 |  |  | No | qinn1 | Completed | 2020-12-31
| Tech Spec released on 3.25 |  | T540-15AMA G | 90L5CTO1WW | 90L5 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2019-05-03 | 2019-06-28 |  |  | No | guorp2 | Completed | 2020-12-31
| Tech Spec updated on 3.5. MKT Spec released on 4.10 |  | Princeton_M_Nano | M90n-1 | 11AD 11AE 11AF 11AG 11AK | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao | Princeton_M Nano | M90n-1(Princeton_M_Nano) |  | 2019-05-28 | 2019-07-02 | 2019-07-02 | 2019-05-21 | Yes | lizj22 | Completed | 2021-06-30
| Tech Spec updated on 3.5. MKT Spec released on 4.10 |  | Princeton_M_Nano | M90n-1 Thin Client | 11AH 11AJ 11AM 11AS 11J3 11J7 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao | Princeton_M Nano | M90n-1(Princeton_M_Nano) |  | 2019-05-28 | 2019-07-02 | 2019-07-02 | 2019-05-21 | Yes | lizj22 | Completed | 2021-06-30
| Tech Spec released on 4.1 |  | 510A-15ARR | 90J0CTO2WW | 90J0 | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  |  | 2019-06-03 | 2019-07-29 |  |  | No | lizj22 | Completed | 2020-12-31
| Tech Spec released on 3.19 |  | IdeaCentre A540-24ICB | F0ELCTO1WW | F0EL | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu |  |  |  | 2019-06-05 | 2019-07-31 |  |  | No | lizj22 | Completed | 2020-12-31
| Tech Spec released on 3.19 |  | IdeaCentre A540-24API | F0EMCTO1WW | F0EM | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu |  |  |  | 2019-06-05 | 2019-07-31 |  |  | No | qinn1 | Completed | 2021-09-30
|  |  | Male_ICK | 510-15ICK | 90LU | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2019-06-28 | 2019-07-31 |  |  | No | qinn1 | Completed | 2020-12-31
|  |  | Male_ICK | 510A-15ICK | 90LV | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2019-06-28 | 2019-07-31 |  |  | No | lizj22 | Completed | 2020-12-31
|  |  | Manila_ICK | T540-15ICK G | 90LW | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2019-06-28 | 2019-07-31 |  |  | No | lizj22 | Completed | 2020-12-31
| Tech Spec released on 4.2 |  | IdeaCentre A540-27ICB | F0EKCTO1WW | F0EK | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu |  |  |  | 2019-06-11 | 2019-08-06 |  |  | No | lizj22 | Completed | 2020-12-31
|  |  | Metz_E | E76x | 11BA | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia |  |  |  | 2019-07-23 | 2019-08-07 |  |  | No | guorp2 | Completed | 2020-12-31
|  |  | Metz_E | E76p | 11BR | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia |  |  |  | 2019-07-30 | 2019-08-14 |  |  | No | lizj22 | Completed | 2020-12-31
|  |  | Metz_E | E96x | 11BB | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia |  |  |  | 2019-07-30 | 2019-08-14 |  |  | No | qinn1 | Completed | 2020-12-31
|  |  | Aegean | A340-24ICK | F0ER | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2019-07-19 | 2019-08-30 |  |  | No | qinn1 | Completed | 2020-12-31
|  |  | Aegean | A340-22ICK | F0ES | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2019-07-19 | 2019-08-30 |  |  | No | lizj22 | Completed | 2020-12-31
|  |  | Duke_M | M75s-1 | 11A9 11AA 11AV 11AW | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | Duke_M | M75s-1(Duke_M) |  | 2019-08-27 | 2019-09-30 | 2019-09-30 | 2019-08-12 | Yes | houce1 | Completed | 2020-12-31
|  |  | Meath_ICK | 510S-07ICK | 90LX | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2019-08-05 | 2019-09-30 |  |  | No | lizj22 | Completed | 2020-12-31
|  |  | Metz_VS | V530S-07ICR | 11BL 11BM | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia | Metz_VS | V530S-07ICR/YTM6900s(Metz_VS_Metz_YT) |  | 2019-08-30 | 2019-09-30 | 2019-09-30 |  | Yes | qinn1 | Completed | 2020-12-31
|  |  | Metz_V | V530-15ICR | 11BG 11BH | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia | Metz_V | V530-15ICR(Metz_V) |  | 2019-08-27 | 2019-09-30 | 2019-09-30 |  | Yes | lizj22 | Completed | 2020-12-31
|  |  | Metz_MS | M720e | 11BD 11BE | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Hua Hua7 Chen | Metz_MS | M720e(Metz_MS) |  | 2019-08-27 | 2019-09-30 | 2019-09-30 |  | Yes | guorp2 | Completed | 2020-11-30
|  |  | Duke_M_Tiny | M75q-1 | 11A4 11A5 11A6 11A7 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Xuru XR10 Li | Duke_M_Tiny CTO | M75q-1(Duke_M_Tiny) |  | 2019-09-17 | 2019-10-15 | 2019-10-15 | 2019-08-22 | Yes | lizj22 | Completed | 2021-01-31
|  |  | Dhaka_V | Lenovo V55t-15API | 11CB 11CC | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia | Dhaka_V | V55t-15API(Dhaka_V) |  | 2019-09-24 | 2019-10-29 | 2019-10-29 |  | Yes | qinn1 | Completed | 2021-03-31
|  |  | Dhaka_E | E76a | 11E6 | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia |  |  |  | 2019/11/5 | 2019-11-29 |  |  | No | guorp2 | Completed | 2021-03-31
|  |  | Seoul_E5 | Lenovo V30a-24IML | 11FT 11FU | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu |  |  | lipy9 | 2020-01-14 | 2020-02-18 |  |  | No | qinn1 | Completed | 2020-12-31
|  |  | Ecuador | IdeaCentre 3 07ADA05 | 90MV 90NT | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  | Liuqic | 2020-01-04 | 2020-02-28 |  |  | No | lizj22 | Completed | 2020-12-31
|  |  | Monaco | IdeaCentre 5 14IMB05 | 90NA 90NQ | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  | Gaofei4 | 2019-12-31 | 2020-03-04 |  |  | No | guorp2 | Completed
|  |  | Capri | IdeaCentre AIO 3 22ADA05 | F0EX | DT_Consumer | IdeaCentre | Consumer | Ye Ye16 Li |  |  | Zhangtao | 2020-02-03 | 2020-03-31 |  |  | No | qinn1 | Completed
|  |  | Capri | IdeaCentre AIO 3 24IMB05 | F0EU | DT_Consumer | IdeaCentre | Consumer | Ye Ye16 Li |  |  | Zhangtao | 2020-02-03 | 2020-03-31 |  |  | No | guorp2 | Completed
|  |  | Capri | IdeaCentre AIO 3 22IMB05 | F0EV | DT_Consumer | IdeaCentre | Consumer | Ye Ye16 Li |  |  | Zhangtao | 2020-02-03 | 2020-03-31 |  |  | No | lizj22 | Completed
|  |  | Capri | IdeaCentre AIO 3 27IMB05 | F0EY | DT_Consumer | IdeaCentre | Consumer | Ye Ye16 Li |  |  | Zhangtao | 2020-02-03 | 2020-03-31 |  |  | No | guorp2 | Completed
|  |  | Capri | IdeaCentre AIO 3 24ARE05 | F0EW | DT_Consumer | IdeaCentre | Consumer | Ye Ye16 Li |  |  | Zhangtao | 2020-02-07 | 2020-04-03 |  |  | No | qinn1 | Completed
|  |  | Metra | Lenovo Legion T5 28IMB05 | 90NC 90NK | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  | fengweid | 2020-02-14 | 2020-04-10 |  |  | No | guorp2 | Completed
|  |  | Aletai | IdeaCentre AIO 5 24IMB05 | F0FB | DT_Consumer | IdeaCentre | Consumer | Ye Ye16 Li |  |  | zhengtao | 2020-02-28 | 2020-04-24 |  |  | No | lizj22 | Completed
|  |  | Metra | Lenovo Legion R5 28IMB05 | 90NE 90NJ | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2020-03-03 | 2020-04-28 |  |  | No | guorp2 | Completed
|  |  | Poland | IdeaCentre G5 14IMB05 | 90N9 90NR | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  | Gaofei4 | 2020-03-05 | 2020-04-30 |  |  | Yes | lizj22 | Completed
|  |  | Estonia | IdeaCentre 3 07IMB05 | 90NB 90NS | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  | Liuqic | 2020-03-05 | 2020-04-30 |  |  | No | guorp2 | Completed
|  |  | Aletai | IdeaCentre AIO 5 27IMB05 | F0FA | DT_Consumer | IdeaCentre | Consumer | Ye Ye16 Li |  |  | zhengtao | 2020-03-05 | 2020-04-30 |  |  | No | houce1 | Completed
|  |  | Seoul_E4 | Lenovo V30a-22IML | 11FV 11FW | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu |  |  | lipy9 | 2020-04-08 | 2020-05-13 |  |  | No | houce1 | Completed | 2020-12-31
|  |  | Madison_M_Tiny | M70q | 11DT 11DU 11DV 11DW 11E7 11E8 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao | Madison_M_Tiny | M70q/M730q(Madison_M) | Lisy22 | 2020-04-21 | 2020-05-14 | 2020-05-14 |  | Yes | guorp2 | Completed | 2021-12-31
|  |  | Portland_M_Tiny | M80q | 11DN 11DQ 11DR 11DS 11EG | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao | Portland_M_Tiny | M80q_KTM930q(Portland_M_Tiny) | Lisy22 | 2020-04-21 | 2020-05-14 | 2020-05-14 |  | Yes | guorp2 | Completed | 2021-12-31
|  |  | Dorsten_V | Lenovo V35s-07ADA | 11HE 11HF 11HQ 11HR | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia | Dorsten_V | YTM3900q/V35S-07ADA(Dorsten_YT) |  | 2020-04-14 | 2020-05-15 | 2020-05-15 |  | Yes | houce1 | Completed | 2021-07-31
|  |  | Madison_M | M70t | 11D9 11DA 11EU 11EV | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Ian Yuan11 Yao | Madison_M CTO | M70t/s(Madison_M) | Lisy22 | 2020-04-14 | 2020-05-21 | 2020-05-21 |  | Yes | lizj22 | Completed | 2021-12-31
|  |  | Madison_M | M70s | 11DB 11DC 11EW 11EX | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Ian Yuan11 Yao | Madison_M CTO | M70t/s(Madison_M) | Lisy22 | 2020-04-14 | 2020-05-21 | 2020-05-21 |  | Yes | qinn1 | Completed | 2021-12-31
|  | Add new CTO | Damascus_M_Nano | M75n | 11BS 11BT 11BU 11BV 11BW 11BX 11GW 11GX 11G4 11G5 11G6 11G7 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Junjun JJ25 Liu | Damascus Fan CTO Damascus Fanless CTO | M75n(Damascus_M_Nano) | Linyf6 | 2020-04-17 | 2020-05-21 | 2020-05-21 |  | Yes | houce1 | Completed | 2021-12-31
|  |  | Portland_M | M80t | 11CS 11CT 11EK 11EL | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | Portland_M | M80t/s_KTM930t/s(Portland_M) | Lisy22 | 2020-04-30 | 2020-05-26 | 2020-05-26 |  | Yes | houce1 | Completed | 2021-12-31
|  |  | Portland_M | M80s | 11CU 11CV 11EM 11EN | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | Portland_M | M80t/s_KTM930t/s(Portland_M) | Lisy22 | 2020-04-30 | 2020-05-26 | 2020-05-26 |  | Yes | houce1 | Completed | 2021-12-31
|  |  | Madison_V | Lenovo V50t-13IMB | 11EC 11ED 11HC 11HD | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia | Madison_V | V50t-13IMB(Madison_V) | songhao1 | 2020-04-21 | 2020-05-27 | 2020-05-27 |  | Yes | lizj22 | Completed
|  |  | Macon_M7 | M70a | 11CK 11CL 11E2 11E3 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Hua Hua7 Chen | Macon_M7 | M70a/M830z(Macon_M7) | Clai1 | 2020-04-23 | 2020-05-29 | 2020-05-29 |  | Yes | guorp2 | Completed
|  |  | Seoul_M5 | Lenovo V50a-24IMB | 11FJ 11FK 11FL 11FM | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu |  |  | lipy9 | 2020-04-27 | 2020-06-01 |  |  | No | guorp2 | Completed
|  |  | Seoul_M4 | Lenovo V50a-22IMB | 11FN 11FQ 11FR 11FS | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu |  |  | lipy9 | 2020-04-27 | 2020-06-01 |  |  | No | lizj22 | Completed
|  |  | Prague_M | M90t | 11CY 11D0 11D4 11D5 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | Prague_M | M90t/s_KTM993t (Prague_M) | Lisy22 | 2020-05-07 | 2020-06-02 | 2020-06-02 |  | Yes | lizj22 | Completed
|  |  | Prague_M | M90s | 11D1 11D2 11D6 11D7 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | Prague_M | M90t/s_KTM993t (Prague_M) | Lisy22 | 2020-05-07 | 2020-06-02 | 2020-06-02 |  | Yes | Qinn1 | Completed
|  |  | Madison_E | E77 | 11EB | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia |  |  | songhao1 | 2020-04-28 | 2020-06-03 |  |  | No | houce1 | Completed | 2021-08-31
|  |  | Macon_P9 | M90a | 11CD 11CE 11DY 11E0 11JX | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Hua Hua7 Chen | Macon_P9 | M90a_M930z(Macon_P9) | Clai1 | 2020-04-30 | 2020-06-04 | 2020-06-04 |  | Yes | guorp2 | Completed
|  |  | Madison_E | E97 | 11EA | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia |  |  | songhao1 | 2020-05-05 | 2020-06-05 |  |  | No | lizj22 | Completed | 2021-08-31
|  |  | Cyber | Lenovo Legion T7 34IMZ05 | 90Q8 90Q9 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2020-04-13 | 2020-06-08 |  |  | No | qinn1 | Completed
|  |  | Prague_M_Tiny | M90q | 11CR 11DG 11DH 11DJ 11DK 11DL 11EY 11F0 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao | Prague_M_Tiny | M90q(Prague_M_Tiny) | Lisy22 | 2020-05-05 | 2020-06-11 | 2020-06-11 |  | Yes | guorp2 | Completed
|  |  | Sabre | P340 Tiny | 30DE 30DF 30DG 30DR 30DS | DT Workstation_Commercial | ThinkStation | Commercial WS | Qianyu QY18 Wang | P340 Tiny | P340 Tiny(Sabre) | fangxin3 | 2020-05-07 | 2020-06-11 | 2020-06-11 |  | Yes | lizj22 | Completed | 2021-09-30
|  |  | Corsair_Hellcat | P340 SFF | 30DK 30DL 30DN | DT Workstation_Commercial | ThinkStation | Commercial WS | Yimeng YM23 Zhang | HELLCAT CTO | P340(Corsair_Hellcat) | fangxin3 | 2020-05-26 | 2020-06-30 | 2020-06-30 |  | Yes | guorp2 | Completed | 2021-09-30
|  |  | Corsair_Hellcat | P340 Tower | 30DH 30DJ 30DM 30EN | DT Workstation_Commercial | ThinkStation | Commercial WS | Yimeng YM23 Zhang | CORSAIR CTO | P340(Corsair_Hellcat) | fangxin3 | 2020-05-26 | 2020-06-30 | 2020-06-30 |  | Yes | houce1 | Completed | 2021-09-30
|  |  | Madison_VS | Lenovo V50s-07IMB | 11EE 11EF 11HA 11HB | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia | Madison_VS | V50s-07IMB/M4900q(Madison_vs) | songhao1 | 2020-06-02 | 2020-07-10 | 2020-07-10 |  | Yes | lizj22 | Completed
|  |  | Denmark | IdeaCentre C5 14IMB05 | 90R7 90R8 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2020-05-15 | 2020-07-10 |  |  | No | qinn1 | Completed
|  |  | Thun | IdeaCentre Mini 5 01IMH05 | 90Q6 90Q7 | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  |  | 2020-06-05 | 2020-07-31 |  |  | No | lizj22 | Completed
|  |  | Panama | IdeaCentre G5 14AMR05 | 90Q0 90Q1 | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  |  | 2020-06-12 | 2020-08-07 |  |  | Yes | guorp2 | Completed
|  |  | PaloAlto | IdeaCentre 5 14ARE05 | 90Q2 90Q3 | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  |  | 2020-06-12 | 2020-08-07 |  |  | No | houce1 | In Progress
|  |  | Madison_MS | M70c | 11GJ 11GK 11GL 11GM | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Hua Hua7 Chen |  | M70c/M730e KT(Madison_MS) | clai1 | 2020-07-21 | 2020-08-28 | 2020-08-28 |  | Yes | lizj22 | In Progress | 2021-11-30
|  |  | Stealth | P620 | 30E0 30E1 | DT Workstation_Commercial | ThinkStation | Commercial WS | Yimeng YM23 Zhang | Terminator CTO |  |  | 2020-08-24 | 2020-09-04 |  | 2020-07-13 | Yes | qinn1 | In Progress
|  |  | Punk | Lenovo Legion T5 26AMR5 ES | 90RB | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2020-07-21 | 2020-09-11 |  |  | No | guorp2 | In Progress
|  |  | Punk | Lenovo Legion T5 26AMR5 Non ES | 90RC | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu |  |  |  | 2020-07-21 | 2020-09-11 |  |  | No | guorp2 | In Progress
Add |  |  | Denali | Hub T | 11H0 11H1 | DT_SMB/Commercial/NEC | ThinkSmart | Commercial DT | Ian Yuan11 Yao |  |  |  | 2020-09-15 | 2020-09-15 |  |  | No | guorp2 | In Progress
Add |  |  | Denali | Hub Z | 11H2 11H3 | DT_SMB/Commercial/NEC | ThinkSmart | Commercial DT | Ian Yuan11 Yao |  |  |  | 2020-09-15 | 2020-09-15 |  |  | No | guorp2 | In Progress
|  |  | IdeaCentre AIO 3 22IIL5 | F0FQCTO1WW | F0FQ | DT_Consumer | IdeaCentre | Consumer | Ye Ye16 Li |  |  |  | 2020-08-21 | 2020-10-16 |  |  | No | guorp2 | In Progress
|  |  | IdeaCentre AIO 3 24IIL5 | F0FRCTO1WW | F0FR | DT_Consumer | IdeaCentre | Consumer | Ye Ye16 Li |  |  |  | 2020-08-21 | 2020-10-16 |  |  | No | qinn1 | In Progress
|  |  | Santiago_E4 | Lenovo V30a 22IIL | 11LC 11LD | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu |  |  |  | 2020-09-11 | 2020-10-16 |  |  | No | houce1 | In Progress
|  |  | Santiago_E5 | Lenovo V30a 24IIL | 11LA 11LB | DT_SMB/Commercial/NEC | Lenovo | SMB | Kevin ZJ9 Liu |  |  |  | 2020-09-11 | 2020-10-16 |  |  | No | qinn1 | In Progress
|  |  | Durham_M | M75t Gen 2 | 11KB 11KC 11KD 11KE | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Ian Yuan11 Yao |  |  |  | 2020-09-15 | 2020-10-20 | 2020-09-30 |  | Yes | houce1 | Not Start
|  |  | Durham_M | M75s Gen 2 | 11JA 11JB 11JC 11JD | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Ian Yuan11 Yao |  |  |  | 2020-09-15 | 2020-10-20 | 2020-09-30 |  | Yes | houce1 | Not Start
|  |  | Durham_M_Tiny | M75q Gen2 | 11JJ 11JK 11JL 11JM | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Xuru XR10 Li | Durham_M_Tiny CTO |  | xiaosh1 | 2020-09-22 | 2020-10-29 | 2020-10-29 |  | Yes | lizj22 | Not Start | 2021-01-31
|  |  | Derby_V | Lenovo V55t-15ARE | 11KF 11KG 11KH 11KJ | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia | Derby_V |  |  | 2020-10-16 | 2020-11-20 |  |  | Yes | lizj22 | In Progress
|  |  | Ely_M_Tiny | M60e | 11LU 11LV 11LW 11LX 11LY 11M0 11M1 11M2 | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia |  |  |  | 2020-12-25 | 2021-01-29 |  |  | No | guorp2 | Not Start
Add |  |  | Avengers | Lenovo Legion T5 26IOB6 | 90RS 90RT |  |  | Consumer | Ricky RC1 Liu |  |  |  | 2021-01-25 | 2021-03-22 |  |  | No | houce1 | Not Start
|  |  | Paterson_M | M90n Gen 2 | 11NA 11NB 11NC 11ND 11NE 11NF 11NG 11NH 11NJ 11NK | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Junjun JJ25 Liu |  |  |  | 2021-02-23 | 2021-03-31 |  |  | Yes | qinn1 | Not Start
Add |  |  | Peking | IdeaCentre Gaming5 14IOB6 | 90RD 90RE | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  |  | 2021-02-03 | 2021-03-31 |  |  | No | houce1 | Not Start
Add |  |  | Dallas | IC Creator 5 14IOB6 | 90RF 90RG | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  |  | 2021-02-03 | 2021-03-31 |  |  | No | lizj22 | Not Start
Add |  |  | Malbork | IdeaCentre 5 14IOB6 | 90RH 90RJ | DT_Consumer | IdeaCentre | Consumer | Ricky RC1 Liu |  |  |  | 2021-02-03 | 2021-03-31 |  |  | No | qinn1 | Not Start
|  |  | Malaga_M7 | M70a Gen 2 | 11K3 11K4 11K5 11K6 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Hua Hua7 Chen |  |  |  | 2021-03-23 | 2021-04-27 |  |  | Yes | houce1 | Not Start
|  |  | Moroni_M | M70t Gen 2 | 11M3 11M4 11M7 11M8 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Ian Yuan11 Yao |  |  |  | 2021-03-23 | 2021-04-27 |  |  | Yes | lizj22 | Not Start
|  |  | Moroni_M | M70s Gen 2 | 11M5 11M6 11M9 11MA | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Ian Yuan11 Yao |  |  |  | 2021-03-23 | 2021-04-27 |  |  | Yes | lizj22 | Not Start
|  |  | Moroni_M_Tiny | M70q Gen 2 | 11MQ 11MR 11MU 11MV 11MS 11MT 11MW 11MX | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao |  |  |  | 2021-03-23 | 2021-04-27 |  |  | Yes | guorp2 | Not Start
|  |  | Pleasanton_M_Tiny | M90q Gen 2 | 11MY 11N0 11N3 11N4 11N1 11N2 11N5 11N6 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Astrid Jing12 Zhao |  |  |  | 2021-04-13 | 2021-05-18 |  |  | Yes | guorp2 | Not Start
|  |  | Malaga_P9 | M90a Gen 2 | 11JY 11K0 11K1 11K2 11MN | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Hua Hua7 Chen |  |  |  | 2021-04-13 | 2021-05-20 |  |  | Yes | houce1 | Not Start
|  |  | Pleasanton_M | M90t Gen 2 | 11L0 11L1 11L4 11L5 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang |  |  |  | 2021-04-20 | 2021-05-25 |  |  | Yes | qinn1 | Not Start
|  |  | Pleasanton_M | M90s Gen 2 | 11L2 11L3 11L6 11L7 | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang |  |  |  | 2021-04-20 | 2021-05-25 |  |  | Yes | qinn1 | Not Start
Note on P1: Runpeng RP2 Guo: Always same as AD
Note on Q1: Runpeng RP2 Guo: IAD=EOW-1 Week
Note on E58: Runpeng RP2 Guo: Thin client与非Thin client只有风扇上的差别 对于我们team没有任何影响 完全可以当做一个项目
Note on O71: Stephen Qi1 Shi: AD of 11AV & 11AW is 11.29
Note on D78: Runpeng RP2 Guo: 此项目本于11月29日AD 但是由于planner漏报导致项目延期

## FY2021 Workload Planning
Model | CTO | Type | PM | EOW | AD | Enable Web CTO | time axis 2019-01-08 to 2021-05-25
IdeaCentre AIO 3 24ARE05 | F0EW | New Launch | houce1 | 2020-02-07 | 2020-04-03 | No | 2019-12-10: Tech Spec/CSR Release; 2019-12-17: SBB maintain; 2019-12-24: SBB maintain; 2019-12-31: SBB DRR; 2020-01-07: SBB Review/Final; 2020-01-14: MKT Spec/POR Release; 2020-01-21: MTM Maintain; 2020-01-28: MTM DRR; 2020-02-04: MTM Review/Final/EOW
IdeaCentre AIO 5 24IMB05 | F0FB | New Launch | lizj22 | 2020-02-28 | 2020-04-24 | No | 2019-12-31: Tech Spec/CSR Release; 2020-01-07: SBB maintain; 2020-01-14: SBB maintain; 2020-01-21: SBB DRR; 2020-01-28: SBB Review/Final; 2020-02-04: MKT Spec/POR Release; 2020-02-11: MTM Maintain; 2020-02-18: MTM DRR; 2020-02-25: MTM Review/Final/EOW
Lenovo Legion R5 28IMB05 | 90NE | New Launch | guorp2 | 2020-03-03 | 2020-04-28 | No | 2020-01-07: Tech Spec/CSR Release; 2020-01-14: SBB maintain; 2020-01-21: SBB maintain; 2020-01-28: SBB DRR; 2020-02-04: SBB Review/Final; 2020-02-11: MKT Spec/POR Release; 2020-02-18: MTM Maintain; 2020-02-25: MTM DRR; 2020-03-03: MTM Review/Final
IdeaCentre G5 14IMB05 | 90N9 | New Launch | lizj22 | 2020-03-05 | 2020-04-30 | No | 2020-01-07: Tech Spec/CSR Release; 2020-01-14: SBB maintain; 2020-01-21: SBB maintain; 2020-01-28: SBB DRR; 2020-02-04: SBB Review/Final; 2020-02-11: MKT Spec/POR Release; 2020-02-18: MTM Maintain; 2020-02-25: MTM DRR; 2020-03-03: MTM Review/Final/EOW
IdeaCentre AIO 5 27IMB05 | F0FA | New Launch | houce1 | 2020-03-05 | 2020-04-30 | No | 2020-01-07: Tech Spec/CSR Release; 2020-01-14: SBB maintain; 2020-01-21: SBB maintain; 2020-01-28: SBB DRR; 2020-02-04: SBB Review/Final; 2020-02-11: MKT Spec/POR Release; 2020-02-18: MTM Maintain; 2020-02-25: MTM DRR; 2020-03-03: MTM Review/Final/EOW
IdeaCentre 3 07IMB05 | 90NB | New Launch | guorp2 | 2020-03-05 | 2020-04-30 | No | 2020-01-07: Tech Spec/CSR Release; 2020-01-14: SBB maintain; 2020-01-21: SBB maintain; 2020-01-28: SBB DRR; 2020-02-04: SBB Review/Final; 2020-02-11: MKT Spec/POR Release; 2020-02-18: MTM Maintain; 2020-02-25: MTM DRR; 2020-03-03: MTM Review/Final/EOW
Lenovo V30a-22IML | 11FV 11FW | New Launch | houce1 | 2020-04-08 | 2020-05-13 | No | 2020-02-11: Tech Spec/CSR Release; 2020-02-18: SBB maintain; 2020-02-25: SBB maintain; 2020-03-03: SBB DRR; 2020-03-10: SBB Review/Final; 2020-03-17: MKT Spec/POR Release; 2020-03-24: MTM Maintain; 2020-03-31: MTM DRR; 2020-04-07: MTM Review/Final/EOW
M70q | 11DT | New Launch | guorp2 | 2020-04-21 | 2020-05-14 | Yes | 2020-01-21: Tech Spec/CSR Release; 2020-01-28: SBB maintain; 2020-02-04: SBB maintain; 2020-02-11: SBB DRR; 2020-02-18: SBB Review/Final; 2020-02-25: MKT Spec/POR Release; 2020-03-03: MTM Maintain; 2020-03-10: MTM DRR; 2020-03-17: MTM Review/Final; 2020-03-24: PM/Final/CV Long; 2020-03-31: Data/BOM Final; 2020-04-07: Mod; 2020-04-14: Mod/EOW; 2020-04-21: QA; 2020-04-28: PMv(approve); 2020-05-05: BU; 2020-05-12: eC/AD
M80q | 11DN | New Launch | guorp2 | 2020-04-09 | 2020-05-14 | Yes | 2020-01-21: Tech Spec/CSR Release; 2020-01-28: SBB maintain; 2020-02-04: SBB maintain; 2020-02-11: SBB DRR; 2020-02-18: SBB Review/Final; 2020-02-25: MKT Spec/POR Release; 2020-03-03: MTM Maintain; 2020-03-10: MTM DRR; 2020-03-17: MTM Review/Final; 2020-03-24: PM/Final/CV Long; 2020-03-31: Data/BOM Final; 2020-04-07: Mod/EOW; 2020-04-14: Mod; 2020-04-21: QA; 2020-04-28: PMv(approve); 2020-05-05: BU; 2020-05-12: eC/AD
Lenovo V35s-07ADA |  | New Launch | houce1 | 2020-04-14 | 2020-05-15 | Yes | 2020-01-21: Tech Spec/CSR Release; 2020-01-28: SBB maintain; 2020-02-04: SBB maintain; 2020-02-11: SBB DRR; 2020-02-18: SBB Review/Final; 2020-02-25: MKT Spec/POR Release; 2020-03-03: MTM Maintain; 2020-03-10: MTM DRR; 2020-03-17: MTM Review/Final; 2020-03-24: PM/Final/CV Long; 2020-03-31: Data/BOM Final; 2020-04-07: Mod/EOW; 2020-04-14: Mod; 2020-04-21: QA; 2020-04-28: PMv(approve); 2020-05-05: BU; 2020-05-12: eC/AD
M70t | 11D9 | New Launch | lizj22 | 2020-04-14 | 2020-05-21 | Yes | 2020-01-28: Tech Spec/CSR Release; 2020-02-04: SBB maintain; 2020-02-11: SBB maintain; 2020-02-18: SBB DRR; 2020-02-25: SBB Review/Final; 2020-03-03: MKT Spec/POR Release; 2020-03-10: MTM Maintain; 2020-03-17: MTM DRR; 2020-03-24: MTM Review/Final; 2020-03-31: PM/Final/CV Long; 2020-04-07: Data/BOM Final; 2020-04-14: Mod; 2020-04-21: Mod/EOW; 2020-04-28: QA; 2020-05-05: PMv(approve); 2020-05-12: BU; 2020-05-19: eC/AD
M70s | 11DB | New Launch | qinn1 | 2020-04-14 | 2020-05-21 | Yes | 2020-01-28: Tech Spec/CSR Release; 2020-02-04: SBB maintain; 2020-02-11: SBB maintain; 2020-02-18: SBB DRR; 2020-02-25: SBB Review/Final; 2020-03-03: MKT Spec/POR Release; 2020-03-10: MTM Maintain; 2020-03-17: MTM DRR; 2020-03-24: MTM Review/Final; 2020-03-31: PM/Final/CV Long; 2020-04-07: Data/BOM Final; 2020-04-14: Mod; 2020-04-21: Mod/EOW; 2020-04-28: QA; 2020-05-05: PMv(approve); 2020-05-12: BU; 2020-05-19: eC/AD
M75n | 11BS | New Launch | houce1 | 2020-04-17 | 2020-05-21 | Yes | 2020-01-28: Tech Spec/CSR Release; 2020-02-04: SBB maintain; 2020-02-11: SBB maintain; 2020-02-18: SBB DRR; 2020-02-25: SBB Review/Final; 2020-03-03: MKT Spec/POR Release; 2020-03-10: MTM Maintain; 2020-03-17: MTM DRR; 2020-03-24: MTM Review/Final; 2020-03-31: PM/Final/CV Long; 2020-04-07: Data/BOM Final; 2020-04-14: Mod/EOW; 2020-04-21: Mod; 2020-04-28: QA; 2020-05-05: PMv(approve); 2020-05-12: BU; 2020-05-19: eC/AD
M80t |  | New Launch | houce1 | 2020-04-30 | 2020-05-26 | Yes | 2020-02-04: Tech Spec/CSR Release; 2020-02-11: SBB maintain; 2020-02-18: SBB maintain; 2020-02-25: SBB DRR; 2020-03-03: SBB Review/Final; 2020-03-10: MKT Spec/POR Release; 2020-03-17: MTM Maintain; 2020-03-24: MTM DRR; 2020-03-31: MTM Review/Final; 2020-04-07: PM/Final/CV Long; 2020-04-14: Data/BOM Final; 2020-04-21: Mod/EOW; 2020-04-28: Mod; 2020-05-05: QA; 2020-05-12: PMv(approve); 2020-05-19: BU; 2020-05-26: eC/AD
M80s |  | New Launch | houce1 | 2020-04-30 | 2020-05-26 | Yes | 2020-02-04: Tech Spec/CSR Release; 2020-02-11: SBB maintain; 2020-02-18: SBB maintain; 2020-02-25: SBB DRR; 2020-03-03: SBB Review/Final; 2020-03-10: MKT Spec/POR Release; 2020-03-17: MTM Maintain; 2020-03-24: MTM DRR; 2020-03-31: MTM Review/Final; 2020-04-07: PM/Final/CV Long; 2020-04-14: Data/BOM Final; 2020-04-21: Mod/EOW; 2020-04-28: Mod; 2020-05-05: QA; 2020-05-12: PMv(approve); 2020-05-19: BU; 2020-05-26: eC/AD
Lenovo V50t-13IMB | 11EC | New Launch | lizj22 | 2020-04-21 | 2020-05-27 | Yes | 2020-02-04: Tech Spec/CSR Release; 2020-02-11: SBB maintain; 2020-02-18: SBB maintain; 2020-02-25: SBB DRR; 2020-03-03: SBB Review/Final; 2020-03-10: MKT Spec/POR Release; 2020-03-17: MTM Maintain; 2020-03-24: MTM DRR; 2020-03-31: MTM Review/Final; 2020-04-07: PM/Final/CV Long; 2020-04-14: Data/BOM Final; 2020-04-21: Mod/EOW; 2020-04-28: Mod; 2020-05-05: QA; 2020-05-12: PMv(approve); 2020-05-19: BU; 2020-05-26: eC/AD
M70a | 11CK | New Launch | guorp2 | 2020-04-23 | 2020-05-29 | Yes | 2020-02-04: Tech Spec/CSR Release; 2020-02-11: SBB maintain; 2020-02-18: SBB maintain; 2020-02-25: SBB DRR; 2020-03-03: SBB Review/Final; 2020-03-10: MKT Spec/POR Release; 2020-03-17: MTM Maintain; 2020-03-24: MTM DRR; 2020-03-31: MTM Review/Final; 2020-04-07: PM/Final/CV Long; 2020-04-14: Data/BOM Final; 2020-04-21: Mod/EOW; 2020-04-28: Mod; 2020-05-05: QA; 2020-05-12: PMv(approve); 2020-05-19: BU; 2020-05-26: eC/AD
Lenovo V50a-22IMB |  | New Launch | lizj22 | 2020-04-27 | 2020-06-01 | No | 2020-03-03: Tech Spec/CSR Release; 2020-03-10: SBB maintain; 2020-03-17: SBB maintain; 2020-03-24: SBB DRR; 2020-03-31: SBB Review/Final; 2020-04-07: MKT Spec/POR Release; 2020-04-14: MTM Maintain; 2020-04-21: MTM DRR; 2020-04-28: MTM Review/Final/EOW
Lenovo V50a-24IMB | 11FJ | New Launch | guorp2 | 2020-04-27 | 2020-06-01 | No | 2020-03-03: Tech Spec/CSR Release; 2020-03-10: SBB maintain; 2020-03-17: SBB maintain; 2020-03-24: SBB DRR; 2020-03-31: SBB Review/Final; 2020-04-07: MKT Spec/POR Release; 2020-04-14: MTM Maintain; 2020-04-21: MTM DRR; 2020-04-28: MTM Review/Final/EOW
M90t |  | New Launch | lizj22 | 2020-05-07 | 2020-06-02 | Yes | 2020-02-11: Tech Spec/CSR Release; 2020-02-18: SBB maintain; 2020-02-25: SBB maintain; 2020-03-03: SBB DRR; 2020-03-10: SBB Review/Final; 2020-03-17: MKT Spec/POR Release; 2020-03-24: MTM Maintain; 2020-03-31: MTM DRR; 2020-04-07: MTM Review/Final; 2020-04-14: PM/Final/CV Long; 2020-04-21: Data/BOM Final; 2020-04-28: Mod/EOW; 2020-05-05: Mod; 2020-05-12: QA; 2020-05-19: PMv(approve); 2020-05-26: BU; 2020-06-02: eC/AD
M90s |  | New Launch | qinn1 | 2020-05-07 | 2020-06-02 | Yes | 2020-02-11: Tech Spec/CSR Release; 2020-02-18: SBB maintain; 2020-02-25: SBB maintain; 2020-03-03: SBB DRR; 2020-03-10: SBB Review/Final; 2020-03-17: MKT Spec/POR Release; 2020-03-24: MTM Maintain; 2020-03-31: MTM DRR; 2020-04-07: MTM Review/Final; 2020-04-14: PM/Final/CV Long; 2020-04-21: Data/BOM Final; 2020-04-28: Mod/EOW; 2020-05-05: Mod; 2020-05-12: QA; 2020-05-19: PMv(approve); 2020-05-26: BU; 2020-06-02: eC/AD
P720,P920c refresh 6.0 |  | Refresh | lizj22 | #N/A | 2020-06-02 | Yes | 2020-04-14: PM/Final/CV Long; 2020-04-21: Data/BOM Final; 2020-04-28: Mod; 2020-05-05: Mod/EOW; 2020-05-12: QA; 2020-05-19: PMv(approve); 2020-05-26: BU; 2020-06-02: eC/AD
P520,P520c refresh 6.0 |  | Refresh | houce1 | #N/A | 2020-06-02 | Yes | 2020-04-14: PM/Final/CV Long; 2020-04-21: Data/BOM Final; 2020-04-28: Mod; 2020-05-05: Mod/EOW; 2020-05-12: QA; 2020-05-19: PMv(approve); 2020-05-26: BU; 2020-06-02: eC/AD
E77 |  | New Launch | houce1 | 2020-04-28 | 2020-06-03 | No | 2020-03-03: Tech Spec/CSR Release; 2020-03-10: SBB maintain; 2020-03-17: SBB maintain; 2020-03-24: SBB DRR; 2020-03-31: SBB Review/Final; 2020-04-07: MKT Spec/POR Release; 2020-04-14: MTM Maintain; 2020-04-21: MTM DRR; 2020-04-28: MTM Review/Final/EOW
M90a | 11CD | New Launch | guorp2 | 2020-04-30 | 2020-06-04 | Yes | 2020-02-11: Tech Spec/CSR Release; 2020-02-18: SBB maintain; 2020-02-25: SBB maintain; 2020-03-03: SBB DRR; 2020-03-10: SBB Review/Final; 2020-03-17: MKT Spec/POR Release; 2020-03-24: MTM Maintain; 2020-03-31: MTM DRR; 2020-04-07: MTM Review/Final; 2020-04-14: PM/Final/CV Long; 2020-04-21: Data/BOM Final; 2020-04-28: Mod/EOW; 2020-05-05: Mod; 2020-05-12: QA; 2020-05-19: PMv(approve); 2020-05-26: BU; 2020-06-02: eC/AD
E97 |  | New Launch | lizj22 | 2020-05-05 | 2020-06-05 | No | 2020-03-10: Tech Spec/CSR Release; 2020-03-17: SBB maintain; 2020-03-24: SBB maintain; 2020-03-31: SBB DRR; 2020-04-07: SBB Review/Final; 2020-04-14: MKT Spec/POR Release; 2020-04-21: MTM Maintain; 2020-04-28: MTM DRR; 2020-05-05: MTM Review/Final/EOW
Lenovo Legion T7 34IMZ05 |  | New Launch | qinn1 | 2020-04-13 | 2020-06-08 | No | 2020-02-18: Tech Spec/CSR Release; 2020-02-25: SBB maintain; 2020-03-03: SBB maintain; 2020-03-10: SBB DRR; 2020-03-17: SBB Review/Final; 2020-03-24: MKT Spec/POR Release; 2020-03-31: MTM Maintain; 2020-04-07: MTM DRR; 2020-04-14: MTM Review/Final
M90q | 11CR | New Launch | guorp2 | 2020-05-05 | 2020-06-11 | Yes | 2020-02-18: Tech Spec/CSR Release; 2020-02-25: SBB maintain; 2020-03-03: SBB maintain; 2020-03-10: SBB DRR; 2020-03-17: SBB Review/Final; 2020-03-24: MKT Spec/POR Release; 2020-03-31: MTM Maintain; 2020-04-07: MTM DRR; 2020-04-14: MTM Review/Final; 2020-04-21: PM/Final/CV Long; 2020-04-28: Data/BOM Final; 2020-05-05: Mod/EOW; 2020-05-12: Mod; 2020-05-19: QA; 2020-05-26: PMv(approve); 2020-06-02: BU; 2020-06-09: eC/AD
P340 Tiny |  | New Launch | lizj22 | 2020-05-07 | 2020-06-11 | Yes | 2020-02-18: Tech Spec/CSR Release; 2020-02-25: SBB maintain; 2020-03-03: SBB maintain; 2020-03-10: SBB DRR; 2020-03-17: SBB Review/Final; 2020-03-24: MKT Spec/POR Release; 2020-03-31: MTM Maintain; 2020-04-07: MTM DRR; 2020-04-14: MTM Review/Final; 2020-04-21: PM/Final/CV Long; 2020-04-28: Data/BOM Final; 2020-05-05: Mod/EOW; 2020-05-12: Mod; 2020-05-19: QA; 2020-05-26: PMv(approve); 2020-06-02: BU; 2020-06-09: eC/AD
P520,P520c 5.0 wave2 |  | Refresh | houce1 | #N/A | 2020-06-16 | Yes | 2020-04-28: PM/Final/CV Long; 2020-05-05: Data/BOM Final; 2020-05-12: Mod/EOW; 2020-05-19: Mod; 2020-05-26: QA; 2020-06-02: PMv(approve); 2020-06-09: BU; 2020-06-16: eC/AD
P720,P920c 5.0 wave2 |  | Refresh | lizj22 | #N/A | 2020-06-16 | Yes | 2020-04-28: PM/Final/CV Long; 2020-05-05: Data/BOM Final; 2020-05-12: Mod/EOW; 2020-05-19: Mod; 2020-05-26: QA; 2020-06-02: PMv(approve); 2020-06-09: BU; 2020-06-16: eC/AD
P340 Tower |  | New Launch | houce1 | 2020-05-26 | 2020-06-30 | Yes | 2020-03-10: Tech Spec/CSR Release; 2020-03-17: SBB maintain; 2020-03-24: SBB maintain; 2020-03-31: SBB DRR; 2020-04-07: SBB Review/Final; 2020-04-14: MKT Spec/POR Release; 2020-04-21: MTM Maintain; 2020-04-28: MTM DRR; 2020-05-05: MTM Review/Final; 2020-05-12: PM/Final/CV Long; 2020-05-19: Data/BOM Final; 2020-05-26: Mod/EOW; 2020-06-02: Mod; 2020-06-09: QA; 2020-06-16: PMv(approve); 2020-06-23: BU; 2020-06-30: eC/AD
P340 SFF | 30DK | New Launch | guorp2 | 2020-05-26 | 2020-06-30 | Yes | 2020-03-10: Tech Spec/CSR Release; 2020-03-17: SBB maintain; 2020-03-24: SBB maintain; 2020-03-31: SBB DRR; 2020-04-07: SBB Review/Final; 2020-04-14: MKT Spec/POR Release; 2020-04-21: MTM Maintain; 2020-04-28: MTM DRR; 2020-05-05: MTM Review/Final; 2020-05-12: PM/Final/CV Long; 2020-05-19: Data/BOM Final; 2020-05-26: Mod/EOW; 2020-06-02: Mod; 2020-06-09: QA; 2020-06-16: PMv(approve); 2020-06-23: BU; 2020-06-30: eC/AD
Lenovo V50s-07IMB | 11EE | New Launch | lizj22 | 2020-06-02 | 2020-07-10 | Yes | 2020-03-17: Tech Spec/CSR Release; 2020-03-24: SBB maintain; 2020-03-31: SBB maintain; 2020-04-07: SBB DRR; 2020-04-14: SBB Review/Final; 2020-04-21: MKT Spec/POR Release; 2020-04-28: MTM Maintain; 2020-05-05: MTM DRR; 2020-05-12: MTM Review/Final; 2020-05-19: PM/Final/CV Long; 2020-05-26: Data/BOM Final; 2020-06-02: Mod/EOW; 2020-06-09: Mod; 2020-06-16: QA; 2020-06-23: PMv(approve); 2020-06-30: BU; 2020-07-07: eC/AD
IdeaCentre C5 14IMB05 |  | New Launch | qinn1 | 2020-05-15 | 2020-07-10 | No | 2020-03-17: Tech Spec/CSR Release; 2020-03-24: SBB maintain; 2020-03-31: SBB maintain; 2020-04-07: SBB DRR; 2020-04-14: SBB Review/Final; 2020-04-21: MKT Spec/POR Release; 2020-04-28: MTM Maintain; 2020-05-05: MTM DRR; 2020-05-12: MTM Review/Final/EOW
IdeaCentre Mini 5 01IMH05 | 90Q6 | New Launch | lizj22 | 2020-06-05 | 2020-07-31 | No | 2020-04-07: Tech Spec/CSR Release; 2020-04-14: SBB maintain; 2020-04-21: SBB maintain; 2020-04-28: SBB DRR; 2020-05-05: SBB Review/Final; 2020-05-12: MKT Spec/POR Release; 2020-05-19: MTM Maintain; 2020-05-26: MTM DRR; 2020-06-02: MTM Review/Final/EOW
IdeaCentre G5 14AMR05 | 90Q0 | New Launch | guorp2 | 2020-06-12 | 2020-08-07 | Yes | 2020-04-14: Tech Spec/CSR Release; 2020-04-21: SBB maintain; 2020-04-28: SBB maintain; 2020-05-05: SBB DRR; 2020-05-12: SBB Review/Final; 2020-05-19: MKT Spec/POR Release; 2020-05-26: MTM Maintain; 2020-06-02: MTM DRR; 2020-06-09: MTM Review/Final/EOW; 2020-06-16: PM/Final/CV Long; 2020-06-23: Data/BOM Final; 2020-06-30: Mod/EOW; 2020-07-07: Mod; 2020-07-14: QA; 2020-07-21: PMv(approve); 2020-07-28: BU; 2020-08-04: eC/AD
IdeaCentre 5 14ARE05 | 90Q2 | New Launch | houce1 | 2020-06-12 | 2020-08-07 | No | 2020-04-14: Tech Spec/CSR Release; 2020-04-21: SBB maintain; 2020-04-28: SBB maintain; 2020-05-05: SBB DRR; 2020-05-12: SBB Review/Final; 2020-05-19: MKT Spec/POR Release; 2020-05-26: MTM Maintain; 2020-06-02: MTM DRR; 2020-06-09: MTM Review/Final/EOW
Lenovo Legion T5 26AMR5 ES | 90RB | New Launch | guorp2 | 2020-06-18 | 2020-08-13 | No | 2020-04-21: Tech Spec/CSR Release; 2020-04-28: SBB maintain; 2020-05-05: SBB maintain; 2020-05-12: SBB DRR; 2020-05-19: SBB Review/Final; 2020-05-26: MKT Spec/POR Release; 2020-06-02: MTM Maintain; 2020-06-09: MTM DRR; 2020-06-16: MTM Review/Final/EOW
Lenovo Legion T5 26AMR5 Non ES | 90RC | New Launch | guorp2 | 2020-06-18 | 2020-08-13 | No | 2020-04-21: Tech Spec/CSR Release; 2020-04-28: SBB maintain; 2020-05-05: SBB maintain; 2020-05-12: SBB DRR; 2020-05-19: SBB Review/Final; 2020-05-26: MKT Spec/POR Release; 2020-06-02: MTM Maintain; 2020-06-09: MTM DRR; 2020-06-16: MTM Review/Final/EOW
M70c |  | New Launch | lizj22 | 2020-07-21 | 2020-08-28 | Yes | 2020-05-05: Tech Spec/CSR Release; 2020-05-12: SBB maintain; 2020-05-19: SBB maintain; 2020-05-26: SBB DRR; 2020-06-02: SBB Review/Final; 2020-06-09: MKT Spec/POR Release; 2020-06-16: MTM Maintain; 2020-06-23: MTM DRR; 2020-06-30: MTM Review/Final; 2020-07-07: PM/Final/CV Long; 2020-07-14: Data/BOM Final; 2020-07-21: Mod/EOW; 2020-07-28: Mod; 2020-08-04: QA; 2020-08-11: PMv(approve); 2020-08-18: BU; 2020-08-25: eC/AD
P720, P920 7.0 |  | Refresh | lizj22 | #N/A | 2020-09-01 | Yes | 2020-07-14: PM/Final/CV Long; 2020-07-21: Data/BOM Final; 2020-07-28: Mod/EOW; 2020-08-04: Mod; 2020-08-11: QA; 2020-08-18: PMv(approve); 2020-08-25: BU; 2020-09-01: eC/AD
P520,P520c 7.0 |  | Refresh | houce1 | #N/A | 2020-09-01 | Yes | 2020-07-14: PM/Final/CV Long; 2020-07-21: Data/BOM Final; 2020-07-28: Mod/EOW; 2020-08-04: Mod; 2020-08-11: QA; 2020-08-18: PMv(approve); 2020-08-25: BU; 2020-09-01: eC/AD
P620 | 30E0 | New Launch | qinn1 | 2020-08-24 | 2020-09-04 | Yes | 2020-05-12: Tech Spec/CSR Release; 2020-05-19: SBB maintain; 2020-05-26: SBB maintain; 2020-06-02: SBB DRR; 2020-06-09: SBB Review/Final; 2020-06-16: MKT Spec/POR Release; 2020-06-23: MTM Maintain; 2020-06-30: MTM DRR; 2020-07-07: MTM Review/Final/EOW; 2020-07-14: PM/Final/CV Long; 2020-07-21: Data/BOM Final; 2020-07-28: Mod/EOW; 2020-08-04: Mod; 2020-08-11: QA; 2020-08-18: PMv(approve); 2020-08-25: BU; 2020-09-01: eC/AD
Hub T | 11H0 | New Launch | guorp2 | 2020-09-15 | 2020-09-15 | Yes | 2020-07-21: Tech Spec/CSR Release; 2020-07-28: SBB maintain; 2020-08-04: SBB maintain; 2020-08-11: SBB DRR; 2020-08-18: SBB Review/Final; 2020-08-25: MKT Spec/POR Release; 2020-09-01: MTM Maintain; 2020-09-08: MTM DRR; 2020-09-15: MTM Review/Final
Hub Z | 11H2 | New Launch | guorp2 | 2020-09-15 | 2020-09-15 | Yes | 2020-07-21: Tech Spec/CSR Release; 2020-07-28: SBB maintain; 2020-08-04: SBB maintain; 2020-08-11: SBB DRR; 2020-08-18: SBB Review/Final; 2020-08-25: MKT Spec/POR Release; 2020-09-01: MTM Maintain; 2020-09-08: MTM DRR; 2020-09-15: MTM Review/Final
IdeaCentre AIO 3 22IIL5 | F0FQ | New Launch | guorp2 | 2020-08-21 | 2020-10-16 | No | 2020-06-23: Tech Spec/CSR Release; 2020-06-30: SBB maintain; 2020-07-07: SBB maintain; 2020-07-14: SBB DRR; 2020-07-21: SBB Review/Final; 2020-07-28: MKT Spec/POR Release; 2020-08-04: MTM Maintain; 2020-08-11: MTM DRR; 2020-08-18: MTM Review/Final
IdeaCentre AIO 3 24IIL5 | F0FR | New Launch | qinn1 | 2020-08-21 | 2020-10-16 | No | 2020-06-23: Tech Spec/CSR Release; 2020-06-30: SBB maintain; 2020-07-07: SBB maintain; 2020-07-14: SBB DRR; 2020-07-21: SBB Review/Final; 2020-07-28: MKT Spec/POR Release; 2020-08-04: MTM Maintain; 2020-08-11: MTM DRR; 2020-08-18: MTM Review/Final
Lenovo V30a 22IIL | 11LA | New Launch | houce1 | 2020-09-11 | 2020-10-16 | No | 2020-07-14: Tech Spec/CSR Release; 2020-07-21: SBB maintain; 2020-07-28: SBB maintain; 2020-08-04: SBB DRR; 2020-08-11: SBB Review/Final; 2020-08-18: MKT Spec/POR Release; 2020-08-25: MTM Maintain; 2020-09-01: MTM DRR; 2020-09-08: MTM Review/Final
Lenovo V30a 24IIL | 11LC | New Launch | qinn1 | 2020-09-11 | 2020-10-16 | No | 2020-07-14: Tech Spec/CSR Release; 2020-07-21: SBB maintain; 2020-07-28: SBB maintain; 2020-08-04: SBB DRR; 2020-08-11: SBB Review/Final; 2020-08-18: MKT Spec/POR Release; 2020-08-25: MTM Maintain; 2020-09-01: MTM DRR; 2020-09-08: MTM Review/Final
M75t Gen 2 |  | New Launch | houce1 | 2020-09-15 | 2020-10-20 | Yes | 2020-06-30: Tech Spec/CSR Release; 2020-07-07: SBB maintain; 2020-07-14: SBB maintain; 2020-07-21: SBB DRR; 2020-07-28: SBB Review/Final; 2020-08-04: MKT Spec/POR Release; 2020-08-11: MTM Maintain; 2020-08-18: MTM DRR; 2020-08-25: MTM Review/Final; 2020-09-01: PM/Final/CV Long; 2020-09-08: Data/BOM Final; 2020-09-15: Mod/EOW; 2020-09-22: Mod; 2020-09-29: QA; 2020-10-06: PMv(approve); 2020-10-13: BU; 2020-10-20: eC/AD
M75s Gen 2 |  | New Launch | houce1 | 2020-09-15 | 2020-10-20 | Yes | 2020-06-30: Tech Spec/CSR Release; 2020-07-07: SBB maintain; 2020-07-14: SBB maintain; 2020-07-21: SBB DRR; 2020-07-28: SBB Review/Final; 2020-08-04: MKT Spec/POR Release; 2020-08-11: MTM Maintain; 2020-08-18: MTM DRR; 2020-08-25: MTM Review/Final; 2020-09-01: PM/Final/CV Long; 2020-09-08: Data/BOM Final; 2020-09-15: Mod/EOW; 2020-09-22: Mod; 2020-09-29: QA; 2020-10-06: PMv(approve); 2020-10-13: BU; 2020-10-20: eC/AD
M75q Gen2 |  | New Launch | lizj22 | 2020-09-22 | 2020-10-29 | Yes | 2020-07-07: Tech Spec/CSR Release; 2020-07-14: SBB maintain; 2020-07-21: SBB maintain; 2020-07-28: SBB DRR; 2020-08-04: SBB Review/Final; 2020-08-11: MKT Spec/POR Release; 2020-08-18: MTM Maintain; 2020-08-25: MTM DRR; 2020-09-01: MTM Review/Final; 2020-09-08: PM/Final/CV Long; 2020-09-15: Data/BOM Final; 2020-09-22: Mod/EOW; 2020-09-29: Mod; 2020-10-06: QA; 2020-10-13: PMv(approve); 2020-10-20: BU; 2020-10-27: eC/AD
Lenovo V55t-15ARE | 11KF | New Launch | lizj22 | 2020-10-16 | 2020-11-20 | Yes | 2020-06-09: Tech Spec/CSR Release; 2020-06-16: SBB maintain; 2020-06-23: SBB maintain; 2020-06-30: SBB DRR; 2020-07-07: SBB Review/Final; 2020-07-14: MKT Spec/POR Release; 2020-07-21: MTM Maintain; 2020-07-28: MTM DRR; 2020-08-04: MTM Review/Final; 2020-08-11: PM/Final/CV Long; 2020-08-18: Data/BOM Final; 2020-08-25: Mod/EOW; 2020-09-01: Mod; 2020-09-08: QA; 2020-09-15: PMv(approve); 2020-09-22: BU; 2020-09-29: eC/AD
M60e | 11LU | New Launch | guorp2 | 2020-12-25 | 2021-01-29 | No | 2020-10-27: Tech Spec/CSR Release; 2020-11-03: SBB maintain; 2020-11-10: SBB maintain; 2020-11-17: SBB DRR; 2020-11-24: SBB Review/Final; 2020-12-01: MKT Spec/POR Release; 2020-12-08: MTM Maintain; 2020-12-15: MTM DRR; 2020-12-22: MTM Review/Final
Lenovo Legion T5 26IOB6 |  | New Launch | houce1 | 2021-01-25 | 2021-03-22 | No | 2020-12-01: Tech Spec/CSR Release; 2020-12-08: SBB maintain; 2020-12-15: SBB maintain; 2020-12-22: SBB DRR; 2020-12-29: SBB Review/Final; 2021-01-05: MKT Spec/POR Release; 2021-01-12: MTM Maintain; 2021-01-19: MTM DRR; 2021-01-26: MTM Review/Final
IdeaCentre Gaming5 14IOB6 |  | New Launch | houce1 | 2021-02-03 | 2021-03-31 | No | 2020-12-08: Tech Spec/CSR Release; 2020-12-15: SBB maintain; 2020-12-22: SBB maintain; 2020-12-29: SBB DRR; 2021-01-05: SBB Review/Final; 2021-01-12: MKT Spec/POR Release; 2021-01-19: MTM Maintain; 2021-01-26: MTM DRR; 2021-02-02: MTM Review/Final
IC Creator 5 14IOB6 |  | New Launch | lizj22 | 2021-02-03 | 2021-03-31 | No | 2020-12-08: Tech Spec/CSR Release; 2020-12-15: SBB maintain; 2020-12-22: SBB maintain; 2020-12-29: SBB DRR; 2021-01-05: SBB Review/Final; 2021-01-12: MKT Spec/POR Release; 2021-01-19: MTM Maintain; 2021-01-26: MTM DRR; 2021-02-02: MTM Review/Final
IdeaCentre 5 14IOB6 |  | New Launch | qinn1 | 2021-02-03 | 2021-03-31 | No | 2020-12-08: Tech Spec/CSR Release; 2020-12-15: SBB maintain; 2020-12-22: SBB maintain; 2020-12-29: SBB DRR; 2021-01-05: SBB Review/Final; 2021-01-12: MKT Spec/POR Release; 2021-01-19: MTM Maintain; 2021-01-26: MTM DRR; 2021-02-02: MTM Review/Final
M90n Gen 2 | 11NA | New Launch | qinn1 | 2021-02-23 | 2021-03-31 | Yes | 2020-12-08: Tech Spec/CSR Release; 2020-12-15: SBB maintain; 2020-12-22: SBB maintain; 2020-12-29: SBB DRR; 2021-01-05: SBB Review/Final; 2021-01-12: MKT Spec/POR Release; 2021-01-19: MTM Maintain; 2021-01-26: MTM DRR; 2021-02-02: MTM Review/Final/EOW; 2021-02-09: PM/Final/CV Long; 2021-02-16: Data/BOM Final; 2021-02-23: Mod/EOW; 2021-03-02: Mod; 2021-03-09: QA; 2021-03-16: PMv(approve); 2021-03-23: BU; 2021-03-30: eC/AD
M70a Gen 2 |  | New Launch | houce1 | 2021-03-23 | 2021-04-27 | Yes | 2021-01-05: Tech Spec/CSR Release; 2021-01-12: SBB maintain; 2021-01-19: SBB maintain; 2021-01-26: SBB DRR; 2021-02-02: SBB Review/Final; 2021-02-09: MKT Spec/POR Release; 2021-02-16: MTM Maintain; 2021-02-23: MTM DRR; 2021-03-02: MTM Review/Final; 2021-03-09: PM/Final/CV Long; 2021-03-16: Data/BOM Final; 2021-03-23: Mod/EOW; 2021-03-30: Mod; 2021-04-06: QA; 2021-04-13: PMv(approve); 2021-04-20: BU; 2021-04-27: eC/AD
M70t Gen 2 |  | New Launch | lizj22 | 2021-03-23 | 2021-04-27 | Yes | 2021-01-05: Tech Spec/CSR Release; 2021-01-12: SBB maintain; 2021-01-19: SBB maintain; 2021-01-26: SBB DRR; 2021-02-02: SBB Review/Final; 2021-02-09: MKT Spec/POR Release; 2021-02-16: MTM Maintain; 2021-02-23: MTM DRR; 2021-03-02: MTM Review/Final; 2021-03-09: PM/Final/CV Long; 2021-03-16: Data/BOM Final; 2021-03-23: Mod/EOW; 2021-03-30: Mod; 2021-04-06: QA; 2021-04-13: PMv(approve); 2021-04-20: BU; 2021-04-27: eC/AD
M70s Gen 2 |  | New Launch | lizj22 | 2021-03-23 | 2021-04-27 | Yes | 2021-01-05: Tech Spec/CSR Release; 2021-01-12: SBB maintain; 2021-01-19: SBB maintain; 2021-01-26: SBB DRR; 2021-02-02: SBB Review/Final; 2021-02-09: MKT Spec/POR Release; 2021-02-16: MTM Maintain; 2021-02-23: MTM DRR; 2021-03-02: MTM Review/Final; 2021-03-09: PM/Final/CV Long; 2021-03-16: Data/BOM Final; 2021-03-23: Mod/EOW; 2021-03-30: Mod; 2021-04-06: QA; 2021-04-13: PMv(approve); 2021-04-20: BU; 2021-04-27: eC/AD
M70q Gen 2 | 11MQ | New Launch | guorp2 | 2021-03-23 | 2021-04-27 | Yes | 2021-01-05: Tech Spec/CSR Release; 2021-01-12: SBB maintain; 2021-01-19: SBB maintain; 2021-01-26: SBB DRR; 2021-02-02: SBB Review/Final; 2021-02-09: MKT Spec/POR Release; 2021-02-16: MTM Maintain; 2021-02-23: MTM DRR; 2021-03-02: MTM Review/Final/EOW; 2021-03-09: PM/Final/CV Long; 2021-03-16: Data/BOM Final; 2021-03-23: Mod/EOW; 2021-03-30: Mod; 2021-04-06: QA; 2021-04-13: PMv(approve); 2021-04-20: BU; 2021-04-27: eC/AD
M90q Gen 2 | 11MY | New Launch | guorp2 | 2021-04-13 | 2021-05-18 | Yes | 2021-01-26: Tech Spec/CSR Release; 2021-02-02: SBB maintain; 2021-02-09: SBB maintain; 2021-02-16: SBB DRR; 2021-02-23: SBB Review/Final; 2021-03-02: MKT Spec/POR Release; 2021-03-09: MTM Maintain; 2021-03-16: MTM DRR; 2021-03-23: MTM Review/Final/EOW; 2021-03-30: PM/Final/CV Long; 2021-04-06: Data/BOM Final; 2021-04-13: Mod/EOW; 2021-04-20: Mod; 2021-04-27: QA; 2021-05-04: PMv(approve); 2021-05-11: BU; 2021-05-18: eC/AD
M90a Gen 2 |  | New Launch | houce1 | 2021-04-13 | 2021-05-20 | Yes | 2021-01-26: Tech Spec/CSR Release; 2021-02-02: SBB maintain; 2021-02-09: SBB maintain; 2021-02-16: SBB DRR; 2021-02-23: SBB Review/Final; 2021-03-02: MKT Spec/POR Release; 2021-03-09: MTM Maintain; 2021-03-16: MTM DRR; 2021-03-23: MTM Review/Final; 2021-03-30: PM/Final/CV Long; 2021-04-06: Data/BOM Final; 2021-04-13: Mod/EOW; 2021-04-20: Mod; 2021-04-27: QA; 2021-05-04: PMv(approve); 2021-05-11: BU; 2021-05-18: eC/AD
M90t Gen 2 |  | New Launch | qinn1 | 2021-04-20 | 2021-05-25 | Yes | 2021-02-02: Tech Spec/CSR Release; 2021-02-09: SBB maintain; 2021-02-16: SBB maintain; 2021-02-23: SBB DRR; 2021-03-02: SBB Review/Final; 2021-03-09: MKT Spec/POR Release; 2021-03-16: MTM Maintain; 2021-03-23: MTM DRR; 2021-03-30: MTM Review/Final/EOW; 2021-04-06: PM/Final/CV Long; 2021-04-13: Data/BOM Final; 2021-04-20: Mod/EOW; 2021-04-27: Mod; 2021-05-04: QA; 2021-05-11: PMv(approve); 2021-05-18: BU; 2021-05-25: eC/AD
M90s Gen 2 |  | New Launch | qinn1 | 2021-04-20 | 2021-05-25 | Yes | 2021-02-02: Tech Spec/CSR Release; 2021-02-09: SBB maintain; 2021-02-16: SBB maintain; 2021-02-23: SBB DRR; 2021-03-02: SBB Review/Final; 2021-03-09: MKT Spec/POR Release; 2021-03-16: MTM Maintain; 2021-03-23: MTM DRR; 2021-03-30: MTM Review/Final/EOW; 2021-04-06: PM/Final/CV Long; 2021-04-13: Data/BOM Final; 2021-04-20: Mod/EOW; 2021-04-27: Mod; 2021-05-04: QA; 2021-05-11: PMv(approve); 2021-05-18: BU; 2021-05-25: eC/AD
Note on B1: Runpeng RP2 Guo: This CTO do not include all CTO numbers just for reference
Note on L1: Peng Peng11 Zhang: 春节

## EOL List
Remark | Note | PROJECT | Sub-Series Name | CTO # | Product Category | Brand | Segment | Planner | Launch Type | EOW | AD | Web CTO AD | IAD | Enable Web CTO | Status | EOL
|  | Wolverine | TS150 (WW) TS250 (PRC) |  | Think Server |  |  | Jenncy Yu35 Zhang | New Launch | 2015-11-03 | 2015-12-01 |  |  |  | Completed
|  | Thor | TS450 (WW) TS550 (PRC) |  | Think Server |  |  | Jenncy Yu35 Zhang | New Launch | 2015-11-03 | 2015-12-01 |  |  |  | Completed
|  | Motuo_M7 | M700z |  | Think DT |  |  | Xue Xue7 Chen | New Launch | 2015-11-10 | 2015-12-15 |  |  |  | Completed | #N/A
|  | Motuo_M8 | M800z |  | Think DT |  |  | Astrid Jing12 Zhao | New Launch | 2015-10-13 | 2015-11-17 |  |  |  | Completed | #N/A
|  | Motuo_P9 | M900z |  | Think DT |  |  | Astrid Jing12 Zhao | New Launch | 2015-10-06 | 2015-11-10 |  |  |  | Completed | #N/A
|  | Perth_M | M900 (TWR & SFF & Tiny) |  | Think DT |  |  | Kristy CR1 E | New Launch | 2015-10-13 | 2015-11-10 |  |  |  | Completed | #N/A
|  | Provence_M | M800 |  | Think DT |  |  | Hua Hua7 Chen | New Launch | 2015-10-13 | 2015-11-10 |  |  |  | Completed | #N/A
|  | Enfield _M | M600 |  | Think DT |  |  | Kevin ZJ9 Liu | New Launch | 2015-09-15 | 2015-10-20 |  |  |  | Completed | #N/A
|  | Enfield_S | Lenovo S200 |  | Think DT |  |  | Yanna1 Kang | New Launch | 2015-10-13 | 2015-11-10 |  |  |  | Completed | #N/A
|  | Seattle_E2 | Lenovo S200z |  | Think DT |  |  | Lynn Ling2 He | New Launch | 2015-08-18 | 2015-09-22 |  |  |  | Completed | #N/A
|  | Seattle_E4 | Lenovo S400z |  | Think DT |  |  | Lynn Ling2 He | New Launch | 2015-09-15 | 2015-10-20 |  |  |  | Completed | #N/A
|  | Seattle_M5 | Lenovo S500z |  | Think DT |  |  | Lynn Ling2 He | New Launch | 2015-09-15 | 2015-10-20 |  |  |  | Completed | #N/A
|  | Mars_S | Lenovo S500 |  | Think DT |  |  | MingXiu Xiang | New Launch | 2015-07-28 | 2015-08-25 |  |  |  | Completed | #N/A
|  | Alaska_GVR | M79 |  | Think DT |  |  | Yue Yue2 Yan | New Launch | NA | 2015-09-29 |  |  |  | Completed | #N/A
|  | Chaozhou_GVR | E79 |  | Think DT |  |  | Yue Yue2 Yan | New Launch | NA | 2015-09-29 |  |  |  | Completed | #N/A
|  | Seattle_D4 | Lenovo S405z |  | Think DT |  |  | Lynn Ling2 He | New Launch | 2015-09-18 | 2015-10-27 |  |  |  | Completed | #N/A
|  | Paris Havana (TWR & SFF) | P310 |  | Think Station |  |  | Maura Xu12 Wang | New Launch | 2015-11-10 | 2015-11-24 |  |  |  | Completed | #N/A
|  | AIO 700-27ISH | F0BDCTO1WW | F0BD | Lenovo DT |  |  | Miaomiao MM13 Wang | New Launch | 2015-07-27 | 2015-09-21 |  |  |  | Completed
|  | AIO 700-24ISH | F0BECTO1WW | F0BE | Lenovo DT |  |  | Miaomiao MM13 Wang | New Launch | 2015-07-20 | 2015-09-14 |  |  |  | Completed
|  | AIO 700-22ISH | F0BFCTO1WW | F0BF | Lenovo DT |  |  | Miaomiao MM13 Wang | New Launch | 2015-09-21 | 2015-11-16 |  |  |  | Completed
|  | AIO 700-24AGR | F0BGCTO1WW | F0BG | Lenovo DT |  |  | Miaomiao MM13 Wang | New Launch | 2015-07-06 | 2015-09-02 |  |  |  | Completed
|  | C20-00 | F0BBCTO1WW | F0BB | Lenovo DT |  |  | Tracy MO1 Wang | New Launch | 2015-07-29 | 2015-09-22 |  |  |  | Completed
|  | AIO 300-23ACL | F0BCCTO1WW | F0BC | Lenovo DT |  |  | Tracy MO1 Wang | New Launch | 2015-09-03 | 2015-11-05 |  |  |  | Completed
|  | ideacentre 300-20IBR | 90DNCTO1WW | 90DN | Lenovo DT |  |  | Yanna1 Kang | New Launch | 2015-09-04 | 2015-10-30 |  |  |  | Completed
|  | ideacentre 300S-11IBR | 90DQCTO1WW | 90DQ | Lenovo DT |  |  | Yanna1 Kang | New Launch | 2015-09-04 | 2015-10-30 |  |  |  | Completed
|  | 300-20ISH | 90DACTO1WW | 90DA | Lenovo DT |  |  | MingXiu Xiang | New Launch | 2015-08-28 | 2015-10-23 |  |  |  | Completed
|  | 300S-11ISH | 90D9CTO1WW | 90D9 | Lenovo DT |  |  | MingXiu Xiang | New Launch | 2015-08-28 | 2015-10-23 |  |  |  | Completed
|  | ideacentre Y900-34ISZ | 90DDCTO1WW 90FWCTO1WW 90FXCTO1WW | 90DD 90FW 90FX | Lenovo DT |  |  | Rainbow LL9 Liu | New Launch | 2015-07-31 | 2015-09-25 |  |  |  | Completed
|  | ideacentre Y700-34ISH | 90DGCTO1WW | 90DG | Lenovo DT |  |  | Rainbow LL9 Liu | New Launch | 2015-08-17 | 2015-10-12 |  |  |  | Completed
|  | ideacentre Y700-34ISH | 90DFCTO1WW | 90DF | Lenovo DT |  |  | Rainbow LL9 Liu | New Launch | 2015-08-17 | 2015-10-12 |  |  |  | Completed
|  | YOGA Home 900-27IBU | F0BMCTO1WW | F0BM | Lenovo DT |  |  | Miaomiao MM13 Wang | New Launch | 2015-06-16 | 2015-12-08 |  |  |  | Completed
|  | YOGA Home 500-22IBU | F0BNCTO1WW | F0BN | Lenovo DT |  |  | Miaomiao MM13 Wang | New Launch | 2015-06-25 | 2015-08-20 |  |  |  | Completed
|  | ideacentre AIO 300-20ISH | F0BVCTO1WW | F0BV | Lenovo DT |  |  | Tracy MO1 Wang | New Launch | 2015-09-24 | 2015-12-03 |  |  |  | Completed
|  | ideacentre AIO 300-22ACL | F0BWCTO1WW | F0BW | Lenovo DT |  |  | Tracy MO1 Wang | New Launch | 2015-09-03 | 2015-11-05 |  |  |  | Completed
|  | ideacentre AIO 300-22ISU | F0BXCTO1WW | F0BX | Lenovo DT |  |  | Tracy MO1 Wang | New Launch | 2015-09-03 | 2015-11-05 |  |  |  | Completed
|  | ideacentre AIO 300-23ISU | F0BYCTO1WW | F0BY | Lenovo DT |  |  | Tracy MO1 Wang | New Launch | 2015-09-03 | 2015-11-05 |  |  |  | Completed
|  | ideacentre 700-25ISH | 90EDCTO1WW | 90ED | Lenovo DT |  |  | Rainbow LL9 Liu | New Launch | 2015-07-29 | 2015-09-23 |  |  |  | Completed
|  | ideacentre 300S-08IHH | 90F1CTO1WW | 90F1 | Lenovo DT |  |  | MingXiu Xiang | New Launch | 2015-07-24 | 2015-09-18 |  |  |  | Completed
|  | ideacentre Stick 300-01IBY 2.0 | 90F2CTO1WW | 90F2 | Lenovo DT |  |  | Kexin Shi | New Launch | 2015-09-16 | 2015-09-30 |  |  |  | Completed
|  | Porto | M73p (TWR) |  | Think DT |  |  | Jerry Jing1 Jia | New Launch | 2015-08-11 | 2015-08-31 |  |  |  | Completed | #N/A
|  | ideacentre 200-01IBW | 90FACTO1WW | 90FA | Lenovo DT |  |  | Rainbow LL9 Liu | New Launch | 2015-08-21 | 2015-10-16 |  |  |  | Completed
|  | Mainz_M | M700 (Tiny) |  | Think DT |  |  | Kevin ZJ9 Liu | New Launch | 2015-12-15 | 2016-01-12 |  |  |  | Completed | #N/A
|  | Murray_M | M700 (TWR&SFF) |  | Think DT |  |  | MingXiu Xiang | New Launch | 2015-12-09 | 2016-01-12 |  |  |  | Completed | #N/A
|  | Maldives | X1 |  | Think DT |  |  | Astrid Jing12 Zhao | New Launch | 2015-12-22 | 2016-01-26 |  |  |  | Completed | #N/A
|  | Murray_C | E74/E74s |  | Think DT |  |  | MingXiu Xiang | New Launch | 2015-12-31 | 2016-02-02 |  |  |  | Completed | #N/A
|  | ideacentre 710-25ISH | 90FBCTO1WW |  | Lenovo DT |  |  | Rainbow LL9 Liu | New Launch | 2016-02-04 | 2016-03-31 |  |  |  | Completed
|  | Emei_M2 | E74z |  | Think DT |  |  | Hua Hua7 Chen | New Launch | 2016-02-16 | 2016-03-03 |  |  |  | Completed | #N/A
|  | Vancouver | P410 |  | Think Station |  |  | Maura Xu12 Wang | New Launch | 2016-04-19 | 2016-05-03 |  |  | Yes | Completed | #N/A
|  | Mikonos | P510 |  | Think Station |  |  | Stone XD8 Wang | New Launch | 2016-05-12 | 2016-06-14 |  |  | Yes | Completed | #N/A
|  | Feb Block--MLK | RD350_MLK/RD450_MLK/RD550_MLK/RD650_MLK & TD350 |  | Think Server |  |  | Lynn Jing10 Zhao | New Launch/ Refresh(TD350) | 2016-02-16 | 2016-04-01 |  |  |  | Completed
|  | Rome | P710 |  | Think Station |  |  | Stone XD8 Wang | New Launch | 2016-03-22 | 2016-04-05 |  |  | Yes | Completed | #N/A
|  | Shanghai | P910 |  | Think Station |  |  | Stone XD8 Wang | New Launch | 2016-03-22 | 2016-04-05 |  |  | Yes | Completed | #N/A
|  | ideacentre AIO 910-27ISH | F0C2CTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2015-02-18 | 2016-04-15 |  |  |  | Completed | #N/A
|  | V310-14ISK | 80SXCTO1WW |  | Commercial SMB |  |  | Jessica LY4 Zhu | New Launch | 2016-03-09 | 2016-04-15 |  |  |  | Completed | #N/A
|  | V310-15ISK | 80SYCTO1WW |  | Commercial SMB |  |  | Jessica LY4 Zhu | New Launch | 2016-03-09 | 2016-04-15 |  |  |  | Completed | #N/A
|  | Munich_S | Lenovo S510(TWR & SFF) |  | Commercial DT & SMB DT |  |  | MingXiu Xiang | New Launch | 2016-03-01 | 2016-04-05 |  |  |  | Completed | #N/A
|  | ideacentre 610S-02ISH | 90FCCTO1WW |  | Consumer DT |  |  | Rainbow LL9 Liu | New Launch | 2016-03-11 | 2016-05-06 |  |  |  | Completed | #N/A
|  | ideacentre AIO 510S-23ISU | F0C3CTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2016-03-02 | 2016-04-27 |  |  |  | Completed | #N/A
|  | V110-15ISK | 80TLCTO1WW |  | Commercial SMB |  |  | Ren Ren1 Xu | New Launch | 2016-04-28 | 2016-06-12 |  |  |  | Completed | #N/A
Tech Sepc updated on 7.21 |  | V110-14AST | 80TCCTO1WW |  | Commercial SMB |  |  | Ren Ren1 Xu | New Launch | 2016-07-29 | 2016-09-07 |  |  |  | Completed | #N/A
|  | Y900 RE-34ISZ | 90FKCTO1WW |  | Consumer DT |  |  | Rainbow LL9 Liu | New Launch | 2016-02-19 | 2016-04-15 |  |  |  | Completed | #N/A
Tech Sepc updated on 7.21 |  | V110-15AST | 80TDCTO1WW |  | Commercial SMB |  |  | Ren Ren1 Xu | New Launch | 2016-07-29 | 2016-09-07 |  |  |  | Completed | #N/A
|  | Plano | M900x |  | Commercial DT & SMB DT |  |  | Kevin ZJ9 Liu | New Launch | 2016-06-08 | 2016-06-21 |  |  |  | Completed | #N/A
|  | Dakota | M715q |  | Commercial DT & SMB DT |  |  | Kevin ZJ9 Liu | New Launch | 2016-09-16 | 2016-10-25 |  |  |  | Completed | #N/A
|  | ideacentre AIO 510-22ASR | F0CCCTO1WW |  | Consumer DT |  |  | Junjun JJ25 Liu | New Launch | 2016-05-19 | 2016-07-14 |  |  |  | Completed | #N/A
|  | ideacentre AIO 510-23ASR | F0CECTO1WW |  | Consumer DT |  |  | Junjun JJ25 Liu | New Launch | 2016-05-19 | 2016-07-14 |  |  |  | Completed | #N/A
|  | ideacentre AIO 510-22ISH | F0CBCTO1WW |  | Consumer DT |  |  | Junjun JJ25 Liu | New Launch | 2016-05-19 | 2016-07-14 |  |  |  | Completed | #N/A
|  | ideacentre AIO 510-23ISH | F0CDCTO1WW |  | Consumer DT |  |  | Junjun JJ25 Liu | New Launch | 2016-05-19 | 2016-07-14 |  |  |  | Completed | #N/A
|  | ideacentre Y710 Cube-15ISH | 90FLCTO1WW 90FMCTO1WW |  | Consumer DT |  |  | Rainbow LL9 Liu | New Launch | 2016-05-13 | 2016-07-08 |  |  |  | Completed | #N/A
Tech Spec updated on 11.23 |  | V310-14IKB | 80T2CTO1WW |  | Commercial SMB |  |  | Jessica LY4 Zhu | New Launch | 2016-07-07 | 2016-08-15 |  |  |  | Completed | #N/A
Tech Spec updated on 11.23 |  | V310-15IKB | 80T3CTO1WW |  | Commercial SMB |  |  | Jessica LY4 Zhu | New Launch | 2016-07-07 | 2016-08-15 |  |  |  | Completed | #N/A
|  | ideacentre AIO Y910-27ISH | F0CJCTO1WW |  | Consumer DT |  |  | Miaomiao MM13 Wang | New Launch | 2016-06-29 | 2016-08-24 |  |  |  | Completed | #N/A
|  | V110-14IAP | 80TFCTO1WW |  | Commercial SMB |  |  | Ren Ren1 Xu | New Launch | 2016-08-12 | 2016-09-23 |  |  |  | Completed | #N/A
|  | V110-15IAP | 80TGCTO1WW |  | Commercial SMB |  |  | Ren Ren1 Xu | New Launch | 2016-08-12 | 2016-09-23 |  |  |  | Completed | #N/A
|  | ideacentre 510s-08ISH | 90FNCTO1WW |  | Consumer DT |  |  | Ricky RC1 Liu | New Launch | 2016-03-31 | 2016-05-10 |  |  |  | Completed | #N/A
|  | Palau_M | M910t |  | Commercial DT & SMB DT |  |  | Xia Xia1 Yuan | New Launch | 2017-01-17 | 2017-02-21 |  |  |  | Completed | #N/A
|  | Palau_M | M910s |  | Commercial DT & SMB DT |  |  | Xia Xia1 Yuan | New Launch | 2017-01-17 | 2017-02-21 |  |  |  | Completed | #N/A
|  | Mofushi_M | M710t |  | Commercial DT & SMB DT |  |  | Hua Hua7 Chen | New Launch | 2017-01-17 | 2017-02-21 |  |  |  | Completed | #N/A
|  | Mofushi_M | M710s |  | Commercial DT & SMB DT |  |  | Hua Hua7 Chen | New Launch | 2017-01-17 | 2017-02-21 |  |  |  | Completed | #N/A
|  | ideacentre AIO 310-20ASR | F0CKCTO1WW |  | Consumer DT |  |  | Junjun JJ25 Liu | New Launch | 2016-09-12 | 2016-11-07 |  |  |  | Completed | #N/A
|  | ideacentre AIO 310-20IAP | F0CLCTO1WW |  | Consumer DT |  |  | Junjun JJ25 Liu | New Launch | 2016-09-12 | 2016-11-07 |  |  |  | Completed | #N/A
|  | V110-17IKB | 80V2CTO1WW |  | Commercial SMB |  |  | Jessica LY4 Zhu | New Launch | 2016-08-25 | 2016-09-30 |  |  |  | Completed | #N/A
|  | V110-17ISK | 80VMCTO1WW |  | Commercial SMB |  |  | Jessica LY4 Zhu | New Launch | 2016-12-08 | 2017-01-13 |  |  |  | Completed | #N/A
|  | Palau_M Tiny | M910q |  | Commercial DT & SMB DT |  |  | Jerry Jing1 Jia | New Launch | 2017-01-17 | 2017-02-21 |  |  |  | Completed | #N/A
|  | ideacentre 310-15ASR | 90G5CTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2016-11-28 | 2017-01-23 |  |  |  | Completed | #N/A
|  | ideacentre 310s-08ASR | 90G9CTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2016-11-28 | 2017-01-23 |  |  |  | Completed | #N/A
|  | ideacentre 310-15IAP | 90G6CTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2016-11-28 | 2017-01-23 |  |  |  | Completed | #N/A
|  | ideacentre 310s-08IAP | 90GACTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2016-11-28 | 2017-01-23 |  |  |  | Completed | #N/A
|  | ideacentre 510-15ABR | 90G7CTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2016-11-28 | 2017-01-23 |  |  |  | Completed | #N/A
|  | Ideacentre 510-15IKL | 90G8CTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2017-01-02 | 2017-02-27 |  |  |  | Completed | #N/A
|  | Ideacentre 510S-08IKL | 90GBCTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2017-01-02 | 2017-02-27 |  |  |  | Completed | #N/A
|  | Exeter_V | Lenovo V320-15IAP Desktop |  | Commercial DT & SMB DT |  |  | MingXiu Xiang | New Launch | 2016-12-13 | 2017-01-17 |  |  |  | Completed | #N/A
|  | ideacentre AIO 720-24IKB | F0CMCTO1WW |  | Consumer DT |  |  | Miaomiao MM13 Wang | New Launch | 2016-11-15 | 2017-01-10 |  |  |  | Completed | #N/A
|  | Mofushi_V | Lenovo V520-15IKL Desktop |  | Commercial DT & SMB DT |  |  | MingXiu Xiang | New Launch | 2017-01-31 | 2017-03-07 |  |  |  | Completed | #N/A
|  | Mofushi_V | Lenovo V520S-08IKL Desktop |  | Commercial DT & SMB DT |  |  | MingXiu Xiang | New Launch | 2017-01-31 | 2017-03-07 |  |  |  | Completed | #N/A
|  | Sydney_M5 | Lenovo V510z |  | Commercial DT & SMB DT |  |  | Astrid Jing12 Zhao | New Launch | 2016-10-04 | 2016-10-11 |  |  |  | Completed | #N/A
Wave 1 |  | Riddler | RS160 |  | Think Server |  |  | Wenjie WJ8 Zhang | New Launch | 2016-08-16 | 2016-09-13 |  |  |  | Completed
Wave 2 |  | Riddler | RS160 |  | Think Server |  |  | Wenjie WJ8 Zhang | New Launch | - | 2017-02-14 |  |  |  | Completed
|  | Macao_M8 | M810z |  | Commercial DT & SMB DT |  |  | Ian Yuan11 Yao | New Launch | 2017-01-09 | 2017-03-07 |  |  |  | Completed | #N/A
| For PRC Only | Macao_M8C | M810z |  | Commercial DT & SMB DT |  |  | Ian Yuan11 Yao | New Launch | - | 2017-02-28 |  |  |  | Completed | #N/A
|  | Macao_P9 | M910z |  | Commercial DT & SMB DT |  |  | Ian Yuan11 Yao | New Launch | 2017-01-24 | 2017-02-28 |  |  |  | Completed | #N/A
| For PRC Only | Macao_P9C | M910z |  | Commercial DT & SMB DT |  |  | Ian Yuan11 Yao | New Launch | - | 2017-02-28 |  |  |  | Completed | #N/A
|  | V510-14IKB | 80WRCTO1WW |  | Commercial SMB |  |  | Ren Ren1 Xu | New Launch | 2016-07-26 | 2016-09-12 |  |  |  | Completed | #N/A
|  | V510-15IKB | 80WQCTO1WW |  | Commercial SMB |  |  | Ren Ren1 Xu | New Launch | 2016-07-26 | 2016-09-06 |  |  |  | Completed | #N/A
|  | WildThing | TS460 |  | Think Server |  |  | Wenjie WJ8 Zhang | New Launch | 2017-01-20 | 2017-02-21 |  |  |  | Completed
|  | ideacentre 310A-15ASR | 90GSCTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2017-01-12 | 2017-03-09 |  |  |  | Completed | #N/A
|  | ideacentre 510A-15ABR | 90GUCTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2017-01-12 | 2017-03-09 |  |  |  | Completed | #N/A
|  | ideacentre 310A-15IAP | 90GTCTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2017-01-12 | 2017-03-09 |  |  |  | Completed | #N/A
|  | Ideacentre 510A-15IKL | 90GVCTO1WW |  | Consumer DT |  |  | Tracy MO1 Wang | New Launch | 2017-01-12 | 2017-03-09 |  |  |  | Completed | #N/A
|  | Sydney_E3 | Lenovo V310z |  | Commercial DT & SMB DT |  |  | Astrid Jing12 Zhao | New Launch | 2017-03-07 | 2017-03-21 |  |  |  | Completed | #N/A
|  | ideacentre Y720 Cube-15ISH ES | 90H2CTO1WW | 90H2 | Consumer DT |  |  | Rainbow LL9 Liu | New Launch | 2016-11-28 | 2017-01-23 |  |  |  | Completed | #N/A
|  | ideacentre Y720 Cube-15ISH Non ES | 90H3CTO1WW | 90H3 | Consumer DT |  |  | Rainbow LL9 Liu | New Launch | 2016-11-28 | 2017-01-23 |  |  |  | Completed | #N/A
|  | ideacentre AIO 520S-23IKU | F0CUCTO1WW | F0CU | Consumer DT |  |  | Miaomiao MM13 Wang | New Launch | 2016-12-21 | 2017-02-15 |  |  |  | Completed | #N/A
Tech Spec released on 5.24. MKT Spec released on 8.29 |  | Jordan | P920 | 30BC 30BD | DT Workstation_Commercial | ThinkStation | Commercial WS | Maura Xu12 Wang | New Launch | 2017-09-15 | 2017-09-26 | 2017-10-31 |  | Yes | Completed
Tech Spec released on 5.24. MKT Spec released on 8.29 |  | Magic | P720 | 30BA 30BB | DT Workstation_Commercial | ThinkStation | Commercial WS | Maura Xu12 Wang | New Launch | 2017-09-15 | 2017-09-26 | 2017-10-31 |  | Yes | Completed
MKT Spec released on 4.13 |  | Dakar_M | M715t | 10MD 10ME | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | New Launch | 2017-05-23 | 2017-06-27 | 2017-06-27 |  | Yes | Completed | 2019-03-31
MKT Spec released on 4.13 |  | Dakar_M | M715s | 11MB 11MC | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jason Peng14 Zhang | New Launch | 2017-05-23 | 2017-06-27 | 2017-06-27 |  | Yes | Completed | 2019-03-31
|  | Paros_M Tiny | M910x |  | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Jerry Jing1 Jia | New Launch | 2017-03-07 | 2017-04-11 | 2017-04-11 |  | Yes | Completed | EOLed
Tech Spec released on 4.7. MKT Spec released on 5.27 |  | Doha_V | Lenovo V525-15ABR Desktop | 10N7 10N8 | DT_SMB/Commercial/NEC | Lenovo | SMB | MingXiu Xiang | New Launch | 2017-06-13 | 2017-07-18 | 2017-07-18 |  | Yes | Completed | 2018-11-30
Tech Spec released on 7.25. MKT Spec released on 11.22 |  | Barkley | P520c | 30BX 30BY | DT Workstation_Commercial | ThinkStation | Commercial WS | Amanda Ling8 Li | New Launch | 2017-12-07 | 2018-01-25 | 2018-01-25 | 2017-10-27 | Yes | Completed
Tech Spec released on 7.25. MKT Spec released on 11.22 |  | Bird | P520 | 30BE 30BF | DT Workstation_Commercial | ThinkStation | Commercial WS | Amanda Ling8 Li | New Launch | 2017-12-07 | 2018-01-25 | 2018-01-25 | 2017-10-27 | Yes | Completed
Tech Spec released on 1.13. |  | ideacentre 720-18ASU | 90H1CTO1WW | 90H1 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu | New Launch | 2017-03-13 | 2017-05-08 | 2017-05-08 |  | No | Completed | 2018-09-30
Tech Spec released on 12.21, MKT Spec released on 1.9 |  | ideacentre 720-18IKL | 90H0CTO1WW | 90H0 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu | New Launch | 2017-02-13 | 2017-04-10 | 2017-04-10 |  | No | Completed | 2018-08-31
| ROW only | Lenovo Legion Y520 Tower-25IKL ES | 90H7CTO1WW | 90H7 | DT_Consumer | Lenovo | Consumer | Ricky RC1 Liu | New Launch | 2017-03-10 | 2017-05-05 | 2017-05-05 |  | No | Completed | 2018-06-30
Tech Spec released on 4.6. MKT Spec released on 5.3 |  | Lenovo Legion Y920 Tower-34IKZ | 90H4CTO1WW | 90H4 | DT_Consumer | Lenovo | Consumer | Rainbow LL9 Liu | New Launch | 2017-06-05 | 2017-07-31 | 2017-07-31 |  | No | Completed | 2018-09-30
Tech Spec released on 4.6. MKT Spec released on 5.3 |  | Lenovo Legion Y720 Tower-34IKH ES | 90H5CTO1WW | 90H5 | DT_Consumer | Lenovo | Consumer | Rainbow LL9 Liu | New Launch | 2017-06-05 | 2017-07-31 | 2017-07-31 |  | No | Completed | 2018-06-30
Tech Spec released on 4.6. MKT Spec released on 5.3 | No MTM submitted, temp not MTM DRR | Lenovo Legion Y720 Tower-34IKH Non-ES | 90H6CTO1WW | 90H6 | DT_Consumer | Lenovo | Consumer | Rainbow LL9 Liu | New Launch | 2017-06-05 | 2017-07-31 | 2017-07-31 |  | No | Completed | 2018-06-30
Tech Spec released on 4.6. MKT Spec released on 5.3 |  | Lenovo Legion Y720T-34ASU | 90H9CTO1WW | 90H9 | DT_Consumer | Lenovo | Consumer | Rainbow LL9 Liu | New Launch | 2017-06-05 | 2017-07-31 | 2017-07-31 |  | No | Completed | 2018-05-31
| MTM Only | Sydney_M4 | Lenovo V410z | 10QV 10QW 10R5 10R6 | DT_SMB/Commercial/NEC | Lenovo | SMB | Astrid Jing12 Zhao | New Launch | 2017-06-06 | 2017-06-27 | 2017-06-27 |  | No | Completed | 2018-12-31
Tech Spec released on 4.11. MKT Spec released on 5.12 |  | ideacentre AIO 520-22AST | F0D6CTO1WW | F0D6 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu | New Launch | 2017-05-29 | 2017-07-24 | 2017-07-24 |  | No | Completed | 2019-06-30
Tech Spec released on 4.25. MKT Spec released on 5.3 |  | ideacentre 620S-03IKL | 90HCCTO1WW | 90HC | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu | New Launch | 2017-06-05 | 2017-07-31 | 2017-07-31 |  | No | Completed | 2018-09-30
Tech Spec released on 4.11. MKT Spec released on 5.12 |  | ideacentre AIO 520-27IKL | F0D0CTO1WW | F0D0 | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu | New Launch | 2017-05-29 | 2017-07-24 | 2017-07-24 |  | No | Completed | 2018-09-30
Tech Spec released on 4.11.MKT Spec released on 5.12 |  | ideacentre AIO 520-24IKL | F0D1CTO1WW | F0D1 | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu | New Launch | 2017-05-29 | 2017-07-24 | 2017-07-24 |  | No | Completed | 2018-12-31
Tech Spec released on 4.11. MKT Spec released on 5.12 |  | ideacentre AIO 520-24AST | F0D3CTO1WW | F0D3 | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu | New Launch | 2017-05-29 | 2017-07-24 | 2017-07-24 |  | No | Completed | 2018-12-31
Tech Spec released on 4.11. MKT Spec released on 5.12 |  | ideacentre AIO 520-22IKL | F0D4CTO1WW | F0D4 | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu | New Launch | 2017-05-29 | 2017-07-24 | 2017-07-24 |  | No | Completed | 2019-03-31
|  | Dakota_M | M715q Thinclient |  | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Kevin ZJ9 Liu | New Launch | 2017-06-02 | 2017-07-04 | 2017-07-04 |  | Yes | Completed | EOLed
Tech Spec released on 5.5. MKT Spec released on 6.9 | PRC Only | Mofushi_E | E95 | 10RJ | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Kevin ZJ9 Liu | New Launch | 2017-07-17 | 2017-08-21 | 2017-08-21 |  | No | Completed | 2020-12-31
Tech Spec released on 5.25. MKT Spec releasd on 6.9 | PRC Only | Eerduosi | E95z | 10RK | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Kevin ZJ9 Liu | New Launch | 2017-07-25 | 2017-08-22 | 2017-08-22 |  | No | Completed | 2018-12-31
MKT Spec released on 8.15. Tech Spec released on 8.16 |  | Lenovo Legion Y520 Tower-25ICZ ES | 90JBCTO1WW | 90JB | DT_Consumer | Lenovo | Consumer | Ricky RC1 Liu | New Launch | 2017-10-03 | 2017-11-28 | 2017-11-28 |  | No | Completed | 2018-09-30
|  | Mofushi E-1.0 | E75s | 10QF | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia | New Launch | 2017-03-02 | 2017-04-18 | 2017-04-18 |  | No | Completed | 2020-12-31
Tech Spec released on 12.20. MKT Spec released on 1.25 | MTM Only | Edinburgh_V | Lenovo V330-15IGM Desktop | 10TS | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia | New Launch | 2018-03-06 | 2018-04-10 | 2018-04-10 |  | No | Completed | 2018-06-19
|  | Macao_P9 | M910z | 10NR 10NT 10NS 10NU | DT_SMB/Commercial/NEC | ThinkCentre | Commercial DT | Ian Yuan11 Yao | New Launch | 2017-01-24 | 2017-02-28 | 2017-02-28 |  | Yes | Completed | 2019-06-30
|  | Mofushi_V | Lenovo V520-15IKL Desktop | 10NK 10NL | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia | New Launch | 2017-01-31 | 2017-03-07 | 2017-03-07 |  | Yes | Completed | 2019-06-30
|  | Pippen | P320 Tiny | 30C1 30C2 | DT Workstation_Commercial | ThinkStation | Commercial WS | Yimeng YM23 Zhang | New Launch | 2017-05-22 | 2017-06-06 | 2017-06-06 |  |  | Completed | 2018-12-31
|  | Mofushi_V | Lenovo V520S-08IKL Desktop | 10NM 10NN | DT_SMB/Commercial/NEC | Lenovo | SMB | Jerry Jing1 Jia | New Launch | 2017-01-31 | 2017-03-07 | 2017-03-07 |  | Yes | Completed | 2018-10-31
|  | ideacentre AIO 520-24IKU | ideacentre AIO 520-24IKU | F0D2 | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu | New Launch | 2017-05-29 | 2017-07-24 | 2017-07-24 |  | No | Completed | 2019-12-30
|  | ideacentre AIO 520-22IKU | F0D5CTO1WW | F0D5 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu | New Launch | 2017-05-29 | 2017-07-24 | 2017-07-24 |  | No | Completed | 2019-12-30
|  | ideacentre AIO 730S-24IKB | ideacentre AIO 730S-24IKB | F0DX F0DY | DT_Consumer | IdeaCentre | Consumer | Lynn Ling2 He | New Launch | 2018-01-12 | 2018-03-09 | 2018-03-09 |  | No | Completed | 2019-09-30
| Tech Spec released on 1.9. MKT Spec released on 1.25 | ideacentre AIO 520-24ICB | F0DJCTO1WW | F0DJ | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu | New Launch | 2018-03-12 | 2018-05-07 | 2018-05-07 |  | No | Completed | 2019-10-31
| Tech Spec released on 1.9. MKT Spec released on 1.25 | ideacentre AIO 520-22ICB | F0DTCTO1WW | F0DT | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu | New Launch | 2018-03-12 | 2018-05-07 | 2018-05-07 |  | No | Completed | 2019-10-31
| Tech Spec updated on 7.20. MKT Spec released on 1.25 | ideacentre AIO 520-24ARR | F0DNCTO1WW | F0DN | DT_Consumer | IdeaCentre | Consumer | Junjun JJ25 Liu | New Launch | 2018-03-20 | 2018-05-15 | 2018-05-15 |  | No | Completed | 2019-12-30
| Tech Spec released on 12.26. MKT Spec released on 1.17 Update EOL Target | ideacentre 510-15ICB | 90HUCTO1WW | 90HU | DT_Consumer | IdeaCentre | Consumer | Lynn Ling2 He | New Launch | 2018-03-26 | 2018-05-21 | 2018-05-21 |  | No | Completed | 2019-12-31
| Tech Spec released on 3.19. MKT Spec released on 4.28 | Mansfield_E | E76s | 10XU | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia | New Launch | 2018-06-12 | 2018-07-10 | 2018-07-10 |  | No | Completed | 2019-09-30
| Tech Spec released on 3.26. MKT Spec released on 4.18 | ideacentre 510S-07ICB | 90K8CTO1WW | 90K8 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu | New Launch | 2018-05-21 | 2018-07-16 | 2018-07-16 |  | No | Completed | 2019-12-31
| Tech Spec released on 3.27. MKT Spec released on 5.4 | Mansfield_E | E76 | 10UM | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia | New Launch | 2018-06-12 | 2018-07-17 | 2018-07-17 |  | No | Completed | 2019-12-31
| Tech Spec released on 4.24. MKT Spec released on 5.29 | Erhai | E96z | 10Y4 | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Kevin ZJ9 Liu | New Launch | 2018-07-10 | 2018-08-14 | 2018-08-14 |  | No | Completed | 2019-09-30
| Tech Spec released on 5.7. MKT Spec released on 6.12. IMG released on 8.2 | Mansfield_E | E96 | 10UN | DT_SMB/Commercial/NEC | ThinkCentre | SMB | Jerry Jing1 Jia | New Launch | 2018-07-17 | 2018-08-21 | 2018-08-21 |  | No | Completed | 2019-12-31
| Tech Spec released on 9.21.MKT Spec released on 10.22 | ideacentre A340-22ICB | F0E9CTO1WW | F0E9 | DT_Consumer | IdeaCentre | Consumer | Rainbow LL9 Liu | New Launch | 2018-11-21 | 2019-01-16 | 2019-01-16 |  | No | Completed | 2019-12-31
|  | Mofushi_M | M710q | 10MQ 10MR 10MS 10MT 10QR | Commercial DT | ThinkCentre | Commercial | Kevin ZJ9 Liu | New Launch | 2017-01-17 | 2017-02-21 | 2017-02-21 |  | Yes | Completed | 2020-03-31
|  | Mofushi_M | M710s | 10M7 10M8 | Commercial DT | ThinkCentre | Commercial | Hua Hua7 Chen | New Launch | 2017-01-17 | 2017-02-21 | 2017-02-21 |  | Yes | Completed | 2020-03-31
|  | Mofushi_M | M710t | 10M9 10MA | Commercial DT | ThinkCentre | Commercial | Hua Hua7 Chen | New Launch | 2017-01-17 | 2017-02-21 | 2017-02-21 |  | Yes | Completed | 2020-03-31
|  | Palau_M Tiny | M910q | 10MU 10MV | Commercial DT | ThinkCentre | Commercial | Astrid Jing12 Zhao | New Launch | 2017-01-17 | 2017-02-21 | 2017-02-21 |  | Yes | Completed | 2020-03-31
|  | Palau_M | M910s | 10MK 10ML | Commercial DT | ThinkCentre | Commercial | Ian Yuan11 Yao | New Launch | 2017-01-17 | 2017-02-21 | 2017-02-21 |  | Yes | Completed | 2020-03-31
|  | Palau_KT | M910t | 10MM 10MN | Commercial DT | ThinkCentre | Commercial | Ian Yuan11 Yao | New Launch | 2017-01-17 | 2017-02-21 | 2017-02-21 |  | Yes | Completed | 2020-03-31
|  | ideacentre 720-18ICB | 90HTCTO1WW | 90HT | Consumer DT | IdeaCentre | Consumer | Rainbow LL9 Liu | New Launch | 2018-03-16 | 2018-05-11 | 2018-05-11 |  | No | Completed | 2020-03-31
|  | ideacentre AIO 520-27ICB | F0DECTO1WW | F0DE | Consumer DT | IdeaCentre | Consumer | Junjun JJ25 Liu | New Launch | 2018-04-13 | 2018-06-08 | 2018-06-08 |  | No | Completed | 2020-03-31
|  | IdeaCentre T540-15ICB G | 90L1CTO1WW | 90L1 | Consumer DT | IdeaCentre | Consumer | Rainbow LL9 Liu | New Launch | 2019-02-01 | 2019-03-29 | 2019-03-29 |  | No | Completed | 2020-03-31
|  | Mansfield_V | Lenovo V530-15ICB Desktop | 10TV 10TW | DT_SMB/Commercial/NEC | IdeaCentre | SMB | Jerry Jing1 Jia | New Launch | 2018-05-15 | 2018-06-19 | 2018-06-19 |  | Yes | Completed | 2020-03-31
|  | Mansfield_V | Lenovo V530s-07ICB Desktop | 10TX 10TY | DT_SMB/Commercial/NEC | IdeaCentre | SMB | Jerry Jing1 Jia | New Launch | 2018-06-12 | 2018-07-10 | 2018-07-24 |  | Yes | Completed | 2020-03-31
|  | Detroit_V | Lenovo V530-15ARR Desktop | 10V3 10Y3 | DT_SMB/Commercial/NEC | IdeaCentre | SMB | Jerry Jing1 Jia | New Launch | 2018-09-25 | 2018-10-30 | 2018-10-30 |  | Yes | Completed | 2020-04-30
|  | Stockholm_M4 | Lenovo V540-24IWL AIO | 10YS | DT_SMB/Commercial/NEC | IdeaCentre | SMB | Kevin ZJ9 Liu | New Launch | 2019-02-26 | 2019-03-26 | 2019-03-26 |  | No | Completed | 2020-04-30
|  | Malaysia | M710e | 10UQ 10UR | Commercial DT | ThinkCentre | Commercial | Hua Hua7 Chen | New Launch | 2018-01-08 | 2018-01-30 | 2018-01-30 |  | Yes | Completed | 2020-03-31
Note on Q143: 作者: 10/8 DT EOL UPDATE
Note on Q145: 作者: 10/8 DT EOL UPDATE
Note on S145: 作者: 10/8 DT EOL UPDATE
Note on Q164: 作者: 10/8 DT EOL UPDATE
Note on Q165: 作者: 10/8 DT EOL UPDATE

## CTO List
Sub-Series Name | CTO # | CTO # | PDM PM | Status | Enable Web CTO | AD
310S-08ASR | 90G9CTO1WW | 90G9 | guorp2 | Completed | No | 2017-01-23
P320 SFF | 30BKCTO1WW | 30BK | guorp2 | Completed | Yes | 2017-04-18
P320 SFF | 30BJCTO1WW | 30BJ | guorp2 | Completed | Yes | 2017-04-18
P320 Tower | 30BGCTO1WW | 30BG | guorp2 | Completed | Yes | 2017-04-18
P320 Tower | 30BHCTO1WW | 30BH | guorp2 | Completed | Yes | 2017-04-18
E75 | 10QECTO1WW | 10QE | guorp2 | Completed | No | 2017-04-18
E95 | 10RJCTO1WW | 10RJ | lizj22 | Completed | No | 2017-08-21
F0D8CTO1WW | F0D8CTO1WW | F0D8 | guorp2 | Completed | No | 2017-11-20
90HXCTO1WW | 90HXCTO1WW | 90HX | guorp2 | Completed | No | 2018-02-07
M625q | 10TFCTO1WW | 10TF | houce1 | Completed | Yes | 2018-04-24
M625q | 10TGCTO1WW | 10TG | houce1 | Completed | Yes | 2018-04-24
M625q | 10THCTO1WW | 10TH | houce1 | Completed | Yes | 2018-04-24
M625q | 10TJCTO1WW | 10TJ | houce1 | Completed | Yes | 2018-04-24
M625q | 10TKCTO1WW | 10TK | houce1 | Completed | Yes | 2018-04-24
M625q Thin Client | 10TLCTO1WW | 10TL | houce1 | Completed | Yes | 2018-04-24
M625q Thin Client | 10UYCTO1WW | 10UY | houce1 | Completed | Yes | 2018-04-24
M625q Thin Client | 10V0CTO1WW | 10V0 | houce1 | Completed | Yes | 2018-04-24
M625q Thin Client | 10V1CTO1WW | 10V1 | houce1 | Completed | Yes | 2018-04-24
M625q Thin Client | 10V2 CTO1WW | 10V2 | houce1 | Completed | Yes | 2018-04-24
90J0CTO1WW | 90J0CTO1WW | 90J0 | lizj22 | Completed | No | 2018-04-27
F0D7CTO1WW | F0D7CTO1WW | F0D7 | qinn1 | Completed | No | 2018-05-16
90HVCTO1WW | 90HVCTO1WW | 90HV | guorp2 | Completed | No | 2018-05-21
Lenovo V130-20IGM | 10RXCTO1WW | 10RX | qinn1 | Completed | No | 2018-05-22
90JLCTO1WW | 90JLCTO1WW | 90JL | qinn1 | Completed | No | 2018-05-28
90JXCTO1WW | 90JXCTO1WW | 90JX | guorp2 | Completed | No | 2018-05-28
90JFCTO1WW | 90JFCTO1WW | 90JF | guorp2 | Completed | No | 2018-05-28
M720t | 10SQCTO1WW | 10SQ | qinn1 | Completed | Yes | 2018-06-12
M720t | 10SRCTO1WW | 10SR | qinn1 | Completed | Yes | 2018-06-12
M720t | 10U4CTO1WW | 10U4 | qinn1 | Completed | Yes | 2018-06-12
M720t | 10U5CTO1WW | 10U5 | qinn1 | Completed | Yes | 2018-06-12
M720s | 10STCTO1WW | 10ST | qinn1 | Completed | Yes | 2018-06-12
M720s | 10SUCTO1WW | 10SU | qinn1 | Completed | Yes | 2018-06-12
M720s | 10U6CTO1WW | 10U6 | qinn1 | Completed | Yes | 2018-06-12
M720s | 10U7CTO1WW | 10U7 | qinn1 | Completed | Yes | 2018-06-12
90JHCTO1WW | 90JHCTO1WW | 90JH | guorp2 | Completed | No | 2018-06-15
Lenovo V330-20ICB | 10UKCTO1WW | 10UK | guorp2 | Completed | Yes | 2018-06-19
Lenovo V330-20ICB | 10ULCTO1WW | 10UL | guorp2 | Completed | Yes | 2018-06-19
Lenovo V530-22ICB | 10USCTO1WW | 10US | guorp2 | Completed | No | 2018-06-19
Lenovo V530-22ICB | 10UTCTO1WW | 10UT | guorp2 | Completed | No | 2018-06-19
Lenovo V530-22ICB | 10UUCTO1WW | 10UU | guorp2 | Completed | No | 2018-06-19
Lenovo V530-22ICB | 10UVCTO1WW | 10UV | guorp2 | Completed | No | 2018-06-19
Lenovo V530-24ICB | 10UWCTO1WW | 10UW | lizj22 | Completed | No | 2018-06-19
Lenovo V530-24ICB | 10UXCTO1WW | 10UX | lizj22 | Completed | No | 2018-06-19
M715q | 10VGCTO1WW | 10VG | qinn1 | Completed | Yes | 2018-06-19
M715q | 10VHCTO1WW | 10VH | qinn1 | Completed | Yes | 2018-06-19
M715q | 10VJCTO1WW | 10VJ | qinn1 | Completed | Yes | 2018-06-19
M715q | 10VKCTO1WW | 10VK | qinn1 | Completed | Yes | 2018-06-19
M715q Thinclient | 10VLCTO1WW | 10VL | qinn1 | Completed | Yes | 2018-06-19
M715q Thinclient | 10VMCTO1WW | 10VM | qinn1 | Completed | Yes | 2018-06-19
M715q Thinclient | 10VNCTO1WW | 10VN | qinn1 | Completed | Yes | 2018-06-19
M715q Thinclient | 10VQCTO1WW | 10VQ | qinn1 | Completed | Yes | 2018-06-19
M720q | 10T7CTO1WW | 10T7 | qinn1 | Completed | Yes | 2018-06-26
M720q | 10T8CTO1WW | 10T8 | qinn1 | Completed | Yes | 2018-06-26
M720q | 10T9CTO1WW | 10T9 | qinn1 | Completed | Yes | 2018-06-26
M720q | 10TACTO1WW | 10TA | qinn1 | Completed | Yes | 2018-06-26
M720q | 10TCCTO1WW | 10TC | qinn1 | Completed | Yes | 2018-06-26
M920t | 10SFCTO1WW | 10SF | guorp2 | Completed | Yes | 2018-06-26
M920t | 10SGCTO1WW | 10SG | guorp2 | Completed | Yes | 2018-06-26
M920t | 10U0CTO1WW | 10U0 | guorp2 | Completed | Yes | 2018-06-26
M920t | 10U1CTO1WW | 10U1 | guorp2 | Completed | Yes | 2018-06-26
M920s | 10SJCTO1WW | 10SJ | guorp2 | Completed | Yes | 2018-06-26
M920s | 10SKCTO1WW | 10SK | guorp2 | Completed | Yes | 2018-06-26
M920s | 10U3CTO1WW | 10U3 | guorp2 | Completed | Yes | 2018-06-26
M920s | 10U4CTO1WW | 10U4 | guorp2 | Completed | Yes | 2018-06-26
90JYCTO1WW | 90JYCTO1WW | 90JY | guorp2 | Completed | No | 2018-06-28
90K0CTO1WW | 90K0CTO1WW | 90K0 | guorp2 | Completed | No | 2018-06-28
90HYCTO1WW | 90HYCTO1WW | 90HY | guorp2 | Completed | No | 2018-06-29
M920q | 10RRCTO1WW | 10RR | qinn1 | Completed | Yes | 2018-07-03
M920q | 10RSCTO1WW | 10RS | qinn1 | Completed | Yes | 2018-07-03
M920q | 10RTCTO1WW | 10RT | qinn1 | Completed | Yes | 2018-07-03
M920q | 10RUCTO1WW | 10RU | qinn1 | Completed | Yes | 2018-07-03
M920q | 10V8CTO1WW | 10V8 | qinn1 | Completed | Yes | 2018-07-03
M920q | 10SYCTO1WW | 10SY | qinn1 | Completed | Yes | 2018-07-03
M820z | 10SCCTO1WW | 10SC | lizj22 | Completed | Yes | 2018-07-24
M820z | 10SDCTO1WW | 10SD | lizj22 | Completed | Yes | 2018-07-24
M920z | 10S6CTO1WW | 10S6 | qinn1 | Completed | Yes | 2018-07-24
M920z | 10S7CTO1WW | 10S7 | qinn1 | Completed | Yes | 2018-07-24
M920z | 10Y6CTO1WW | 10Y6 | qinn1 | Completed | Yes | 2018-07-24
P330 Tower | 30CYCTO1WW | 30CY | guorp2 | Completed | Yes | 2018-07-24
P330 Tower | 30D0CTO1WW | 30D0 | guorp2 | Completed | Yes | 2018-07-24
P330 SFF | 30D1CTO1WW | 30D1 | guorp2 | Completed | Yes | 2018-07-24
P330 SFF | 30D2CTO1WW | 30D2 | guorp2 | Completed | Yes | 2018-07-24
M920x | 10S0CTO1WW | 10S0 | houce1 | Completed | Yes | 2018-07-31
M920x | 10S1CTO1WW | 10S1 | houce1 | Completed | Yes | 2018-07-31
M920x | 10S2CTO1WW | 10S2 | houce1 | Completed | Yes | 2018-07-31
M920x | 10S3CTO1WW | 10S3 | houce1 | Completed | Yes | 2018-07-31
P720 | 30BACTO1WW | 30BA | lizj22 | Completed | Yes | 2018-07-31
P720 | 30BBCTO1WW | 30BB | lizj22 | Completed | Yes | 2018-07-31
P920 | 30BCCTO1WW | 30BC | lizj22 | Completed | Yes | 2018-07-31
P920 | 30BDCTO1WW | 30BD | lizj22 | Completed | Yes | 2018-07-31
P520c | 30BXCTO1WW | 30BX | houce1 | Completed | Yes | 2018-07-31
P520c | 30BYCTO1WW | 30BY | houce1 | Completed | Yes | 2018-07-31
P520 | 30BECTO1WW | 30BE | houce1 | Completed | Yes | 2018-07-31
P520 | 30BFCTO1WW | 30BF | houce1 | Completed | Yes | 2018-07-31
M725s | 10VTCTO1WW | 10VT | lizj22 | Completed | Yes | 2018-07-31
M725s | 10VUCTO1WW | 10VU | lizj22 | Completed | Yes | 2018-07-31
P330 Tiny | 30CFCTO1WW | 30CF | houce1 | Completed | Yes | 2018-07-31
P330 Tiny | 30CECTO1WW | 30CE | houce1 | Completed | Yes | 2018-07-31
90JGCTO1WW | 90JGCTO1WW | 90JG | lizj22 | Completed | No | 2018-11-16
F0E4CTO1WW | F0E4CTO1WW | F0E4 | qinn1 | Completed | No | 2019-01-14
F0E5CTO1WW | F0E5CTO1WW | F0E5 | qinn1 | Completed | No | 2019-01-14
F0E6CTO1WW | F0E6CTO1WW | F0E6 | lizj22 | Completed | No | 2019-01-16
F0E7CTO1WW | F0E7CTO1WW | F0E7 | guorp2 | Completed | No | 2019-01-16
F0EACTO1WW | F0EACTO1WW | F0EA | guorp2 | Completed | No | 2019-01-16
F0E8CTO1WW | F0E8CTO1WW | F0E8 | lizj22 | Completed | No | 2019-01-31
F0EBCTO1WW | F0EBCTO1WW | F0EB | guorp2 | Completed | No | 2019-01-31
90L2CTO1WW | 90L2CTO1WW | 90L2 | qinn1 | Completed | No | 2019-01-31
90L3CTO1WW | 90L3CTO1WW | 90L3 | qinn1 | Completed | No | 2019-01-31
90L4CTO1WW | 90L4CTO1WW | 90L4 | qinn1 | Completed | No | 2019-01-31
M630e | 10YMCTO1WW | 10YM | qinn1 | Completed | No | 2019-03-12
M630e TIO | 10YNCTO1WW | 10YN | qinn1 | Completed | No | 2019-03-12
F0EQCTO1WW | F0EQCTO1WW | F0EQ | qinn1 | Completed | No | 2019-04-29
90L5CTO1WW | 90L5CTO1WW | 90L5 | guorp2 | Completed | No | 2019-06-28
M90n-1 | 11ADCTO1WW | 11AD | lizj22 | Completed | Yes | 2019-07-02
M90n-1 | 11AECTO1WW | 11AE | lizj22 | Completed | Yes | 2019-07-02
M90n-1 | 11AFCTO1WW | 11AF | lizj22 | Completed | Yes | 2019-07-02
M90n-1 | 11AGCTO1WW | 11AG | lizj22 | Completed | Yes | 2019-07-02
M90n-1 | 11AKCTO1WW | 11AK | lizj22 | Completed | Yes | 2019-07-02
M90n-1 Thin Client | 11AHCTO1WW | 11AH | lizj22 | Completed | Yes | 2019-07-02
M90n-1 Thin Client | 11AJCTO1WW | 11AJ | lizj22 | Completed | Yes | 2019-07-02
M90n-1 Thin Client | 11AMCTO1WW | 11AM | lizj22 | Completed | Yes | 2019-07-02
M90n-1 Thin Client | 11ASCTO1WW | 11AS | lizj22 | Completed | Yes | 2019-07-02
M90n-1 Thin Client | 11J3CTO1WW | 11J3 | lizj22 | Completed | Yes | 2019-07-02
M90n-1 Thin Client | 11J7CTO1WW | 11J7 | lizj22 | Completed | Yes | 2019-07-02
90J0CTO2WW | 90J0CTO2WW | 90J0 | lizj22 | Completed | No | 2019-07-31
F0ELCTO1WW | F0ELCTO1WW | F0EL | lizj22 | Completed | No | 2019-07-31
F0EMCTO1WW | F0EMCTO1WW | F0EM | qinn1 | Completed | No | 2019-07-31
510-15ICK | 90LUCTO1WW | 90LU | qinn1 | Completed | No | 2019-07-31
510A-15ICK | 90LVCTO1WW | 90LV | lizj22 | Completed | No | 2019-07-31
T540-15ICK G | 90LWCTO1WW | 90LW | lizj22 | Completed | No | 2019-07-31
F0EKCTO1WW | F0EKCTO1WW | F0EK | lizj22 | Completed | No | 2019-08-06
E76x | 11BACTO1WW | 11BA | guorp2 | Completed | No | 2019-08-07
E76p | 11BRCTO1WW | 11BR | lizj22 | Completed | No | 2019-08-14
E96x | 11BBCTO1WW | 11BB | qinn1 | Completed | No | 2019-08-14
A340-24ICK | F0ERCTO1WW | F0ER | qinn1 | Completed | No | 2019-08-30
A340-22ICK | F0ESCTO1WW | F0ES | lizj22 | Completed | No | 2019-08-30
M75s-1 | 11A9CTO1WW | 11A9 | houce1 | Completed | Yes | 2019-09-30
M75s-1 | 11AACTO1WW | 11AA | houce1 | Completed | Yes | 2019-09-30
M75s-1 | 11AVCTO1WW | 11AV | houce1 | Completed | Yes | 2019-09-30
M75s-1 | 11AWCTO1WW | 11AW | houce1 | Completed | Yes | 2019-09-30
510S-07ICK | 90LXCTO1WW | 90LX | lizj22 | Completed | No | 2019-09-30
V530S-07ICR | 11BLCTO1WW | 11BL | qinn1 | Completed | Yes | 2019-09-30
V530S-07ICR | 11BMCTO1WW | 11BM | qinn1 | Completed | Yes | 2019-09-30
V530-15ICR | 11BGCTO1WW | 11BG | lizj22 | Completed | Yes | 2019-09-30
V530-15ICR | 11BHCTO1WW | 11BH | lizj22 | Completed | Yes | 2019-09-30
M720e | 11BDCTO1WW | 11BD | guorp2 | Completed | Yes | 2019-09-30
M720e | 11BECTO1WW | 11BE | guorp2 | Completed | Yes | 2019-09-30
M75q-1 | 11A4CTO1WW | 11A4 | lizj22 | Completed | Yes | 2019-10-15
M75q-1 | 11A5CTO1WW | 11A5 | lizj22 | Completed | Yes | 2019-10-15
M75q-1 | 11A6CTO1WW | 11A6 | lizj22 | Completed | Yes | 2019-10-15
M75q-1 | 11A7CTO1WW | 11A7 | lizj22 | Completed | Yes | 2019-10-15
Lenovo V55t-15API | 11CBCTO1WW | 11CB | qinn1 | Completed | Yes | 2019-10-29
Lenovo V55t-15API | 11CCCTO1WW | 11CC | qinn1 | Completed | Yes | 2019-10-29
E76a | 11E6CTO1WW | 11E6 | guorp2 | Completed | No | 2019-11-29
Lenovo V30a-24IML | 11FTCTO1WW | 11FT | qinn1 | Completed | No | 2020-02-18
Lenovo V30a-24IML | 11FUCTO1WW | 11FU | qinn1 | Completed | No | 2020-02-18
IdeaCentre 3 07ADA05 | 90MVCTO1WW | 90MV | lizj22 | Completed | No | 2020-02-28
IdeaCentre 3 07ADA05 | 90NTCTO1WW | 90NT | lizj22 | Completed | No | 2020-02-28
IdeaCentre 5 14IMB05 | 90NACTO1WW | 90NA | guorp2 | Completed | No | 2020-03-04
IdeaCentre 5 14IMB05 | 90NQCTO1WW | 90NQ | guorp2 | Completed | No | 2020-03-04
IdeaCentre AIO 3 22ADA05 | F0EXCTO1WW | F0EX | qinn1 | Completed | No | 2020-03-31
IdeaCentre AIO 3 24IMB05 | F0EUCTO1WW | F0EU | guorp2 | Completed | No | 2020-03-31
IdeaCentre AIO 3 22IMB05 | F0EVCTO1WW | F0EV | lizj22 | Completed | No | 2020-03-31
IdeaCentre AIO 3 27IMB05 | F0EYCTO1WW | F0EY | guorp2 | Completed | No | 2020-03-31
IdeaCentre AIO 3 24ARE05 | F0EWCTO1WW | F0EW | qinn1 | Completed | No | 2020-04-03
Lenovo Legion T5 28IMB05 | 90NCCTO1WW | 90NC | guorp2 | Completed | No | 2020-04-10
Lenovo Legion T5 28IMB05 | 90NKCTO1WW | 90NK | guorp2 | Completed | No | 2020-04-10
Lenovo Legion R5 28IMB05 | 90NJCTO1WW | 90NJ | guorp2 | Completed | No | 2020-04-10
IdeaCentre AIO 5 24IMB05 | F0FBCTO1WW | F0FB | lizj22 | Completed | No | 2020-04-24
Lenovo Legion R5 28IMB05 | 90NECTO1WW | 90NE | guorp2 | Completed | No | 2020-04-28
IdeaCentre G5 14IMB05 | 90N9CTO1WW | 90N9 | lizj22 | Completed | No | 2020-04-30
IdeaCentre G5 14IMB05 | 90NRCTO1WW | 90NR | lizj22 | Completed | No | 2020-04-30
IdeaCentre 3 07IMB05 | 90NBCTO1WW | 90NB | guorp2 | Completed | No | 2020-04-30
IdeaCentre 3 07IMB05 | 90NSCTO1WW | 90NS | guorp2 | Completed | No | 2020-04-30
IdeaCentre AIO 5 27IMB05 | F0FACTO1WW | F0FA | houce1 | Completed | No | 2020-04-30
Lenovo V30a-22IML | 11FVCTO1WW | 11FV | houce1 | Completed | No | 2020-05-13
Lenovo V30a-22IML | 11FWCTO1WW | 11FW | houce1 | Completed | No | 2020-05-13
M70q | 11DTCTO1WW | 11DT | guorp2 | Completed | Yes | 2020-05-14
M70q | 11DUCTO1WW | 11DU | guorp2 | Completed | Yes | 2020-05-14
M70q | 11DVCTO1WW | 11DV | guorp2 | Completed | Yes | 2020-05-14
M70q | 11DWCTO1WW | 11DW | guorp2 | Completed | Yes | 2020-05-14
M70q | 11E7CTO1WW | 11E7 | guorp2 | Completed | Yes | 2020-05-14
M70q | 11E8CTO1WW | 11E8 | guorp2 | Completed | Yes | 2020-05-14
M80q | 11DNCTO1WW | 11DN | guorp2 | Completed | Yes | 2020-05-14
M80q | 11DQCTO1WW | 11DQ | guorp2 | Completed | Yes | 2020-05-14
M80q | 11DRCTO1WW | 11DR | guorp2 | Completed | Yes | 2020-05-14
M80q | 11DSCTO1WW | 11DS | guorp2 | Completed | Yes | 2020-05-14
M80q | 11EGCTO1WW | 11EG | guorp2 | Completed | Yes | 2020-05-14
Lenovo V35s-07ADA | 11HECTO1WW | 11HE | houce1 | Completed | Yes | 2020-05-15
Lenovo V35s-07ADA | 11HFCTO1WW | 11HF | houce1 | Completed | Yes | 2020-05-15
Lenovo V35s-07ADA | 11HQCTO1WW | 11HQ | houce1 | Completed | Yes | 2020-05-15
Lenovo V35s-07ADA | 11HRCTO1WW | 11HR | houce1 | Completed | Yes | 2020-05-15
M70t | 11D9CTO1WW | 11D9 | lizj22 | Completed | Yes | 2020-05-21
M70t | 11DACTO1WW | 11DA | lizj22 | Completed | Yes | 2020-05-21
M70t | 11EUCTO1WW | 11EU | lizj22 | Completed | Yes | 2020-05-21
M70t | 11EVCTO1WW | 11EV | lizj22 | Completed | Yes | 2020-05-21
M70s | 11DBCTO1WW | 11DB | qinn1 | Completed | Yes | 2020-05-21
M70s | 11DCCTO1WW | 11DC | qinn1 | Completed | Yes | 2020-05-21
M70s | 11EWCTO1WW | 11EW | qinn1 | Completed | Yes | 2020-05-21
M70s | 11EXCTO1WW | 11EX | qinn1 | Completed | Yes | 2020-05-21
M75n | 11BSCTO1WW | 11BS | houce1 | Completed | Yes | 2020-05-21
M75n | 11BTCTO1WW | 11BT | houce1 | Completed | Yes | 2020-05-21
M75n | 11BUCTO1WW | 11BU | houce1 | Completed | Yes | 2020-05-21
M75n | 11BVCTO1WW | 11BV | houce1 | Completed | Yes | 2020-05-21
M75n | 11BWCTO1WW | 11BW | houce1 | Completed | Yes | 2020-05-21
M75n | 11BXCTO1WW | 11BX | houce1 | Completed | Yes | 2020-05-21
M75n | 11GWCTO1WW | 11GW | houce1 | Completed | Yes | 2020-05-21
M75n | 11GXCTO1WW | 11GX | houce1 | Completed | Yes | 2020-05-21
M75n | 11G4CTO1WW | 11G4 | houce1 | Completed | Yes | 2020-05-21
M75n | 11G5CTO1WW | 11G5 | houce1 | Completed | Yes | 2020-05-21
M75n | 11G6CTO1WW | 11G6 | houce1 | Completed | Yes | 2020-05-21
M75n | 11G7CTO1WW | 11G7 | houce1 | Completed | Yes | 2020-05-21
M80t | 11CSCTO1WW | 11CS | houce1 | Completed | Yes | 2020-05-26
M80t | 11CTCTO1WW | 11CT | houce1 | Completed | Yes | 2020-05-26
M80t | 11EKCTO1WW | 11EK | houce1 | Completed | Yes | 2020-05-26
M80t | 11ELCTO1WW | 11EL | houce1 | Completed | Yes | 2020-05-26
M80s | 11CUCTO1WW | 11CU | houce1 | Completed | Yes | 2020-05-26
M80s | 11CVCTO1WW | 11CV | houce1 | Completed | Yes | 2020-05-26
M80s | 11EMCTO1WW | 11EM | houce1 | Completed | Yes | 2020-05-26
M80s | 11ENCTO1WW | 11EN | houce1 | Completed | Yes | 2020-05-26
Lenovo V50t-13IMB | 11ECCTO1WW | 11EC | lizj22 | Completed | Yes | 2020-05-27
Lenovo V50t-13IMB | 11EDCTO1WW | 11ED | lizj22 | Completed | Yes | 2020-05-27
Lenovo V50t-13IMB | 11HCCTO1WW | 11HC | lizj22 | Completed | Yes | 2020-05-27
Lenovo V50t-13IMB | 11HDCTO1WW | 11HD | lizj22 | Completed | Yes | 2020-05-27
M70a | 11E2CTO1WW | 11E2 | guorp2 | Completed | Yes | 2020-05-29
M70a | 11CKCTO1WW | 11CK | guorp2 | Completed | Yes | 2020-05-29
M70a | 11CLCTO1WW | 11CL | guorp2 | Completed | Yes | 2020-05-29
M70a | 11E3CTO1WW | 11E3 | guorp2 | Completed | Yes | 2020-05-29
Lenovo V50a-24IMB | 11FJCTO1WW | 11FJ | guorp2 | Completed | No | 2020-06-01
Lenovo V50a-24IMB | 11FKCTO1WW | 11FK | guorp2 | Completed | No | 2020-06-01
Lenovo V50a-24IMB | 11FLCTO1WW | 11FL | guorp2 | Completed | No | 2020-06-01
Lenovo V50a-24IMB | 11FMCTO1WW | 11FM | guorp2 | Completed | No | 2020-06-01
Lenovo V50a-22IMB | 11FNCTO1WW | 11FN | lizj22 | Completed | No | 2020-06-01
Lenovo V50a-22IMB | 11FQCTO1WW | 11FQ | lizj22 | Completed | No | 2020-06-01
Lenovo V50a-22IMB | 11FRCTO1WW | 11FR | lizj22 | Completed | No | 2020-06-01
Lenovo V50a-22IMB | 11FSCTO1WW | 11FS | lizj22 | Completed | No | 2020-06-01
M90t | 11CYCTO1WW | 11CY | lizj22 | Completed | Yes | 2020-06-02
M90t | 11D0CTO1WW | 11D0 | lizj22 | Completed | Yes | 2020-06-02
M90t | 11D4CTO1WW | 11D4 | lizj22 | Completed | Yes | 2020-06-02
M90t | 11D5CTO1WW | 11D5 | lizj22 | Completed | Yes | 2020-06-02
M90s | 11D1CTO1WW | 11D1 | houce1 | Completed | Yes | 2020-06-02
M90s | 11D2CTO1WW | 11D2 | houce1 | Completed | Yes | 2020-06-02
M90s | 11D6CTO1WW | 11D6 | houce1 | Completed | Yes | 2020-06-02
M90s | 11D7CTO1WW | 11D7 | houce1 | Completed | Yes | 2020-06-02
E77 | 11EBCTO1WW | 11EB | houce1 | Completed | No | 2020-06-03
M90a | 11CDCTO1WW | 11CD | guorp2 | Completed | Yes | 2020-06-04
M90a | 11CECTO1WW | 11CE | guorp2 | Completed | Yes | 2020-06-04
M90a | 11DYCTO1WW | 11DY | guorp2 | Completed | Yes | 2020-06-04
M90a | 11E0CTO1WW | 11E0 | guorp2 | Completed | Yes | 2020-06-04
M90a | 11JXCTO1WW | 11JX | guorp2 | Completed | Yes | 2020-06-04
E97 | 11EACTO1WW | 11EA | lizj22 | Completed | No | 2020-06-05
Lenovo Legion T7 34IMZ05 | 90Q8CTO1WW | 90Q8 | qinn1 | Completed | No | 2020-06-08
Lenovo Legion T7 34IMZ05 | 90Q9CTO1WW | 90Q9 | qinn1 | Completed | No | 2020-06-08
M90q | 11CRCTO1WW | 11CR | guorp2 | Completed | Yes | 2020-06-11
M90q | 11DGCTO1WW | 11DG | guorp2 | Completed | Yes | 2020-06-11
M90q | 11DHCTO1WW | 11DH | guorp2 | Completed | Yes | 2020-06-11
M90q | 11DJCTO1WW | 11DJ | guorp2 | Completed | Yes | 2020-06-11
M90q | 11DKCTO1WW | 11DK | guorp2 | Completed | Yes | 2020-06-11
M90q | 11DLCTO1WW | 11DL | guorp2 | Completed | Yes | 2020-06-11
M90q | 11EYCTO1WW | 11EY | guorp2 | Completed | Yes | 2020-06-11
M90q | 11F0CTO1WW | 11F0 | guorp2 | Completed | Yes | 2020-06-11
P340 Tiny | 30DECTO1WW | 30DE | lizj22 | Completed | Yes | 2020-06-11
P340 Tiny | 30DFCTO1WW | 30DF | lizj22 | Completed | Yes | 2020-06-11
P340 Tiny | 30DGCTO1WW | 30DG | lizj22 | Completed | Yes | 2020-06-11
P340 Tiny | 30DRCTO1WW | 30DR | lizj22 | Completed | Yes | 2020-06-11
P340 Tiny | 30DSCTO1WW | 30DS | lizj22 | Completed | Yes | 2020-06-11
P340 SFF | 30DKCTO1WW | 30DK | guorp2 | Completed | Yes | 2020-06-30
P340 SFF | 30DLCTO1WW | 30DL | guorp2 | Completed | Yes | 2020-06-30
P340 SFF | 30DNCTO1WW | 30DN | guorp2 | Completed | Yes | 2020-06-30
P340 Tower | 30DHCTO1WW | 30DH | houce1 | Completed | Yes | 2020-06-30
P340 Tower | 30DJCTO1WW | 30DJ | houce1 | Completed | Yes | 2020-06-30
P340 Tower | 30DMCTO1WW | 30DM | houce1 | Completed | Yes | 2020-06-30
Lenovo V50s-07IMB | 11EECTO1WW | 11EE | lizj22 | Completed | Yes | 2020-07-10
Lenovo V50s-07IMB | 11EFCTO1WW | 11EF | lizj22 | Completed | Yes | 2020-07-10
Lenovo V50s-07IMB | 11HACTO1WW | 11HA | lizj22 | Completed | Yes | 2020-07-10
Lenovo V50s-07IMB | 11HBCTO1WW | 11HB | lizj22 | Completed | Yes | 2020-07-10
IdeaCentre C5 14IMB05 | 90R7CTO1WW | 90R7 | qinn1 | Completed | No | 2020-07-10
IdeaCentre C5 14IMB05 | 90R8CTO1WW | 90R8 | qinn1 | Completed | No | 2020-07-10
IdeaCentre Mini 5 01IMH05 | 90Q6CTO1WW | 90Q6 | lizj22 | Completed | No | 2020-07-31
IdeaCentre Mini 5 01IMH05 | 90Q7CTO1WW | 90Q7 | lizj22 | Completed | No | 2020-07-31
IdeaCentre G5 14AMR05 | 90Q0CTO1WW | 90Q0 | guorp2 | Completed | No | 2020-08-07
IdeaCentre G5 14AMR05 | 90Q1CTO1WW | 90Q1 | guorp2 | Completed | No | 2020-08-07
IdeaCentre 5 14ARE05 | 90Q2CTO1WW | 90Q2 | houce1 | Completed | No | 2020-08-07
IdeaCentre 5 14ARE05 | 90Q3CTO1WW | 90Q3 | houce1 | Completed | No | 2020-08-07
Lenovo Legion T5 26AMR5 ES | 90RBCTO1WW | 90RB | guorp2 | Completed | No | 2020-08-13
Lenovo Legion T5 26AMR5 Non ES | 90RCCTO1WW | 90RC | guorp2 | Completed | No | 2020-08-13
M70c | 11GJCTO1WW | 11GJ | lizj22 | In Progress | Yes | 2020-08-28
M70c | 11GKCTO1WW | 11GK | lizj22 | In Progress | Yes | 2020-08-28
M70c | 11GLCTO1WW | 11GL | lizj22 | In Progress | Yes | 2020-08-28
M70c | 11GMCTO1WW | 11GM | lizj22 | In Progress | Yes | 2020-08-28
P620 | 30E0CTO1WW | 30E0 | qinn1 | In Progress | Yes | 2020-09-04
P620 | 30E1CTO1WW | 30E1 | qinn1 | In Progress | Yes | 2020-09-04
Hub T | 11H0CTO1WW | 11H0 | guorp2 | In Progress | No | 2020-09-15
Hub T | 11H1CTO1WW | 11H1 | guorp2 | In Progress | No | 2020-09-15
Hub Z | 11H2CTO1WW | 11H2 | guorp2 | In Progress | No | 2020-09-15
Hub Z | 11H3CTO1WW | 11H3 | guorp2 | In Progress | No | 2020-09-15
IdeaCentre AIO 3 22IIL5 | F0FQCTO1WW | F0FQ | guorp2 | In Progress | No | 2020-10-16
IdeaCentre AIO 3 24IIL5 | F0FRCTO1WW | F0FR | qinn1 | In Progress | No | 2020-10-16
Lenovo V30a 22IIL | 11LCCTO1WW | 11LC | houce1 | In Progress | No | 2020-10-16
Lenovo V30a 22IIL | 11LDCTO1WW | 11LD | houce1 | In Progress | No | 2020-10-16
Lenovo V30a 24IIL | 11LACTO1WW | 11LA | qinn1 | In Progress | No | 2020-10-16
Lenovo V30a 24IIL | 11LBCTO1WW | 11LB | qinn1 | In Progress | No | 2020-10-16
M75t/s Gen 2 | 11JACTO1WW | 11JA | houce1 | In Progress | Yes | 2020-10-20
M75t/s Gen 2 | 11JBCTO1WW | 11JB | houce1 | In Progress | Yes | 2020-10-20
M75t/s Gen 2 | 11JCCTO1WW | 11JC | houce1 | In Progress | Yes | 2020-10-20
M75t/s Gen 2 | 11JDCTO1WW | 11JD | houce1 | In Progress | Yes | 2020-10-20
M75q Gen2 | 11JJCTO1WW | 11JJ | lizj22 | In Progress | Yes | 2020-10-29
M75q Gen2 | 11JKCTO1WW | 11JK | lizj22 | In Progress | Yes | 2020-10-29
M75q Gen2 | 11JLCTO1WW | 11JL | lizj22 | In Progress | Yes | 2020-10-29
M75q Gen2 | 11JMCTO1WW | 11JM | lizj22 | In Progress | Yes | 2020-10-29
M60e | 11LUCTO1WW | 11LU | guorp2 | In Progress | No | 2020-10-30
M60e | 11LVCTO1WW | 11LV | guorp2 | In Progress | No | 2020-10-30
M60e | 11LWCTO1WW | 11LW | guorp2 | In Progress | No | 2020-10-30
M60e | 11LXCTO1WW | 11LX | guorp2 | In Progress | No | 2020-10-30
M60e | 11LYCTO1WW | 11LY | guorp2 | In Progress | No | 2020-10-30
M60e | 11M0CTO1WW | 11M0 | guorp2 | In Progress | No | 2020-10-30
M60e | 11M1CTO1WW | 11M1 | guorp2 | In Progress | No | 2020-10-30
M60e | 11M2CTO1WW | 11M2 | guorp2 | In Progress | No | 2020-10-30
Lenovo V55t-15ARE | 11KFCTO1WW | 11KF | lizj22 | In Progress | Yes | 2020-11-20
Lenovo V55t-15ARE | 11KGCTO1WW | 11KG | lizj22 | In Progress | Yes | 2020-11-20
Lenovo V55t-15ARE | 11KHCTO1WW | 11KH | lizj22 | In Progress | Yes | 2020-11-20
Lenovo V55t-15ARE | 11KJCTO1WW | 11KJ | lizj22 | In Progress | Yes | 2020-11-20
P340 Tower | 30ENCTO1WW | 30EN | houce1 | Completed | Yes | 2021-01-12
Lenovo Legion T5 26IOB6 | 90RSCTO1WW | 90RS | houce1 | Not Start | No | 2021-03-22
Lenovo Legion T5 26IOB6 | 90RTCTO1WW | 90RT | houce1 | Not Start | No | 2021-03-22
M90n Gen 2 | 11NACTO1WW | 11NA | qinn1 | Not Start | Yes | 2021-03-31
M90n Gen 2 | 11NBCTO1WW | 11NB | qinn1 | Not Start | Yes | 2021-03-31
M90n Gen 2 | 11NCCTO1WW | 11NC | qinn1 | Not Start | Yes | 2021-03-31
M90n Gen 2 | 11NDCTO1WW | 11ND | qinn1 | Not Start | Yes | 2021-03-31
M90n Gen 2 | 11NECTO1WW | 11NE | qinn1 | Not Start | Yes | 2021-03-31
M90n Gen 2 | 11NFCTO1WW | 11NF | qinn1 | Not Start | Yes | 2021-03-31
M90n Gen 2 | 11NGCTO1WW | 11NG | qinn1 | Not Start | Yes | 2021-03-31
M90n Gen 2 | 11NHCTO1WW | 11NH | qinn1 | Not Start | Yes | 2021-03-31
M90n Gen 2 | 11NJCTO1WW | 11NJ | qinn1 | Not Start | Yes | 2021-03-31
M90n Gen 2 | 11NKCTO1WW | 11NK | qinn1 | Not Start | Yes | 2021-03-31
IdeaCentre Gaming5 14IOB6 | 90RDCTO1WW | 90RD | houce1 | Not Start | No | 2021-03-31
IdeaCentre Gaming5 14IOB6 | 90RECTO1WW | 90RE | houce1 | Not Start | No | 2021-03-31
IC Creator 5 14IOB6 | 90RFCTO1WW | 90RF | lizj22 | Not Start | No | 2021-03-31
IC Creator 5 14IOB6 | 90RGCTO1WW | 90RG | lizj22 | Not Start | No | 2021-03-31
IdeaCentre 5 14IOB6 | 90RHCTO1WW | 90RH | qinn1 | Not Start | No | 2021-03-31
IdeaCentre 5 14IOB6 | 90RJCTO1WW | 90RJ | qinn1 | Not Start | No | 2021-03-31
M70a Gen 2 | 11K3CTO1WW | 11K3 | houce1 | Not Start | Yes | 2021-04-27
M70a Gen 2 | 11K4CTO1WW | 11K4 | houce1 | Not Start | Yes | 2021-04-27
M70a Gen 2 | 11K5CTO1WW | 11K5 | houce1 | Not Start | Yes | 2021-04-27
M70a Gen 2 | 11K6CTO1WW | 11K6 | houce1 | Not Start | Yes | 2021-04-27
M70t Gen 2 | 11M3CTO1WW | 11M3 | lizj22 | Not Start | Yes | 2021-04-27
M70t Gen 2 | 11M4CTO1WW | 11M4 | lizj22 | Not Start | Yes | 2021-04-27
M70t Gen 2 | 11M7CTO1WW | 11M7 | lizj22 | Not Start | Yes | 2021-04-27
M70t Gen 2 | 11M8CTO1WW | 11M8 | lizj22 | Not Start | Yes | 2021-04-27
M70s Gen 2 | 11M5CTO1WW | 11M5 | lizj22 | Not Start | Yes | 2021-04-27
M70s Gen 2 | 11M6CTO1WW | 11M6 | lizj22 | Not Start | Yes | 2021-04-27
M70s Gen 2 | 11M9CTO1WW | 11M9 | lizj22 | Not Start | Yes | 2021-04-27
M70s Gen 2 | 11MACTO1WW | 11MA | lizj22 | Not Start | Yes | 2021-04-27
M70q Gen 2 | 11MQCTO1WW | 11MQ | guorp2 | Not Start | Yes | 2021-04-27
M70q Gen 2 | 11MRCTO1WW | 11MR | guorp2 | Not Start | Yes | 2021-04-27
M70q Gen 2 | 11MUCTO1WW | 11MU | guorp2 | Not Start | Yes | 2021-04-27
M70q Gen 2 | 11MVCTO1WW | 11MV | guorp2 | Not Start | Yes | 2021-04-27
M70q Gen 2 | 11MSCTO1WW | 11MS | guorp2 | Not Start | Yes | 2021-04-27
M70q Gen 2 | 11MTCTO1WW | 11MT | guorp2 | Not Start | Yes | 2021-04-27
M70q Gen 2 | 11MWCTO1WW | 11MW | guorp2 | Not Start | Yes | 2021-04-27
M70q Gen 2 | 11MXCTO1WW | 11MX | guorp2 | Not Start | Yes | 2021-04-27
M90a Gen 2 | 11MYCTO1WW | 11MY | guorp2 | Not Start | Yes | 2021-05-18
M90a Gen 2 | 11N0CTO1WW | 11N0 | guorp2 | Not Start | Yes | 2021-05-18
M90a Gen 2 | 11N1CTO1WW | 11N1 | guorp2 | Not Start | Yes | 2021-05-18
M90a Gen 2 | 11N2CTO1WW | 11N2 | guorp2 | Not Start | Yes | 2021-05-18
M90a Gen 2 | 11N3CTO1WW | 11N3 | guorp2 | Not Start | Yes | 2021-05-18
M90a Gen 2 | 11N4CTO1WW | 11N4 | guorp2 | Not Start | Yes | 2021-05-18
M90a Gen 2 | 11N5CTO1WW | 11N5 | guorp2 | Not Start | Yes | 2021-05-18
M90a Gen 2 | 11N6CTO1WW | 11N6 | guorp2 | Not Start | Yes | 2021-05-18
M90a Gen 2 | 11JYCTO1WW | 11JY | houce1 | Not Start | Yes | 2021-05-20
M90a Gen 2 | 11K0CTO1WW | 11K0 | houce1 | Not Start | Yes | 2021-05-20
M90a Gen 2 | 11K1CTO1WW | 11K1 | houce1 | Not Start | Yes | 2021-05-20
M90a Gen 2 | 11K2CTO1WW | 11K2 | houce1 | Not Start | Yes | 2021-05-20
M90a Gen 2 | 11MNCTO1WW | 11MN | houce1 | Not Start | Yes | 2021-05-20
M90t Gen 2 | 11L0CTO1WW | 11L0 | qinn1 | Not Start | Yes | 2021-05-25
M90t Gen 2 | 11L1CTO1WW | 11L1 | qinn1 | Not Start | Yes | 2021-05-25
M90t Gen 2 | 11L4CTO1WW | 11L4 | qinn1 | Not Start | Yes | 2021-05-25
M90t Gen 2 | 11L5CTO1WW | 11L5 | qinn1 | Not Start | Yes | 2021-05-25
M90s Gen 2 | 11L2CTO1WW | 11L2 | qinn1 | Not Start | Yes | 2021-05-25
M90s Gen 2 | 11L3CTO1WW | 11L3 | qinn1 | Not Start | Yes | 2021-05-25
M90s Gen 2 | 11L6CTO1WW | 11L6 | qinn1 | Not Start | Yes | 2021-05-25
M90s Gen 2 | 11L7CTO1WW | 11L7 | qinn1 | Not Start | Yes | 2021-05-25
Note on A120: Author: Thin client与非Thin client只有风扇上的差别 对于我们team没有任何影响 完全可以当做一个项目
Note on A121: Author: Thin client与非Thin client只有风扇上的差别 对于我们team没有任何影响 完全可以当做一个项目
Note on A122: Author: Thin client与非Thin client只有风扇上的差别 对于我们team没有任何影响 完全可以当做一个项目
Note on A123: Author: Thin client与非Thin client只有风扇上的差别 对于我们team没有任何影响 完全可以当做一个项目
Note on A124: Author: Thin client与非Thin client只有风扇上的差别 对于我们team没有任何影响 完全可以当做一个项目
Note on A125: Author: Thin client与非Thin client只有风扇上的差别 对于我们team没有任何影响 完全可以当做一个项目
Note on G138: Stephen Qi1 Shi: AD of 11AV & 11AW is 11.29
Note on G139: Stephen Qi1 Shi: AD of 11AV & 11AW is 11.29
Note on G140: Stephen Qi1 Shi: AD of 11AV & 11AW is 11.29
Note on G141: Stephen Qi1 Shi: AD of 11AV & 11AW is 11.29

## Member List
Owner | Web CTO Role | 1st Back Up | 2nd Back Up | QA Group
Rachel Li | Team-Lead
Ce Hou | PM | Runpeng Guo | Zejian Li | Ningning Qi
Runpeng Guo | PM | Zejian Li | Ningning Qi | Ce Hou
Zejian Li | PM | Ningning Qi | Ce Hou | Runpeng Guo
Ningning Qi | PM | Ce Hou | Runpeng Guo | Zejian Li

## Sheet1
Count of Sub-Series Name | Column Labels
| Commercial DT | Commercial DT Total | Commercial WS | Commercial WS Total | Consumer |  | Consumer Total | SMB |  | SMB Total | Grand Total
Row Labels | Yes |  | Yes |  | No | Yes |  | No | Yes
2019
Jan |  |  |  |  | 8 |  | 8 |  |  |  | 8
Mar | [7 empty] | 2 |  | 2 | 2
Apr |  |  |  |  | 1 |  | 1 |  |  |  | 1
Jun |  |  |  |  | 1 |  | 1 |  |  |  | 1
Jul | 2 | 2 |  |  | 6 |  | 6 |  |  |  | 8
Aug |  |  |  |  | 3 |  | 3 | 3 |  | 3 | 6
Sep | 2 | 2 |  |  | 1 |  | 1 |  | 2 | 2 | 5
Oct | 1 | 1 | [6 empty] | 1 | 1 | 2
Nov | [7 empty] | 1 |  | 1 | 1
2020
Feb |  |  |  |  | 1 |  | 1 | 1 |  | 1 | 2
Mar |  |  |  |  | 5 |  | 5 |  |  |  | 5
Apr |  |  |  |  | 6 | 1 | 7 |  |  |  | 7
May | 8 | 8 | [5 empty] | 1 | 2 | 3 | 11
Jun | 4 | 4 | 3 | 3 | 1 |  | 1 | 4 |  | 4 | 12
Jul |  |  |  |  | 2 |  | 2 |  | 1 | 1 | 3
Aug | 1 | 1 |  |  | 3 | 1 | 4 |  |  |  | 5
Sep |  |  | 1 | 1 |  |  |  |  | 1 | 1 | 2
Oct | 3 | 3 |  |  | 2 |  | 2 | 2 |  | 2 | 7
Grand Total | 21 | 21 | 4 | 4 | 40 | 2 | 42 | 14 | 7 | 21 | 88

## Sheet2
Row Labels | Count of Sub-Series Name
Completed | 94
In Progress | 28
Not Start | 19
Grand Total | 141

## Sheet3
Count of Sub-Series Name | Column Labels
Row Labels | Completed | In Progress | Not Start | Grand Total
2019
Jan | 8 |  |  | 8
Mar | 2 |  |  | 2
Apr | 1 |  |  | 1
Jun | 1 |  |  | 1
Jul | 8 |  |  | 8
Aug | 6 |  |  | 6
Sep | 5 |  |  | 5
Oct | 2 |  |  | 2
Nov | 1 |  |  | 1
2020
Feb | 2 |  |  | 2
Mar | 5 |  |  | 5
Apr | 7 |  |  | 7
May | 2 | 9 |  | 11
Jun | 1 | 11 |  | 12
Jul |  | 3 |  | 3
Aug |  | 4 | 1 | 5
Sep |  | 1 | 1 | 2
Oct |  |  | 7 | 7
Grand Total | 51 | 28 | 9 | 88